## Slide 1
Status and plan of
the mechanical and integration
Ji quan ，Xia shang，Zhang junsong
Feb. 28, 2024

## Slide 2
content:
progress of general drawing
progress of subdetector
personnel placement and division of work
next plan

## Slide 3
progress of general drawing：(Structural frame integrity)
Tracker confirm (Feb.23th)
HCAL ECAL (March 1st discussion)
Accelerator (Feb.29thdiscussion)
no shape
束流管不变
tracker
ecal

## Slide 4
Determine the Tracker detector boundary size：(Feb.23th，Tracker)
Ø1200 mm = r 0.6 m
Ø3600 mm = r 1.8 m
Silicon Tracker : 3 layers
How to react correctly to the detection angle?

## Slide 5
progress of subdetector
Confirm the boundary size of track detector —— 2月23日
Accelerator interface ——order(2月29日)
ECAL and HCAL discussion： ——order(3月1日)
Superconducting magnet discussed twice(张俊嵩) ——2月23日 26日
The iron yoke discussion (王小龙，宁飞鹏，夏商，张俊嵩，纪全) ——(2月20日)

## Slide 6
Progress of the iron yoke design
The yoke iron includes a barrel part and an end part, and the thickness of the barrel part is 600mm
Total weight: 1155 tons
Preliminary work: (on the base of mechanical design and installation)
1、Spiral and symmetrical structure
2、Optimal design of liron plate thickness
3、Top-level installation design

## Slide 7
recommend to choose the spiral structure
spiral structure
Symmetrical structure
Spiral type can achieve full coverage, symmetric type can not achieve full coverage
axial mount
side mount
Spiral type can achieve maintainability
Progress of the iron yoke design

## Slide 8
ecommend to choose the spiral structure
spiral structure stiffening plate
Symmetrical structure no stiffening plate
19.7mm max.
1.76mm max.
the spiral structure yoke iron strength is higher.
Progress of the iron yoke design

## Slide 9
Increasing the thickness of the upper and lowest iron layers can increase the overall rigidity of the yoke iron and install more μ-detector layers.
50 X 7 = 350 (μ space)
uniform thickness
off-gauge thickness
1.67mm max.
1.32mm max.
Progress of the iron yoke design
limit design

## Slide 10
interconnecte
Column installation scheme
Installation design with tooling
no tooling installation
High demand top-level design
“make”
Structure innovation.
Efficient installation design
Suggestion: Top-level design must be high demanding
Column scheme
Progress of the iron yoke design

## Slide 11
Iron yoke dicussion (Feb. 20th)：(王小龙，宁飞鹏，夏商，张俊嵩，纪全)
Previous design：thickness 600mm
Feb. 23th：thickness 1150mm
Avoid magnetic saturation
No. of μ layers is
invariant
Final design：thickness 950mm
7layers μ
620 ton
7layers μ
1710 ton
7layers μ 1280 ton
reason for suggestion：
1. thickness 600mm，20mm iron plate layers
meet stiffness requirements
2. thickness 950mm，70mmiron plate layers
meet stiffness requirements
3. thickness1150mm，
The width of detector varies greatly
conclusion：
The larger the total thickness, the greater the difference in μ detector width
Progress of the iron yoke design

## Slide 12
Superconducting magnet built-in scheme
8-sided
12-sided
16-sided
Conclusion: It is found that the larger the number of edges is, the larger the difference of detector size is
Progress of the iron yoke design

## Slide 13
Superconducting magnet built-out scheme
Progress of the iron yoke design

## Slide 14
Superconducting magnet built-out scheme
Conclusion: It is recommended to adopt 12-sided and 800mm yoke thickness scheme
Progress of the iron yoke design
8-sided
12-sided

## Slide 15
personnel placement：
Silicon tracker
DC or TPC
subdetector division：tentative
Iron yoke： 夏商
HCAL： 侯少静
Magnet： 张俊嵩 (南华，陈梓勃)
ECAL： 侯少静 (湖大，李宇杰)
Tracker： 付金煜
Beampipe： 张俊嵩(湖大，何龙岩)
personnel：
Mechanical Engineer：纪全，张俊嵩，付金煜，侯少静，夏商(students)
other staffs：王铮，石澔屿
February 19th，am.10:00 – 12:20，

## Slide 16
Next plan
Complete general drawing
Design boundary constraint
interface structure
leading line
Sub-detector frame structure
Iron yoke and base
ECAl
HCAL
superconducting magnet
Tracker
Beam pipe
Connecting structure
optimization gap
leading line space and requirment
Installation plan
Iron yoke
ECAL
HCAL
superconducting magnet
Tracker
Beam pipe

## Slide 17
Thanks