## Slide 1: Beam Commissioning of the CSNS Sheng Wang Yong Li for CSNS Accelerator Team Institute of High Energy Physics, CAS Aug. 29, 2017 g
SAP2017, Jishou, 28-30 August 2017

## Slide 2: Outline
Project Overview
Linac Commissioning
RCS Commissioning
Summary
2
2

## Slide 3
The phase-I CSNS facility consists of an 80-MeV H- linac, a 1.6-GeV RCS, beam transport lines, a target station, and 3 instruments.
Project Overview

## Slide 4: Key Milestones
4
Feb. 2001 | idea of CSNS discussed
June 2005 | proposal approved in principle by the central government (CD0)
Jan. 2006 | prototyping R&D started
Sept. 2008 | proposal approved
Oct. 2009 | feasibility study report reviewed
April 2010 | site preparation start
Feb. 2011 | feasibility study report approved (CD-1)
May 2011 | preliminary design report approved (CD-2)
Sept. 2011 | construction started (CD-3), component fabrication started
May 2012 | civil construction started
Oct. 2014 | Frontend and LRBT started installation in Linac tunnel
April 2015 | the RCS magnets started installation in RCS tunnel
May 2015 | the Helium Vessel of the target station installed
Jan. 2016 Apr. 2017 | DTL-1 Beam commissioning Linac beam commissioning
May. 2017 | RCS commissioning start
Sept. 2017 | first beam on target
Mar. 2018 | project complete/operation start (6.5 years from start)
Front end | Oct.18,2013-Apr.10, 2014 | 125 days
RFQ,MEBT,DTL1 | Jun.5,2014-Aug.27, 2014 | 60 days
DTL2-4 | Jun.30, 2015-Nov.3, 2015 | 90 days
LRBT+Linac | Nov.4,2015-Jan.6, 2016 | 46 days
RCS | May13,2016-Mar.2, 2017 | 210 days
RTBT | Mar.3,2017-May 25, 2017 | 60 days
First beam on target | Aug.24, 2017 | 
Beam power to 10kW | Aug.25,2017-Mar.3,2018 | 6 months
Beam power to 100kW | Mar.3,2018-Mar.3,2021 | 3 years
Notes: Conventional facility @ infrastructure completed
Key technology R&D

## Slide 5: Site Area
The site of CSNS locates at Dongguan, Guangdong Province.
The Dongguan local government provided a land of about 0.67km2 for CSNS campus. 0.27-km2 is used for the phase-I construction.

## Slide 6
May 2009: before land breaking
Aug 2011: land is prepared

## Slide 7
CSNS site

## Slide 8
Linac service building
RCS service building
Target and experiment Hall

## Slide 9
Linac tunnel
RCS tunnel

## Slide 10
Linac Commissioning
10

## Slide 11: LEBT, RFQ and MEBT (beam commissioning at June 2015)
 | Design | Achieved
Peak current [mA] | 15 | 17
Beam energy[MeV] | 3.025 | 3.02±0.015
Chopping rate [%] | 50 | 50
Pulse width [μs] | 420 | 500
Pulse repetition rate [Hz] | 25 | 25
Simulated Emittance=0.22 PI mm-mrad Measured Emittance=0.27 PI mm-mrad

## Slide 12: Transverse emittance measurement:1
Wireanalysis
XAL
Wire scanner
Beam RMS size along the MEBT
 | α | β[mm/mrad] | Emittance [πmm mrad]
Horizontal Measured / Simulated | -1.716 /-1.773 | 0.256 / 0.233 | 0.215 / 0.215
Vertical Measured / Simulated | 1.944 / 0.639 | 0.173 / 0.074 | 0.211 / 0.212

## Slide 13: Transverse emittance measurement:2
(a) X(mm)-X’(rad)
(b) Y(mm)-Y’(rad)

## Slide 14
DTL commissioning
Temporal Beam Diagnostic system:
1BPM,1CT,2FCT,1 QEM,1 x-y steering magnet,1EM,1WS
1 Energy degrader /Faraday cup,1 Beam dump(0.163kW)
Tank1
Tank2
Tank3
Tank4
CT
FCT
CT
FCT
CT
FCT
Tank number | 1 | 2 | 3 | 4 | total
Output energy (MeV) | 21.67 | 41.41 | 61.07 | 80.09 | 80.09
Number of cell | 64 | 37 | 30 | 26 | 157
RF driving power (MW) | 1.35 | 1.32 | 1.32 | 1.34 | 5.33
Total RF power (MW) (I=15mA) | 1.62 | 1.62 | 1.62 | 1.63 | 6.49
Accelerating field (MV/m) | 2.86 | 2.96 | 2.96 | 3.0 | 
Synchronous phase (degree) | -35 to -25 | -25 | -25 | -25 | 

## Slide 15: DTL beam commissioning
DTL-1: In 2016, 18mA/21.67MeV/50us/1Hz beam was obtained, which exceeds the design goal of beam current of 15mA. the beam reached the end of the first DTL tank with peak current of 18mA at 21.67 MeV, with transmission rate ～ 100%.
DTL-2,3: In April 2017, beam from DTL-3 about 15mA @ 60MeV.
Beam current measurement from CTs for beam commissioning of DTL-1 and DTL-3.

## Slide 16
Setting DTL RF amplitude and phase
XAL, Pasta (an RF phase scan and tuning application)
Signature matching
 | Design [MeV] | Phase scan [MeV] | TOF [MeV]
RFQ | 3.026 | 3.029 | 3.027 ±0.01
DTL1 | 21.669 | 21.802 | 21.685±0.01
DTL2 | 41.415 | 41.52 | 41.566±0.14
DTL3 | 61.072 | 60.917 | 61.09±0.34
All the energy deviation are < 1%
 | DTL1 | Design
Φcavity（degree） | 41 | -35
Amp | 6333 | 2.86MV/m
WRFQ(MeV) | 3.029 | 3.0258
WDTL1(MeV) | 21.802 | 21.67

## Slide 17: LRBT matching
Simulation data
Measurement data
Before
matching
After
matching

## Slide 18: LRBT Orbit correction
before correction
after correction
± 13mm
± 2mm

## Slide 19: RCS Commissioning

## Slide 20: RCS Dry Running
A week per time, 2 times
Problem found:
Water leakage was found in one cavity.
Cooling tubes of two AC magnets were burned through.
17 chokes had strong vibration and had been returned to the manufacture to repair.
Ceramic vacuum chamber Broken
Arc of extraction kicker
……

## Slide 21: Beam Commissioning to Inj. Dump

## Slide 22: RCS Beam Commissioning-DC mode
To control the beam loss during the beam commissioning, the single shot beam mode is adopted. In the first step, the beam commissioning was started in DC mode without acceleration.
In May 31st, the first beam was injected into the RCS, and successfully accumulated in the RCS. The maximum accumulated particle number is about 1/3 of the design goal.
In June 5th, the first beam was extracted to RCS dump.

## Slide 23
1：Optimization of RF pattern
2：Optimization of the B field
  Optimization of the accumulation
3：Injection painting
One day later, beam transmission was more than 98%

## Slide 24
  60 MeV Beam Extraction to R-Dump

## Slide 25: Tune measurement
Measured Tune：4.857/4.779 Design Tune：4.86/4.78

## Slide 26
  Orbit correction
before correction
± 10mm
± 5mm
± 5mm
X
Y
after correction
after correction

## Slide 27: Online Model
 | Tunex | Tuney
Design model | 4.86 | 4.78
Without fringe field in Openxal | 4.946 | 4.979
With fringe field in OpenXAL | 4.863 | 4.785
Measured Tune | 4.857 | 4.779
Chart: 
| 1.0 | 2.0 | 3.0 | 4.0 | 5.0 | 6.0 | 7.0 | 8.0 | 9.0 | 10.0 | 11.0 | 12.0 | 13.0 | 14.0 | 15.0 | 16.0 | 17.0 | 18.0 | 19.0 | 20.0 | 21.0 | 22.0 | 23.0 | 24.0 | 25.0 | 26.0 | 27.0 | 28.0 | 29.0 | 30.0 | 31.0
R1DH09_the | -539.5401 | -108.5516 | 785.0891 | 752.2675 | -556.6932 | -757.1855 | 71.4087 | 383.8773 | 902.0374 | 770.7632 | -215.953 | -345.2774 | -26.5473 | 165.5546 | 915.5862 | 624.5301 | -335.7404 | -869.0273 | -749.34 | 730.4615 | 870.8427 | 304.2861 | 6.2909 | -935.8059 | -956.2074 | -189.8231 | -3.7693 | 371.9315 | 244.8733 | -736.6191 | -876.2541
R1DH09_mea | -512.024 | -67.5764 | 812.5459 | 770.4564 | -549.0463 | -754.9581 | 92.3493 | 433.6983 | 894.6933 | 768.4048 | -196.3841 | -304.3141 | 0 | 183.4883 | 881.9058 | 585.3683 | -344.336 | -843.2621 | -714.9135 | 730.5237 | 910.1606 | 279.6427 | -29.7309 | -898.7661 | -933.7379 | -153.5887 | 24.8017 | 370.0219 | 243.9132 | -723.8676 | -859.6237
Response matrix
Chart: 
| 1.0 | 2.0 | 3.0 | 4.0 | 5.0 | 6.0 | 7.0 | 8.0 | 9.0 | 10.0 | 11.0 | 12.0 | 13.0 | 14.0 | 15.0 | 16.0 | 17.0 | 18.0 | 19.0 | 20.0 | 21.0 | 22.0 | 23.0 | 24.0 | 25.0 | 26.0 | 27.0 | 28.0 | 29.0 | 30.0 | 31.0
R1DV02_the | 354.3302 | 794.5382 | -524.6566 | -854.5586 | -346.9807 | -111.0552 | 1106.0595 | 815.6405 | -97.0085 | -307.2133 | -699.9378 | -894.6924 | 827.6674 | 655.8021 | 428.5269 | -183.6714 | -1032.1677 | 60.5875 | 272.724 | 955.4864 | 583.0753 | -882.6133 | -744.992 | -483.182 | -405.9222 | 739.3691 | 1072.1852 | -205.8225 | -276.3172 | -985.7484 | -479.4547
R1DV02_mea | 285.2769 | 684.0424 | -528.4436 | -821.7516 | -250.5981 | -66.7412 | 1024.0884 | 716.4849 | -123.7814 | -325.2619 | -595.4264 | -747.3224 | 781.6049 | 613.6908 | 335.8672 | -199.895 | -911.5651 | 84.3567 | 267.7336 | 818.6099 | 510.2285 | -795.2451 | -682.4877 | -416.6637 | -362.4826 | 669.2117 | 967.4674 | -179.3567 | -237.5179 | -907.2757 | -439.0001
Fringe field is added to the online model of OPEN XAL.
Field interference is also included.

## Slide 28
Fudge factor by response matrix
Nominal tune: Tunex/tuney: 4.8532/ 4.7816
Measured tune: Tunex/tuney: 4.8568/ 4.7765
After correction: Tunex/tuney: 4.854/ 4.778
Max. beta-beating :0.12

## Slide 29
  RCS Beam Commissioning-AC mode
Beam life time is 4ms in the first shot.
Beam accelerated to 1.6GeV
Shift timing between RF and B field, then major part of beam was accelerated to 1.6GeV and extracted.
July 7, the first beam was accelerated from 60MeV to 1.6 GeV
July 7

## Slide 30: Finally reached about 99% beam transmission rate at RF frequency (0.9018, 2.444MHz）
  RF parameter optimization
Tuning RF amplitude 、frequency curve
July 9

## Slide 31: Modify tune with one cycle
Chart: Turn Number
| 1000.0 | 2000.0 | 3000.0 | 4000.0 | 5000.0 | 6000.0 | 7000.0 | 8000.0 | 9000.0 | 10000.0 | 11000.0 | 12000.0 | 13000.0 | 14000.0 | 15000.0 | 16000.0 | 17000.0 | 18000.0 | 19000.0
Qx:Design model | 0.7402 | 0.7607 | 0.7666 | 0.7715 | 0.7803 | 0.7852 | 0.7905 | 0.792 | 0.7959 | 0.7983 | 0.8037 | 0.8169 | 0.8271 | 0.8335 | 0.8442 | 0.8512 | 0.8555 | 0.8611 | 0.8611
Qy:Design model | 0.78705 | 0.76578 | 0.76578 | 0.75541 | 0.74119 | 0.71355 | 0.71227 | 0.71731 | 0.71466 | 0.72621 | 0.71951 | 0.73414 | 0.73582 | 0.75222 | 0.75001 | 0.76266 | 0.76415 | 0.77188 | 0.79759
Chart: Turn Number
| 1000.0 | 2000.0 | 3000.0 | 4000.0 | 5000.0 | 6000.0 | 7000.0 | 8000.0 | 9000.0 | 10000.0 | 11000.0 | 12000.0 | 13000.0 | 14000.0 | 15000.0 | 16000.0 | 17000.0 | 18000.0 | 19000.0
Qx:Optimized model | 0.8689 | 0.8529 | 0.8438 | 0.8348 | 0.8328 | 0.8298 | 0.8278 | 0.8248 | 0.8238 | 0.8238 | 0.8268 | 0.8308 | 0.8378 | 0.8438 | 0.8539 | 0.8549 | 0.8609 | 0.8679 | 0.8649
Qy:Optimized model | 0.7668 | 0.7658 | 0.7628 | 0.7628 | 0.7598 | 0.7588 | 0.7628 | 0.7648 | 0.7748 | 0.7788 | 0.7688 | 0.7628 | 0.7698 | 0.7738 | 0.7728 | 0.7818 | 0.7738 | 0.7688 | 0.7658
△Qx=0.12
△Qy=0.06

## Slide 32: Beam loss distribution around RCS
Before optimization
After
optimization

## Slide 33: 1.6 GeV Extraction
1.6GeV Proton beam was extracted from RCS with low beam loss along the beam line.

## Slide 34: COD correction
20 orbits at 20 different energy points were chosen to display and correction.

## Slide 35
before correction
After correction
Live orbit
Predicted orbit

## Slide 36: Fixed bump injection and painting injection
Compared to the painting injection, there is more beam loss during the injection process for the fixed bump injection.
Fixed bump injection
Painting injection

## Slide 37
The first beam on the target
Aug. 28, 2017

## Slide 38: Application software development based on XAL
Early preparation:
Optics files in XAL format was created.
EPICS soft IOC for the conversion between power supply and magnet field is created.
Testing the communication(PV) with hardware.
Software platform is created in new control room.
A GIT server was set up for software version control.
Applications development
Directly used \little modification\ self developed
JAVA\MATLAB\JAVAFX/Python
Database creation
Database: PVlogger\score\model-lattice\magnet
OPENXAL contribution
Add fringe filed to online model and created machinesimulator app.
Matlab
Python
Hardware
EPICS
XAL
GUI
App *
App *
App *
App *
App *

## Slide 39: Summary
    CSNS project comes its final stage after 6-year construction.
With 60 MeV injection beam, beam commissioning have been doing with a good performance of 1.6GeV beam extraction.
We plan to commission linac beam at 80MeV with 4 klystrons in November.
The official acceptance will be done in the Mar. of 2018, as promised.

## Slide 40
Thank you!