## Slide 1: Cryogenics at the European Spallation Source Challenges of parallel installation and commissioning activities
Philipp Arnold
Section Leader Cryogenics
www.europeanspallationsource.se
June 05, 2018

## Slide 2: Aerial view May 2018
Coldbox Building G.02

## Slide 3
Cryo Buildings

## Slide 4: Outline
Cryogenic system overview and status
How do we prepare installation activities
What happens in parallel commissioning
A practical tool to ensure workers safety
Outlook and conclusions

## Slide 5: (1.2) Cryogenics at the site - overview
Cryo Compressor Building
Coldbox Hall
Cryogenic Moderator Room
Neutron Instrument Halls
Accelerator Tunnel
Cryomodule Teststand

## Slide 6
Cryo Buildings

## Slide 7
Pure Helium
Gas Storage
Standalone Helium Purifier
Helium Recovery System
Accelerator
Cryoplant
5 m3
LHe Tank
Target Moderator
Cryoplant
LHe Mobile Dewars
Test Stand Cryodistribution System
Instruments & Experiments
LN2 Storage Tanks
LN2 Mobile Dewars
Cryodistribution System for Elliptical Linac
Elliptical
Cryomodules
Test Stand Lund 2
Target Cryodistribution System
Hydrogen Circulation Box
Hydrogen Moderator
Cryodistribution System for
Spoke Linac
Spoke
Cryomodules
20 m3 LHe Tank
(1.3) System overview – block diagram
Test & Instrument Cryoplant
Notes: ACCP: 3kW @ 2K, 11kW @ 40K, 270 l/h Liquefaction  special plant, power consumption in MW range, big industrial compressors, sophisticated CC system
TICP: 76W @ 2K, 420W @ 40K, 6 l/h Liquefaction  plant well in the standard range
TMCP: 32kW @ 15-20K  very large again, some challenges but not terribly sophisticated process, compared to ACCP
Large and sophisticated cryo-distribution system for all plants and their consumers

## Slide 8: (1.4) Master Schedule WP11 Cryogenics

## Slide 9: (1.5) Test and Instruments Cryoplant

## Slide 10: (1.5) Test and Instruments Cryoplant

## Slide 11: (1.6) Accelerator Cryoplant
REMINDER
June 6, 2018, 16.30 – 16.50:
Progress in the installation of the ESS Accelerator Cryoplant, Xilong Wang

## Slide 12: (1.7) Target Moderator Cryoplant

## Slide 13: (1.7) Target Moderator Cryoplant

## Slide 14: Outline
Cryogenic system overview and status
How do we prepare installation activities
What happens in parallel commissioning
A practical tool to ensure workers safety
Outlook and conclusions

## Slide 15: (2.1) Installation preparation
Preparation of Installation Readiness Reviews for all bigger equipment packages / subsystems
Main document: Work and Safety Coordination Plan
Many appendices relating to safety rules, construction site rules, work orders etc.
Installation schedule, Transport and delivery plan
Manpower, tools, equipment, temporary storage planning
Safety training matrix
ESS safety awareness courses
Pre-work visit, ID06, PPE

## Slide 16: (2.2) During installation
Update Area Hazard Analysis
Check Job Hazard Analysis / Method statements
Follow Inspection and Test Plan for installation
Weekly / daily work coordination meetings
Safety rounds
Building, site services, utilities coordination

## Slide 17: (3) Pre-commissioning activities
Blow down of lines
Evacuation and pressure/purge cycles
Oil adsorber heating
Cold adsorber activiation header
Cooling water flushing
Valve check-out / instrument air
Helium filling
Etc.

## Slide 18: Outline
Cryogenic system overview and status
How do we prepare installation activities
What happens in parallel commissioning
A practical tool to ensure workers safety
Outlook and conclusions

## Slide 19: (4.1) Integrated P&ID

## Slide 20: (4.1) P&IDs and derivates
Integrated P&ID of entire installation
Specific reduced P&IDs for common interfaces
  Cooling water
  Instrument air
  Nitrogen
  Helium buffer lines
  Safety relief headers and helium recovery
One special interface connecting ACCP and TICP LP
Attention to inside-skid interfaces

## Slide 21: (4.2) Creating a database
Piping List
Interface List
Valve
List
Instrument List
…

## Slide 22: (4.3) Defining energisation procedure
Procedure for pressurization of cryogenics sub-system(s)
Make a request online for pressurization [1]
Check with the affected sub-system owner(s) that the sub-system(s) can be pressurized (no on-going work)
Approval given to the CT to pressurize the sub-system(s)
Operator
Cryogenics Technician
Sub-system owners affected
Implementation of safety measures (e.g. marking, signposting, valve blocking, etc.)
Cryogenics Technician
Check that the sub-system(s) is(are) safe before pressurization
Update of the cryogenic system database
The sub-system(s) is(are) pressurized after final approval from the CT
Cryogenics Technician
Cryogenics Technician
Information sent to the requester and sub-system owner(s) that the system(s) is(are) pressurized

## Slide 23: (4.3) Defining de-energisation procedure
Procedure for de-pressurization of cryogenics sub-system(s)
Make a request online for de-pressurization [1]
Information sent to the CT
Job description
Sub-system(s) affected
Work duration
Approval given to the CT to de-pressurize the sub-system(s)
Operator
Sub-system owner(s) affected
The sub-system(s) is(are) ready to be de-pressurized
The sub-system(s) is(are) de-pressurized after final approval from the CT
Information sent to the requester and sub-system owner(s) that the sub-system(s) is(are) de-pressurized
Update of the cryogenics system database [2]
Cryogenics Technician
Cryogenics Technician
Implementation of safety measures (e.g. marking, signposting, valve blocking, etc.)
CT informs the affected sub-system owner(s)
Cryogenics Technician
Cryogenics Technician

## Slide 24: (4.4) Realisation of procedure
Defining roles
  Sub-system owners and deputies
  Requesters
  Gate keeper and deputy
Use Atlassian JIRA as database and request handling tool
Continuously train and remind partners to follow procedure REGLIGIOUSLY

## Slide 25: (4.5) Database of piping system

## Slide 26: (4.6) Realisation de-energisation request
After request is finalised the gate keeper is informed by automatic email notification

## Slide 27: (4.7) Gate keeper adds details to request

## Slide 28: (4.8) Gate keeper informs approver(s)

## Slide 29: (4.9) Gate keeper prepares de- energisation

## Slide 30: (4.9) Procedure in practice
Inform everybody involved
Mount warning signs
Block valves
Etc.

## Slide 31: (4.10) De-energisation performed and acknowledged

## Slide 32: (4.11) Piping status overview

## Slide 33: (4.12) ODH and access control
Access control by information
Access control with card readers
Personal ODH monitors
Permanent ODH monitors

## Slide 34: Outline
Cryogenic system overview and status
How do we prepare installation activities
What happens in parallel commissioning
A practical tool to ensure workers safety
Outlook and conclusions

## Slide 35: (5.1) What next
Include measurements, evacuation and purge points in database
Include circuits inside skids in database
Transform JIRA tool from documentation system to work order system
Use statistical tools offered by JIRA
Connect permanent ODH monitors to PPS and backed-up power
Intelligent card reader system

## Slide 36: (5.2) Summary
Good progress on cryogenic systems installation at ESS
Managing parallel installation and (pre-) commissioning activities is challenging
Personal safety is absolute key
Entire team to be involved early in system interconnections and procedures
Questions?