## Slide 1: CEPC alignment and installation optimization Wang Xiaolong HDEC CEPC Day Jun 28 2019

## Slide 2: Contents
  Tasks of alignment and installation
  Control network construction and survey
  Component installation and alignment
  Smooth alignment
  Problems & next work
  Summary

## Slide 3
Tasks of alignment and installation
  Control network construction.
  Control network measurement
  Support installation setting out
  Collider ring installation and alignment.
  Booster installation and alignment
  Linac and BT installation and alignment
  Smooth alignment

## Slide 4
Tasks of alignment and installation
  HDEC CPM, Civil construction is divided into two phases
  Purpose is to finish the first phase construction and lining, then can start alignment and installation.
  Civil construction 2024,1-2028,9 (华东院2019,3,7)
  Alignment and installation 2027,1-2030,9
  Alignment and installation scheme is based on HDEC CPM.
2024
2025
2026
2027
2028
2029

## Slide 5
Control network construction
  Tunnel length 109.55km：100.034km main ring + 6.64kmIR booster tunnel + 1.21km Linac + 0.06km DR+ 1.07km BT + 2X0.268km BT
  Control network: along the tunnel, every 6m one section, each section 4 points, number of total points is 73036.
  Construction after tunnel lining
  One team 3~4 persons, one team one section 2.5h, 12h/day, 18259 sections will devote 16 teams, 9 months.
  Control network construction will parallel with tunnel lining. About 2 months later than lining.
  If tunnel civil construction is divided into two phases, control network construction will follow it.
  first phase: 2027,1,1—2027,9,30 8 teams, 9 months 230m/day
  second phase: 2027,10,1—2028,8,30 8 teams, 11 months, ended 2 months later than that of tunnel lining

## Slide 6
Control network measurement
  Backbone control network measurement.
  To satisfy the intervisible requirement, the distance between adjacent section is about 220m. About 996 points in the whole tunnel.
  Use total station forced center on each point, total 996 stations.
  One team 5 stations / day.
  Level control network measurement
  Use back and forth measurement method for every kilometer
  The back and forth sight distances are 18m each.
  The level route length is 109550 X2=219km.
  One team 4km / day.
  Tunnel control network measurement
  Use laser tracker, 18259 sections, 18259 X2=36518 stations.
  One team 10 stations / day.

## Slide 7
Control network measurement
  Control network measurement will parallel with the control network construction and civil construction.
  Considering the complexity of civil construction, measurement area should away from civil construction area. devote 20 months for control network measurement.
  2 months after the start of control network construction
  first phase: 2027,3,1—2027,11,30, 9 months
    Measurement : 2027,3,1—2027,10,31, 8 months, ended 1 month later than control network construction.
    Tunnel network measurement 12 teams, backbone network 4 teams, level network 4 teams.
    2027,11: one month for measurement data process.
  Second phase: 2027,12,1—2028,10,31, 11 months
    Measurement: 2027,12,1—2028,9,30, 10 months, ended 1 month later than control network construction
    Tunnel network measurement 12 teams, backbone network 4 teams, level network 4 teams.
    2028,10: one month for measurement data process.

## Slide 8
Ring tunnel support installation setting out
  Collider ring and booster will be carried out simultaneously
  Support number: collider ring 50378 + booster 38966 = 89344
  Setting out will begin after the first phase tunnel network measurement been finished
  One team one day 15 supports
  2027,12,1—2029,2,28, 15 months, 16 teams

## Slide 9
Collider ring installation and alignment
  Support installation
  Support number: 50378
  Support installation will begin one month later than support setting out
  2028,1,1—2029,4,30, 16 months, 8 teams, parallel with setting out
  Component installation and alignment
Component | Collider Ring
Dipole | 2546 (13006分段)
Quadrupole | 3712
Sextupole | 1864
Corrector | 5808
Superconducting Cavity | 240
Cryomodule | 40（11米）
Superconducting quadrupole | 8
Superconducting sextupole | 32
Solenoid | 4
BPM | 2910
Total | 16976

## Slide 10
Collider ring installation and alignment
  Component installation will begin one month later than support installation
  Installation progress
Component | Piece (1 team / day) | Month | Team
Dipole | 2 | 16 | 16
Quadrupole | 4 | 4 | 8
Sextupole | 4 | 2 | 8
Corrector | 6 | 9 | 4
Cryomodule | 2 | 1 | 1
Solenoid | 4 |  | 
BPM | 6 | 5 | 4
  2028,2,1—2030,2,28 25 months, 16 teams

## Slide 11
Booster installation and alignment
  Support installation
  Support number: 38966
  One team one day 15 supports. Start at the same time as that of collider ring
  2028,1,1—2029,2,28, 14 months, 8 teams
  Component installation and alignment
Component | Booster
Dipole | 16320
Quadrupole | 2036
Sextupole | 448
Corrector | 350
Superconducting Cavity | 96
Cryomodule | 12（12米）
Septum Magnet | 144
Kicker | 22
BPM | 1900
Total总计 | 21328

## Slide 12
Booster installation and alignment
  Component installation will begin one month later than support installation
  Installation progress
Component | Piece (1 team / day) | Month | Team
Dipole | 2 | 20 | 16
Quadrupole | 4 | 5 | 4
Sextupole | 4 | 1 | 4
Corrector | 6 | 1 | 2
Cryomodule | 2 | 1 | 1
Septum Magnet & kicker | 4 | 2 | 1
BPM | 6 | 3 | 4
  2028,2,1—2030,2,28 25 months 16 teams

## Slide 13
Linac and BT installation and alignment
  Support installation setting out
  Support number: 1511
  One team one day 20 supports.
  2028,10,1—2028,12,31, 3 months, 1 team
  Support installation 2028,11,1—2029,2,28, 4 months, parallel with setting out
  Component installation and alignment
Component | Linac and BT
Dipole | 140
Quadrupole | 464
Sextupole | 24
Corrector | 139
RF Cavity | 2
Septum Magnet | 2
Kicker | 2
Solenoid | 41
Accelerating structure | 285
Cavity | 3
BPM | 300
Total总计 | 1402

## Slide 14
Linac and BT installation and alignment
  Installation progress
Component | Piece (1 team / day) | Month/day | Team
Dipole | 2 | 3 | 1
Quadrupole | 4 | 4 | 1
Corrector | 6 | 1 | 1
Sextupole | 4 | 1 | 1
RF Cavity | 2 |  | 1
Septum Magnet | 4 |  | 1
kicker | 4 |  | 1
Solenoid | 4 |  | 1
Cavity | 2 |  | 1
BPM | 6 | 2 | 1
Accelerating structure | 4 | 3 | 1
  2028,12,1—2030,1,31 14 months 1 team

## Slide 15
Smooth alignment
  CEPC installation and alignment will last more than 2 years
  Control network deformation, ground settlement and component stress release will destroy the alignment result.
  After the initial alignment, it needs an overall smooth alignment.
  Smooth alignment include an overall survey of control network and component, as well as component offset smooth adjustment.
  2030,3,1—2030,9,30 7 months 32 teams

## Slide 16
Problems & next work
  Civil construction will be carried out in two phases, but the detailed area and progress of every phase has not been determined.
  Setting out, installation and alignment will be carried out parallel, in such a narrow tunnel they will interfere with each other.
  Peak time: need to keep a huge alignment and installation team
    Network measurement: 2027,12,1—2028,9,30 12+4 teams
    Setting out: 2027,12,1—2029,2,28 16 teams
    Collider ring alignment: 2028,2,1—2030,2,28 16 teams
    Booster alignment: 2028,2,1—2030,2,28 16 teams
    Linac alignment: 2028,10,1—2028,12,31; 2028,12,1—2030,1,31 1 teams
    Smooth alignment: 2030,3,1—2030,9,30 32 teams
    Compatible installation teams to match up with component alignment.
    Not include component fiducialization teams.

## Slide 17
Problems & next work
  Next work
    Further refine each region installation plan
    Make component fiducialization progress plan (need to get component fabrication progress plan)
    Supplement and improve installation & alignment plan

## Slide 18
Summary
  Tunnel alignment and installation tasks are introduced
  Tunnel control network construction and measurement progress plan is made. It should follow the civil construction progress.
  Component installation and alignment will start after the first phase control network survey. It will last more than 2 years. During this period many works will be carried out in parallel, we need to keep a huge team.
  Smooth alignment is necessary, it requires an enough investment of time and manpower.
  Problems include determine region construction process, mutual interference, huge team.
  Next: Installation & alignment plan need to be further refined. Component fiducialization & pre-alignment plan need to be made.

## Slide 19
Thank You !