## Slide 1: Progress of LHAASO Muon Detector array
Gang Xiao
Zhu Hai
23.Oct.2019

## Slide 2: outline
brief introduction of MD array
Progress of MD
Plan of MD

## Slide 3: Brief introduction
Array
Unit detector

## Slide 4: General specifications of muon detector
performance parameter | Index requirements
detection efficiency | ≥95%
Particle number resolution | Single particle：25%；10000 particles：<5%
Time resolved | <10ns
dynamic range | 1～10,000particles
Punch-through Effect | The purity of μ measurement>95%
Long term stability | Signal attenuation less than 20% in 10 years

## Slide 5: LHAASO-MDA
30meters spacing
40000 m^2 effective area

## Slide 6: detector design
soil
PMT
6.8m
1.2m
ultrapure water
electronics

## Slide 7: progress
1、Production and inspection of components
2、Installation progress
3、1/4 array performance

## Slide 8: Summary of the development of ultra pure water inner liner
745 liners completed by October 2019 .
As of the beginning of October 2019, 667 sets of inner liner have been transported to Daocheng, including 306 sets of double Tyvek inner liner.
The inner liner installed by MD is in good sealing condition .
In 2019, the production of inner liner shall meet the requirements of project schedule and meet the project installation schedule.

## Slide 9: Summary of insulation development
By the middle of October 2019, 508 insulation layers have been installed.
The insulation layer is installed smoothly, the quality is up to standard, and meets the current project.
Inner diameter distribution
(Internal diameter requirement: 6.8 ± 0.01m)
Bottom level distribution
Bottom levelness requirement: ± 0.005m

## Slide 10: Other parts are also produced on time
Protection system:774
Electronics:500
Power Supply:600
PMT:595

## Slide 11
Foundation pit treatment
Fabrication of side wall and bottom plate
Head cover mounting
Install insulation board
Install liner and PMT
ultrapure water infusion
debug
Installation technology
Covering soil
intergrated test

## Slide 12: pro
Irrigation completed
Debugging completed
Map of the Progress
Completion of soil covering
Power on completion
Electronics installation completed
Detector operation

## Slide 13: debugging equipment
The inner space of the sealing cover is 20000l, the air volume of the inner liner is 2500L, and the SF6 gas is 300L. If the SF6 leakage detector detects that the SF6 concentration in the space of the sealing cover exceeds 9.5ppm within 30 minutes, it is deemed that the quality of the inner liner is unqualified.
Leak detection equipment
Two sharp weapons

## Slide 14: Operation survey of quarter MD array
304 MDs in DAQ；
295~298 TCP/IP attachable；
293~295 with hits information；
Occupancy around 0.04, per 12 MDs fired in a shower；
Abnormal MDs：
（1） Connection impassability ：~7
（2）Lower single rate：~5
（3）Higher single rate：2
（4）Other problems, such as abnormal pedestal , charge and waveform：4
For details of performance of the ¼ MD array，Please pay attention to Xiong Zuo’s report: Performances and calibration of ¼ LHAASO-MD array

## Slide 15: Some long-term operation diagrams
temperature
humidity
external
internal

## Slide 16
single rate
NPE

## Slide 17
decay time
AD ratio

## Slide 18: Next step plan
2019 plan: 1/2
2020 plan: entire

## Slide 19: summary
¼ array of LHAASO-MD has been constructed and put into DAQ access ,The monitoring results show that the detector works well.
½ array installation plan is expected to be completed successfully in 2019