## Slide 1: Progress of LHAASO Muon Detector array
Gang Xiao
Cheng Du
18.Aug.2020

## Slide 2: outline
brief introduction of MD array
Progress of MD
Plan of MD

## Slide 3: Brief introduction
Array
Unit detector

## Slide 4: General specifications of muon detector
performance parameter | Index requirements
detection efficiency | ≥95%
Particle number resolution | Single particle：25%；10000 particles：<5%
Time resolved | <10ns
dynamic range | 1～10,000particles
Punch-through Effect | The purity of μ measurement>95%
Long term stability | Signal attenuation less than 20% in 10 years

## Slide 5: LHAASO-MDA
30meters spacing
40000 m^2 effective area

## Slide 6: detector design
soil
PMT
6.8m
1.2m
ultrapure water
electronics

## Slide 7: progress
1、Production and inspection of components
2、Installation progress
3、1/2 array performance

## Slide 8: Summary of the development of ultra pure water inner liner
1184/1230 liners completed.
1084 sets of inner liner have been transported to Daocheng, including 306 sets of double Tyvek inner liner.
The inner liner installed by MD is in good sealing condition .
In 2020, the production of inner liner shall meet the requirements of project schedule and meet the project installation schedule.

## Slide 9
Foundation pit treatment
Fabrication of side wall and bottom plate
Head cover mounting
Install insulation board
Install liner and PMT
ultrapure water infusion
debug
Installation technology
Covering soil
intergrated test

## Slide 10
Irrigation completed(846)
Debugging completed(831)
Map of the Progress
Completion of soil covering(808)
Power on completion(700)
Electronics installation completed(593)
Detector operation(593)

## Slide 11: Performance of 1/2 MD array
593 MDs in DAQ；
593 TCP/IP attachable(8.16)；
592 with hits information(8.16)；
For details of performance of the 1/2 MD array，Please pay attention to Xiong Zuo’s report: Performances and calibration of 1/2 LHAASO-MD array
numbers of MD:

## Slide 12: Some long-term operation diagrams
Temperature (internal)
humidity
Temperature ( external)

## Slide 13
single rate
NPE
decay time
AD ratio

## Slide 14: Next step plan
2020 plan: 3/4
2021 plan: entire

## Slide 15: summary
1/2 array of LHAASO-MD has been constructed and put into DAQ access ,The monitoring results show that the detector works well.
3/4 array installation plan is expected to be completed successfully in 2020