## Slide 1
高能环形正负电子对撞机关键技术研发和验证
课题2：硅径迹探测器关键技术验证
报告人： 梁志均
项目负责人： João Guimarães da Costa
项目承担单位：中国科学院 高能物理研究所
国家重点研发计划

## Slide 2
R&D and Verification of Key Technologies for a High Energy Circular Electron-Positron Collider
国家重点研发计划
课题2：硅径迹探测器关键技术验证
报告人： 梁志均
项目负责人： João Guimarães da Costa
项目承担单位：中国科学院 高能物理研究所

## Slide 3: Overview of task2： vertex detector R & D
Can break down into sub-tasks:
  CMOS imaging sensor chip R & D
  Detector layout optimization, Ladder and vertex detector support structure R & D
  Detector assembly
  Data acquisition system R & D
CMOS imaging
sensor prototyping
Detector module (ladder)
Prototyping
Full size vertex detector Prototype
Beam test to
verify its spatial resolution
Notes: Full size vertex detector

## Slide 4: News
6 Taichu3 wafers are ready.
  IFAE sent to IHEP，custom clearance now, will 13% pay taxes
    COVID19 (10 days policy) for international package.
    Expect wafer arrival at IHEP in 1st week in July
  3 wafers (standard process) + 3 wafers (modified process)
    Dice one wafer of standard process
      Whether we try dicing two wafers ?
    Check top debug pad (200~300um wide)
    Modified process, better resolution ?
    Before irradiation, modified process is not better
    After irradiation, modified process will give better resolution
    Make sure modified process into the ladder making
Need a quick test of the Taichu3 ASIC
  Another 6 wafers waiting for production
  If there is issue, can modify the metal layer for next batch

## Slide 5: Timeline
  ASIC
    ASICs arrive to IHEP (June)
    Dicing and Thinning (one wafer dicing before wafer-level tests) (June)
  Single ASIC testing
    PCB under production ( by Jun 24th )
    Wire-bonding on test PCB … (June)
    Functional Tests … (June)
    Laser, beta source test (July)
    Irradiation test (July )
  Wafer level testing
    Wafer level test of ASICs (End of June)
    Dicing , (thinning ?)

## Slide 6: Timeline
Ladders Mechanics:
  Now: Carbon support samples available
  May: Pre-production carbon support ladders available
  August: Production of final carbon support ladders (if needed)
Ladders Assembly:
  May: Flex cable available
  May: Test of wire bonding and gluing on carbon support
  Tooling design and production (June)
  Dummy sensor (Glass) assembly on flex (JUNE)
  Jig tool , Wire bonding tests on flex (July)
  Assembly of ladders with chips (August )

## Slide 7: DAQ and multi-ASIC testing
Item | Time
TAICHU test board v1.1 | 6.9 - 6.23 (done)
TAICHU standalone test | 6.24 - ？
Bonding and test with flex4 v1.1 | 6.30 – 7.23
Interposer board production | 6.13 - 7.11
Power board (light interposer) production | 6.13 – 6.30 (done)
Flex2 v1.3 production | 6.13 – 7.4
Flex2 v1.3+interposer+fpga test (first prototype) | 7.23 – 8.23
Optimize and batch production | 8.23-？
Final system test | 
DAQ status report today

## Slide 8: Time line
Barrel Prototype:
  June: Installation mock-up (3D printed)
    Received large part of 3D models from Jinyu today, printing now
  July: Barrel support parts fabricated
  August: Assembly first Barrel with ladder support only
    Update from Xinghui today
  September: mounting readout ladders
  October: finished mounting the ladders, and readout tests
  Earlier November: Finish assembly of prototype
  November: Cosmic ray testing or BEPC beam test
December: DESY test beam

## Slide 9: Minute of last meeting discussion
Dicing lines, try to have two dicing for first wafer ( w/wo top debug pad )
  One dicing with top metal for the first wafer
  Discuss the dicing for the second wafer after testing
Use final module to test Chip to –chip slow control communication
 changing firmware