## Slide 1
R&D and Verification of Key Technologies for a High Energy Circular Electron-Positron Collider
国家重点研发计划
Zhijun Liang for CEPC MOST2 vertex detector team

## Slide 2: Overview of task2： vertex detector R & D
Can break down into sub-tasks:
  CMOS imaging sensor chip R & D
  Detector layout optimization, Ladder and vertex detector support structure R & D
  Detector assembly
  Data acquisition system R & D
CMOS imaging
sensor prototyping
Detector module (ladder)
Prototyping
Full size vertex detector Prototype
Beam test to
verify its spatial resolution
Notes: Full size vertex detector

## Slide 3: Pixel Analog design
CEPC time stamping precision requirement:
  25-100ns, better to time stamping each collision at Z pole
Taichu-1 pixel analog design:
  50ns~150ns (based one standard CMOS MAPS tech.)
  Consider to use depleted CMOS MAPS

## Slide 4: News about Taichupix3 production
6 Taichu3 wafers are ready.
    wafer arrival at IHEP in 5th July
  3 wafers (standard process) + 3 wafers (modified process)
    After irradiation, modified process will give better resolution
    Will modified process sensors into the detector assembly
Plan to send 2 wafers for thinning (100um) and dicing
  Test single chip performance
Need a quick test of the Taichu3 ASIC
  Another 6 wafers waiting for production
  If there is issue, can modify the metal layer for next batch

## Slide 5: TaichuPix2 laser testing update
Can reach ~5.5μm resolution in laser test
  In laser power 70%, cluster size ~2.5
  Similar to beta source test cluster size

## Slide 6
Completed preliminary version of detector module (ladder) design
  Detector module (ladder)= 10 sensors + support structure+ flexible PCB+ control board
  Sensors will be glued and wire bonded to the flexible PCB
  Flexible PCB will be supported by carbon fiber support structure
  Signal, clock, control , power, ground will be handled by control board through flexible PCB
3D model of the ladder
Detector module (ladder) R & D
Flexible PCB prototype
Profile of flexible PCB
Schematic of ladder electronics

## Slide 7: Detector module(ladder) assembly
Use gantry to do module assembly
Progress in assembly procedure and tooling design

## Slide 8: Detector module(ladder) assembly
Progress in assembling dummy sensor
Dummy sensor (glass) on flexible PCB
Setting up wire bonding station
For full-size detector module( ladder)

## Slide 9: Support structure of the ladder
Production of ladder support with carbon fiber is in good progress
  Half of the ladder support has been produced.
Ladder support
structure 3D model
Ladder support production

## Slide 10: Vertex detector prototype assembly procedure
Ladder installation procedure designed
Mockup with 3D printing in production
Tooling for installation

## Slide 11: DAQ Architecture development
DAQ Architecture and data structure are defined
DAQ Architecture
data structure

## Slide 12: Plan for test beam
Expect to perform beam test in DESY(3 - 7GeV electron beams)
  IHEP test beam facility as backup plan (a few hundreds MeV electrons )
Enclosure for detector with air cooling is developed for beam test
  Beam is shooting at one sectors of vertex detectors
inlet
outlet
Beam
Beam
Beam
DESY test beam

## Slide 13: Timeline
  ASIC
    ASICs arrive to IHEP (June)
    Dicing and Thinning (one wafer dicing before wafer-level tests) (June)
  Single ASIC testing
    PCB under production ( by Jun 24th )
    Wire-bonding on test PCB … (June)
    Functional Tests … (June)
    Laser, beta source test (July)
    Irradiation test (July )
  Wafer level testing
    Wafer level test of ASICs (End of June)
    Dicing , (thinning ?)

## Slide 14: Timeline
Ladders Mechanics:
  Now: Carbon support samples available
  May: Pre-production carbon support ladders available
  August: Production of final carbon support ladders (if needed)
Ladders Assembly:
  May: Flex cable available
  May: Test of wire bonding and gluing on carbon support
  Tooling design and production (June)
  Dummy sensor (Glass) assembly on flex (JUNE)
  Jig tool , Wire bonding tests on flex (July)
  Assembly of ladders with chips (August )

## Slide 15: DAQ and multi-ASIC testing
Item | Time
TAICHU test board v1.1 | 6.9 - 6.23 (done)
TAICHU standalone test | 6.24 - ？
Bonding and test with flex4 v1.1 | 6.30 – 7.23
Interposer board production | 6.13 - 7.11
Power board (light interposer) production | 6.13 – 6.30 (done)
Flex2 v1.3 production | 6.13 – 7.4
Flex2 v1.3+interposer+fpga test (first prototype) | 7.23 – 8.23
Optimize and batch production | 8.23-？
Final system test | 
DAQ status report today

## Slide 16: Schedule
  June: Installation mock-up
    Received large part of 3D models from Jinyu today, printing now
  July: Barrel support parts fabricated
  August: Assembly first Barrel with ladder support only
  September: mounting readout ladders
  October: finished mounting the ladders, and readout tests
  Earlier November: Finish assembly of prototype
  November: Cosmic ray testing or BEPC beam test
December 12-22: DESY test beam (test beam time slot reserved for two weeks)

## Slide 17: Backup
df

## Slide 18: Timeline
  ASIC
    ASICs arrive to IHEP (June)
    Dicing and Thinning (one wafer dicing before wafer-level tests) (June)
  Single ASIC testing
    PCB under production ( by Jun 24th )
    Wire-bonding on test PCB … (June)
    Functional Tests … (June)
    Laser, beta source test (July)
    Irradiation test (July )
  Wafer level testing
    Wafer level test of ASICs (End of June)
    Dicing , (thinning ?)

## Slide 19: Timeline
Ladders Mechanics:
  Now: Carbon support samples available
  May: Pre-production carbon support ladders available
  August: Production of final carbon support ladders (if needed)
Ladders Assembly:
  May: Flex cable available
  May: Test of wire bonding and gluing on carbon support
  Tooling design and production (June)
  Dummy sensor (Glass) assembly on flex (JUNE)
  Jig tool , Wire bonding tests on flex (July)
  Assembly of ladders with chips (August )

## Slide 20: DAQ and multi-ASIC testing
Item | Time
TAICHU test board v1.1 | 6.9 - 6.23 (done)
TAICHU standalone test | 6.24 - ？
Bonding and test with flex4 v1.1 | 6.30 – 7.23
Interposer board production | 6.13 - 7.11
Power board (light interposer) production | 6.13 – 6.30 (done)
Flex2 v1.3 production | 6.13 – 7.4
Flex2 v1.3+interposer+fpga test (first prototype) | 7.23 – 8.23
Optimize and batch production | 8.23-？
Final system test | 
DAQ status report today

## Slide 21: Time line
Barrel Prototype:
  June: Installation mock-up (3D printed)
    Received large part of 3D models from Jinyu today, printing now
  July: Barrel support parts fabricated
  August: Assembly first Barrel with ladder support only
    Update from Xinghui today
  September: mounting readout ladders
  October: finished mounting the ladders, and readout tests
  Earlier November: Finish assembly of prototype
  November: Cosmic ray testing or BEPC beam test
December: DESY test beam