## Slide 1
R&D and Verification of Key Technologies for a High Energy Circular Electron-Positron Collider
国家重点研发计划
Zhijun Liang for CEPC MOST2 vertex detector team

## Slide 2: Overview of task2： vertex detector R & D
Can break down into sub-tasks:
  CMOS imaging sensor chip R & D
  Detector layout optimization, Ladder and vertex detector support structure R & D
  Detector assembly
  Data acquisition system R & D
CMOS imaging
sensor prototyping
Detector module (ladder)
Prototyping
Full size vertex detector Prototype
Beam test to
verify its spatial resolution
Notes: Full size vertex detector

## Slide 3: Pixel Analog design
CEPC time stamping precision requirement:
  25-100ns, better to time stamping each collision at Z pole
Taichu-1 pixel analog design:
  50ns~150ns (based one standard CMOS MAPS tech.)
  Consider to use depleted CMOS MAPS

## Slide 4: News about Taichupix3 production
6 Taichu3 wafers are ready.
    wafer arrival at IHEP in 5th July
  3 wafers (standard process) + 3 wafers (modified process)
    After irradiation, modified process will give better resolution
    Will modified process sensors into the detector assembly
Send 1 wafers for thinning (150um) and dicing
  Test single chip performance
  Send 5 chips with PCB boards to company for wired bonding
    5 board bonded.
  Wire bonding one PCB board at IHEP
  Try to wire bonding one chip on flex at IHEP next week
Send 3 wafers to NCAP for wafer testing , thinning and dicing

## Slide 5: Taichupix3 testing
Single chip test board testing on-going
Wafer level testing in NCAP (on-going )
  Remote connection from IHEP to NCAP
  Remote commissioning of testing program
Wafer level test
Probe card

## Slide 6: Detector module(ladder) assembly
Progress in assembly in ladder
Dummy sensor (glass) on flexible PCB
Setting up wire bonding station
For full-size detector module( ladder)

## Slide 7: Support structure of the ladder
Production of ladder support with carbon fiber is in good progress
  Half of the ladder support has been produced.
  The yield of first batch of production is a bit low (~30%)
  New batch of production has high yield
Ladder support
structure 3D model
Ladder support production

## Slide 8: Vertex detector prototype assembly procedure
Ladder installation procedure designed
Mockup with 3D printing production done
Talks will be scheduled next week
Mockup with 3D printing

## Slide 9: DAQ Architecture development
DAQ Architecture and data structure are defined
Discussion of DAQ data structure last week
DAQ Architecture
data structure

## Slide 10: Plan for test beam
Expect to perform beam test in DESY(3 - 7GeV electron beams)
  IHEP test beam facility as backup plan (a few hundreds MeV electrons )
Enclosure for detector with air cooling is developed for beam test
  Beam is shooting at one sectors of vertex detectors
List of people
  Request for Invitation letter
List of equipment
inlet
outlet
Beam
Beam
Beam
DESY test beam

## Slide 11: Plan for test beam
Person power, expertise
  Ming Qi (NJU, overall)
  Zhijun Liang (IHEP, overall)
  Tianya Wu(IHEP, ASIC)
  Xiaomin Wei(NWPU, ASIC )
  Jia Zhou (DAQ)
  Ziyue Yan (firmware)
  Needs more DAQ software, firmware and offline expertise

## Slide 12
Instrumentations
  1. vertex detector prototype
  2. FPGA boards (15 boards including JTAG adapter)
  3. Test PC (2 personal computers. one for test one for backup)
    3 PC for DAQ, electronics , offline ?
    2T haredisk , 交换机switcher (24 channels, 8 channels …),
    temp monitoring slow control (PC needed)
    Power adaptors …, 4-5 DC power supply
  4. Several DC power supply (borrow it from DESY?)
  5. Several network cables and other cables.
  6. Borrow one oscilloscope for debug

## Slide 13: Timeline
  ASIC
    ASICs arrive to IHEP (June)
    Dicing and Thinning (one wafer dicing before wafer-level tests) (June)
  Single ASIC testing
    PCB under production ( Done)
    Wire-bonding on test PCB … (Done)
    Functional Tests … (on-going)
    Laser, beta source test (Aug)
    Irradiation test (Oct )
  Wafer level testing
    Wafer level test of ASICs (on-going)
    Dicing , (thinning ?)

## Slide 14: Timeline
Ladders Mechanics:
  Now: Carbon support samples available
  Pre-production carbon support ladders available
  September: Production of final carbon support ladders (if needed)
Ladders Assembly:
  May: Flex cable available
  May: Test of wire bonding and gluing on carbon support
  Tooling design and production (June)
  Dummy sensor (Glass) assembly on flex (JUNE)
  Jig tool , Wire bonding tests on flex (done)
  Assembly of ladders with chips (August )

## Slide 15: DAQ and multi-ASIC testing
Item | Time
TAICHU test board v1.1 | 6.9 - 6.23 (done)
TAICHU standalone test | 6.24 - ？
Bonding and test with flex4 v1.1 | 6.30 – 7.23
Interposer board production | 6.13 - 7.11
Power board (light interposer) production | 6.13 – 6.30 (done)
Flex2 v1.3 production | 6.13 – 7.4
Flex2 v1.3+interposer+fpga test (first prototype) | 7.23 – 8.23
Optimize and batch production | 8.23-？
Final system test | 

## Slide 16: Schedule
  August: Assembly first Barrel with ladder support only
  September: mounting readout ladders
  October: finished mounting the ladders, and readout tests
  Earlier November: Finish assembly of prototype
  November: Cosmic ray testing or BEPC beam test
December 12-22: DESY test beam (test beam time slot reserved for two weeks)

## Slide 17: Backup
df

## Slide 18: Timeline
  ASIC
    ASICs arrive to IHEP (June)
    Dicing and Thinning (one wafer dicing before wafer-level tests) (June)
  Single ASIC testing
    PCB under production ( by Jun 24th )
    Wire-bonding on test PCB … (June)
    Functional Tests … (June)
    Laser, beta source test (July)
    Irradiation test (July )
  Wafer level testing
    Wafer level test of ASICs (End of June)
    Dicing , (thinning ?)

## Slide 19: Timeline
Ladders Mechanics:
  Now: Carbon support samples available
  May: Pre-production carbon support ladders available
  August: Production of final carbon support ladders (if needed)
Ladders Assembly:
  May: Flex cable available
  May: Test of wire bonding and gluing on carbon support
  Tooling design and production (June)
  Dummy sensor (Glass) assembly on flex (JUNE)
  Jig tool , Wire bonding tests on flex (July)
  Assembly of ladders with chips (August )

## Slide 20: DAQ and multi-ASIC testing
Item | Time
TAICHU test board v1.1 | 6.9 - 6.23 (done)
TAICHU standalone test | 6.24 - ？
Bonding and test with flex4 v1.1 | 6.30 – 7.23
Interposer board production | 6.13 - 7.11
Power board (light interposer) production | 6.13 – 6.30 (done)
Flex2 v1.3 production | 6.13 – 7.4
Flex2 v1.3+interposer+fpga test (first prototype) | 7.23 – 8.23
Optimize and batch production | 8.23-？
Final system test | 
DAQ status report today

## Slide 21: Time line
Barrel Prototype:
  June: Installation mock-up (3D printed)
    Received large part of 3D models from Jinyu today, printing now
  July: Barrel support parts fabricated
  August: Assembly first Barrel with ladder support only
    Update from Xinghui today
  September: mounting readout ladders
  October: finished mounting the ladders, and readout tests
  Earlier November: Finish assembly of prototype
  November: Cosmic ray testing or BEPC beam test
December: DESY test beam