## Slide 1
R&D and Verification of Key Technologies for a High Energy Circular Electron-Positron Collider
国家重点研发计划
Zhijun Liang for CEPC MOST2 vertex detector team

## Slide 2: Overview of task2： vertex detector R & D
Can break down into sub-tasks:
  CMOS imaging sensor chip R & D
  Detector layout optimization, Ladder and vertex detector support structure R & D
  Detector assembly
  Data acquisition system R & D
CMOS imaging
sensor prototyping
Detector module (ladder)
Prototyping
Full size vertex detector Prototype
Beam test to
verify its spatial resolution
Notes: Full size vertex detector

## Slide 3: News about Taichupix3 production
6 Taichu3 wafers are ready.
    Wafer arrival at IHEP in 5th July 2022
  3 wafers (standard process) + 3 wafers (modified process)
    After irradiation, modified process will give better resolution
    Will modified process sensors into the detector assembly
Send 4 wafers to NCAP for wafer testing , thinning and dicing
Send 1 wafers for thinning (150um) and dicing
  Test single chip performance
  1st round: Send 5 chips for wired bonding
    2 boards working
  2nd round (this week): Send 5 more chip, 2 working
    3 chips with normal dicing (top and bottom pads available)
    2 chips dicing without top pads
      One chip working  IR drop is not a problem ?
    IR drop tests in next step

## Slide 4: Preliminary TaichuPix-3 test
Single chip test system built
Taichipix3 can reach ~100 e- lower threshold than Taichu2
  Improvement of DAC design in TC3 verified
Taichu2 mean threshold | Taichu3 mean threshold
267 e- | ~169 e-
TaichuPix2
TaichuPix3

## Slide 5: Taichupix3 wafer-level testing
Single chip test board testing on-going
Wafer level testing in NCAP (on-going )
  Remote connection from IHEP to NCAP
  Remote commissioning of testing program
  probe cards repaired, updating test procedure
  More testing results this week ? Yield ?
Wafer level test
Probe card

## Slide 6: TaichuPix3 tests
Functionality of the full signal chain proved with laser tests
Threshold scan in Beta source tests
Irradiation tests
  Oct, two days in BSRF
  X ray machine will repair in September.
laser tests
Beta source tests
Beta source tests

## Slide 7: Flex and interface board
Interface board was planned to have soft+hard PCB design
  Interface board is to connected the flex and FPGA board
Due to low yield, switched to hard PCB design, no flexible components
Expect no much impact to support structure
Time scale for 2nd version of interface board , ~2 weeks
Interface board
Interface board+FPGA +flex

## Slide 8: Flex and interface board
2nd version of the flex submitted ? Will return in 2-3 weeks ?
  September 18th for two-layer design, one more week for 4th layer
  Double metal layer and 4th layer metal design
  Enlarge opening of the pad on flex (100um * 400um)
  Add bus for ground for wire bonding
  Modified the position of the hole
  Change the position of the connector (on the other side of the sensor)
Testing with single chip 1st version flex with wire bonding
  Large leakage current ?

## Slide 9: Support structure of the ladder
Production of ladder support with carbon fiber is in good progress
  Half of the ladder support has been produced. （IHEP designed)
  The yield of first batch of production is a bit low (~30%)
  New batch of production has high yield, when ?
  Expected 120 good ladder support in this production
Ladder support
structure 3D model
Ladder support production

## Slide 10: Detector module(ladder) assembly
Progress in assembly in ladder
Dummy
  2 flex with 10 glass dummy ASIC assembly
  Automatic glue dispensing using gantry
Real chip
Wire bonded one Taichu3 on flexible PCB
Jun and Ziyue are testing it with interface board
Setting up wire bonding station
For full-size detector module( ladder)

## Slide 11: Ladder assembly
Ladder (double side)= 20 ASIC chips + two flexible PCB + carbon fiber support
Ladder assembly procedure verified with dummy ASIC (glass)

## Slide 12: Vertex detector prototype assembly procedure
Ladder installation procedure designed
Mockup with 3D printing production done
Assembly with 3D mockup model
Production with aluminum machining started
  Expected finished at middle of September

## Slide 13: DAQ Architecture development
Try to config single chip test board and data handling with DAQ software (next step)
Purchase 3 DAQ PC for data taking (next step)
Parallel processing for each FPGA board
Hit maps on-line monitoring
DAQ
data structure

## Slide 14: offline reconstruction
Dedicated discussion with Linhui Wu, Gang Li, Shuqi, Hao Zeng
Alignment strategy will be presented today

## Slide 15: Plan for test beam
Expect to perform beam test in DESY(3 - 7GeV electron beams)
  IHEP test beam facility as backup plan (1-2 GeV electrons )
Enclosure for detector with air cooling is developed for beam test
  Beam is shooting at one sectors of vertex detectors
List of people
  Request for Invitation letter
List of equipment
Beam
Beam
DESY test beam
Electron beam

## Slide 16: Plan for test beam
Person power, expertise
  Ming Qi (NJU, overall)
  Joao (IHEP, overall)
  Zhijun Liang (IHEP, overall)
  Tianya Wu(IHEP, ASIC)
  Xiaomin Wei(NWPU, ASIC )
  Jia Zhou (IHEP ,DAQ)
  Ziyue Yan (IHEP ,firmware)
  Xinhui Huang (IHEP, mechanism)
  Shuqi Li (IHEP, offline)
  Requesting Invitation letters (almost ready)
  Application Passports

## Slide 17: Equipment for Test beam
Instrumentations
  1. vertex detector prototype
  2. FPGA boards (15 boards including JTAG adapter)
  3. Test PC (2 personal computers. one for test one for backup)
    3 PC for DAQ, electronics , offline ?
    2T harddisk , 交换机switcher (24 channels, 8 channels …),
    temp monitoring slow control (PC needed)
    Power adaptors …, 4-5 DC power supply ?
  4. Several DC power supply (borrow it from DESY?)
  5. Several network cables and other cables.
  6. Borrow one oscilloscope for debug

## Slide 18: Timeline
  ASIC
    ASICs arrive to IHEP (June)
    Dicing and Thinning (one wafer dicing before wafer-level tests) (June)
  Single ASIC testing
    PCB under production ( Done)
    Wire-bonding on test PCB … (Done)
    Laser tests, Functional Tests … (on-going)
    Beta source test (on-going)
    Irradiation test (Oct, two days )
  Wafer level testing
    Wafer level test of ASICs (on-going)
    Dicing , (thinning ?)

## Slide 19: Timeline
Ladders Mechanics:
  Now: Carbon support samples available
  Pre-production carbon support ladders available
  September: Production of final carbon support ladders (if needed)
Ladders Assembly:
  May: Flex cable available
  May: Test of wire bonding and gluing on carbon support
  Tooling design and production (June)
  Dummy sensor (Glass) assembly on flex (JUNE)
  Jig tool , Wire bonding tests on flex (done)
  Assembly of ladders with chips (Sep )

## Slide 20: Time line
Barrel Prototype:
  June: Installation mock-up (3D printed)
    Received large part of 3D models from Jinyu today, printing now
  July: Barrel support parts fabricated
  August: Assembly first Barrel with ladder support only
  September: mounting readout ladders
  October: finished mounting the ladders, and readout tests
  Earlier November: Finish assembly of prototype
  November: Cosmic ray testing or BEPC beam test
December: DESY test beam

## Slide 21: Global Schedule
  August: Assembly first Barrel with ladder support only
  September: mounting readout ladders
  October: finished mounting the ladders, and readout tests
  Earlier November: Finish assembly of prototype
  November: Cosmic ray testing or BEPC beam test
December 12-22: DESY test beam (test beam time slot reserved for two weeks)

## Slide 23: Pixel Analog design
CEPC time stamping precision requirement:
  25-100ns, better to time stamping each collision at Z pole
Taichu-1 pixel analog design:
  50ns~150ns (based one standard CMOS MAPS tech.)
  Consider to use depleted CMOS MAPS

## Slide 24: News about Taichupix3 testing
Single chip test news
  Charge injection done
  S curve scan in next step
    Need to mask off noise pixel
  Laser tests
  Source tests (next step)
    Threshold tuning
  IR drop tests? (next step)
    Top pad need ?  dicing
  Irradiation tests
    BSRF beam time in Oct 2022
    X ray machine ?
  First Laser tests