## Slide 1
R&D and Verification of Key Technologies for a High Energy Circular Electron-Positron Collider
国家重点研发计划
Zhijun Liang for CEPC MOST2 vertex detector team

## Slide 2: News about Taichupix3 production
6 Taichu3 wafers are ready.
    Wafer arrival at IHEP in 5th July 2022
Send 1 wafers for thinning (150um) and dicing (done!)
    IR drop is not a big problem ?
    Low resistance  after power on, resistance become normal ?
Send 5 wafers to NCAP for wafer testing , thinning and dicing
  Another wafer just diced this week
  Need to test two chip with new dicing scheme

## Slide 3: Ghost hits in laser testing
Observe ghost hits in 40MHz clock during laser testing
Disappear using 20MHz clock

## Slide 4: Electron beam test in BEPC BSRF in Nov
Electron beam test in BSRF from Nov (Nov 8th， 4W1A station )
  Test electron beam going through multiple test boards (Nov 8th. ~ Nov 15th )
  Test of ladder (Nov 15th ~27st )
  Test of prototype (Nov 27th – Dec 5rd )
The current version of single chip board can be used ?
1st version of
single chip board
2nd version of single chip board

## Slide 5: Flex and interface board
2nd version of the flex received. (2 metal layer version)
  5 flex available
  Single chip testing on flex (on-going)
Single chip testing on flex
5 flex received
Wirebonding

## Slide 6: Vertex detector prototype assembly procedure
Prototype support ready
Mounting a dummy ladder with glass (done)
Mounting dummy chip ladder with wire bond (Early Nov)
Mounting real ladders ( End of Nov)
Prototype support with aluminum machining

## Slide 7: DAQ Architecture development
Correct Chip Configuration and Laser tests data taking with DAQ software (done)
  Matlab and DAQ software are getting the same results
Purchase DAQ PC for data taking (done)
Long-term tests with laser (done)
Threshold scan
Parallel processing multi-chip (ongoing)
  Key task before Nov test beam in BSRF
DAQ

## Slide 8: offline reconstruction
Alignment strategy ready
Clustering has the first version
Offline data handling are still needed, to be test in Nov BSRF beam test

## Slide 9: Plan for test beam
beam test in DESY in Dec 12nd (3 - 7GeV electron beams)
Enclosure for detector with air cooling is developed for beam test
  Beam is shooting at one sectors of vertex detectors
News about people :
  Tianya, Xinhui, Shuqi, Zhou jia got Visa
List of equipment : will be listed after BSRF test beam
Beam
DESY test beam
Electron beam

## Slide 10: backup

## Slide 11: Plan for test beam
Person power, expertise
  Ming Qi (NJU, overall)
  Joao (IHEP, overall)
  Zhijun Liang (IHEP, overall)
  Tianya Wu(IHEP, ASIC)
  Xiaomin Wei(NWPU, ASIC )
  Jia Zhou (IHEP ,DAQ)
  Ziyue Yan (IHEP ,firmware)
  Xinhui Huang (IHEP, mechanism)
  Shuqi Li (IHEP, offline)
  Requesting Invitation letters (almost ready)
  Application Passports

## Slide 12: Detector module(ladder) assembly
Progress in assembly in ladder
Dummy
  2 flex with 10 glass dummy ASIC assembly
  Automatic glue dispensing using gantry
Real chip
Wire bonded one Taichu3 on flexible PCB
Jun and Ziyue are testing it with interface board
Setting up wire bonding station
For full-size detector module( ladder)
New pickup tools

## Slide 13: Ladder assembly
Ladder (double side)= 20 ASIC chips + two flexible PCB + carbon fiber support
Ladder assembly procedure verified with dummy ASIC (glass)

## Slide 14: Plan for test beam

## Slide 15: Equipment for Test beam
Instrumentations
  1. vertex detector prototype
  2. FPGA boards (15 boards including JTAG adapter)
  3. Test PC (2 personal computers. one for test one for backup)
    3 PC for DAQ, electronics , offline ?
    2T harddisk , 交换机switcher (24 channels, 8 channels …),
    temp monitoring slow control (PC needed)
    Power adaptors …, 4-5 DC power supply ?
  4. Several DC power supply (borrow it from DESY?): 12 channels DC power supply
  5. Several network cables and other cables.
  6. Borrow one oscilloscope for debug

## Slide 16: Timeline
  ASIC
    ASICs arrive to IHEP (June)
    Dicing and Thinning (one wafer dicing before wafer-level tests) (June)
  Single ASIC testing
    PCB under production ( Done)
    Wire-bonding on test PCB … (Done)
    Laser tests, Functional Tests … (on-going)
    Beta source test (on-going)
    Irradiation test (done)
  Wafer level testing
    Wafer level test of ASICs (on-going)
    Dicing , (on going )

## Slide 17: Timeline
Ladders Mechanics:
  Now: Carbon support samples available
  Pre-production carbon support ladders available
  September: Production of final carbon support ladders (done )
Ladders Assembly:
  May: Flex cable available
  May: Test of wire bonding and gluing on carbon support
  Tooling design and production (June)
  Dummy sensor (Glass) assembly on flex (JUNE)
  Jig tool , Wire bonding tests on flex (done)
  Assembly of ladders with dummy chips (done )
  Assembly of ladders with real chips (Nov, developing )

## Slide 18: Time line
Barrel Prototype:
  Oct: Assembly first Barrel with ladder support only (done)
  Oct: mounting dummy ladders (done)
  Nov: mounting real ladders
December 12nd -22nd : DESY test beam