## Slide 1: CEPC Accelerator Engineering Design Report (EDR) Plan (preliminary) (2023-2025)
J. Gao
CEPC Day (Accelerator), Nov. 25, 2022

## Slide 2
Concerning CEPC accelerator EDR plan, during the IAC meeting, at the Accelerator Parallel session on Nov. 2, 2022, Barry, Steinar and Marica aksed us to send a feedback EDR plan for IAC.
*EDR was also requested in previous IAC and IARC

## Slide 3
CEPC Accelerator EDR Phase Working Plan (preliminary) 2023 – 2025 （draft）
General CEPC EDR goals
According to the general CEPC plan, CEPC Conceptual Design Report (CDR) was completed in Nov. 2018, and the CEPC accelerator Technical Design Report (TDR) will be completed in 2023 after international review(s) (including a CEPC accelerator cost review). Thereafter, CEPC accelerator will enter into the Engineering Design Report (EDR) phase (2023-2025), which is also the preparation phase with the aim for CEPC to be presented to and selected by Chinese government for the construction start during the ”15th five year plan (2026-2030)” (for example, around 2027) and completion around 2035 (the end of the 16th five year plan).

## Slide 4
CEPC Accelerator EDR Phase Working Plan (preliminary) 2023 – 2025 （draft）
CEPC accelerator complex as the centroid of the CEPC, carries ~90% of the project cost, with regard to the country's selection decision of the 15th 5-year plan, in EDR phase, the general goals for CEPC accelerator complex are: (A) Guarantee the physics goals with required energies (Higgs, W, and Z-pole) and corresponding luminosities with 30MW cap on the synchrotron radiation power/beam as a baseline, and 50MW and ttbar energy as upgrade possibilities. (B) Demonstrate the complete and coherent feasibility design. (C) Demonstrate the feasibility of fully verified technologies through R&D with engineering design of CEPC accelerator systems and components towards fabrication in an industrial way (with both domestic and international suppliers). (D) Well prepared for the realization of the CEPC facility with good understanding of the cost, and industrial involvement.

## Slide 5
CEPC Accelerator EDR Phase Working Plan (preliminary) 2023 – 2025 （draft）
(E) Analysis and preparation for the human resources for the completion of CEPC construction. (F) Continue to strengthen the international collaborations and welcome international participation. (G) CEPC site selection study converges to (at least) two candidate sites in EDR phase with compatibility with the TDR (tunnel, infrastructure and environment), and recommend them to the government who will make the final decision on the site selection. (H) EDR documentation preparations (both Electronic Documentation for construction and reports to government for application). (I) Ready for final selection of the 15th 5-year plan.

## Slide 6
Breakdown of CEPC Accelerator EDR working plan and goals (2023-2025) According to the CEPC and CEPC Accelerator EDR general goals described above, CEPC accelerator key subsystems working plans and goals (2023, 2024, 2025), each year to do list (items) and deliverables, milestones, etc. are briefly described as follows:
1)CEPC Collider ring (Yiwei Wang); 2)Booster ring (D. Wang);3)Linac (+damping ring) (C. Meng, J.R. Zhang, D. Wang); 4)MDI (S. Bai); 5)Connection transport lines and timing (X.H. Cui); 6)Collider magnets (M. Yang); 7)Booster magnets (W. Kang); 8)Magnet power sources (B. Chen); 9)Electrostatic-magnet separator (B. Chen); 10)SC quadrupoles (Y.S. Zhu); 11)SRF system for collider ring (J. Y. Zhai, P. Sha); 12)SRF system for booster ring (J.Y. Zhai, P. Sha); 13) Cryogenic system (R. Ge and Mei Li); 14)RF power sources and power distribution (collider, booster and linac) (Z.S. Zhou); 15)Instrumentation and feedbacks (Y.F. Sui and Y.H. Yue); 16)Mechanical system (H.J. Wang and Minxian Li); 17)Vacuum system (Y.S. Ma);

## Slide 7
18) Control system (G. Li); 19)Conventional facilities (J.S. Huang); 20)Environment, health and safety issues (Guang Yi Tang and Zhongjian Ma ) ; 21)Machine protection beam dump (Zhongjian Ma and X.H.Cui); CEPC high energy gamma ray beamlines (Y.W. Wang and Y.S. Huang); 23)Alignment and installation (X. L. Wang);
24)Beam driven plasma injector for CEPC (D.Z. Li); 25)CEPC polarization design (Z. Duan); 26)SppC design and compatibility with CEPC (Jingyu Tang and Y.W. Wang); 27)SppC high field magnet (Q.J. Xu); 28)CEPC electronic documentation system (K. Huang and S. Jin); 29)CEPC site selection and civil engineering design in Qinhuangdao and Chuangchun (Y. Xiao); 30)CEPC site selection and civil engineering design in Changsha (Yangjiang Pan and Zhiji Li); 31)CEPC site selection and civil engineering design in Huzhou (K. Huang); 32)CEPC domestic and international industry preparations (S. Jin); 33) Injector linac and damping ring R&D (J.R. Zhang) (combined in 3); 34)CEPC Injection/extraction system (Jinhui Chen); 35)Collective effects and impedance (Yudong Liu, Na wang)

## Slide 8
A 27 pages CEPC Accelerator EDR Plan (preliminary) Draft has been completed for discussion

## Slide 9
Discusions on CEPC Accelerator Engineering Design Report (EDR) Plan (preliminary) will undergo top-down, bottom-up, and top-down...processes, to reach the following goals：
1) Have a clearly defined target goals: Ready for final selection of the 15th 5-year plan, and ready for the construction start during the ”15th five year plan (2026-2030)” (for example, around 2027) and completion around 2035 (the end of the 16th five year plan).
2) Clarify a complete to do list and deliverables consistent with the CEPC general plan.
3) Identify the relevant urgent and necessary EDR fesibility R&D items and industrial preparation activities with required EDR funds applications and resource allocations to quarantee the smooth development of CEPC in EDR phase.

## Slide 10
Summary of some collected ERD phase related hardware study issues:
3) Linac+damping ring (Jingru Zhang): C-band accelerating structure (45MV/m); DR normal conducting 5 cell cavity, both with high power tests.
4) MDI (Sha Bai): Processing and manufacturing of IR beam pipes, including beryllium pipe and tungsten alloy beam pipe. The welding between beryllium and other materials like aluminum, the window to LumiCal, and so on.
6) Collider magnets (Mei Yang): A short dual aperture dipole magnet is made of carbon steel material to study its magnetic properties. Develop a new prototype of double aperture quadrupole magnet. Develop a sextupole magnet prototype.
7) Booster magnets (Wen Kang): Complete the performance test of the full scale prototype dipole magnets and verify the technologies that were adopted in the R & D of the TDR stage.
8) Magnet power supplies (Bin Chen): Develop the prototype of the power supply, embed the digital control board.

## Slide 11
9)Electrostatic-magnet separator (B. Chen): The whole Electrostatic-magnet separator is tested at high vacuum and high voltage, and overall performance reaches the target.
10)SC quadrupoles (Y.S. Zhu): Developing a 0.5m double aperture superconducting quadrupole model magnet (LTS NbTi, coil inner diameter 40mm, field gradient 142T/m).
Complete the pre-research on superconducting quadrupole coil using high-temperature superconductor (HTS Bi-2212 or YBCO).Finish the fabrication and cryogenic test of a short model superconducting quadrupole coil using high temperature superconductor for Q1a.
11) SRF system for collider ring (J. Y. Zhai, P. Sha): Assembly and testing of the prototype full-scale 650 MHz cryomodule for the Higgs mode.
12) SRF system for booster ring (J.Y. Zhai, P. Sha): Assembly and testing of the prototype high current high Q 1.3 GHz. Reach the TDR specifications of the booster ring cavity and cryomodule.
13) Cryogenic system (R. Ge and Mei Li): Large helium refrigerator (Industry), a 2K JT heat exchanger, and multiple cryogenic transfer lines

## Slide 12
14) RF power sources and power distribution (collider, booster and linac) (Z.S. Zhou): Accomplishment of High power test for MBK, Development of muti-stage collector , High power test of high efficiency klystron with muti-stage collector design.
15) Instrumentation and feedbacks (Y.F. Sui and Y.H. Yue): Find out the final solution of BI device batch manufacturing.
16) Mechanical system (H.J. Wang and Minxian Li): The development and test of the remote vacuum connector if possible. The structure design of all kinds of supports which needs to be finished at EDR stage. Finish all the development and technique studies if there has any.
17) Vacuum system (Y.S. Ma): Optimization the thickness of NEG coating distribution along the vacuum chamber. Optimization the resistance of NEG coating. Optimization the layout of vacuum system.
18) Control system (G. Li): Build a prototype platform to research and solve key technologies such as timing，MPS，Network and database, etc.
22) 22)CEPC high energy gamma ray beamlines (Y.S. Huang and Y.W. Wang )Complete the Validation tests of gamma cameras and gamma focusing lenses on inverse Compton gamma light sources.

## Slide 13
28)CEPC electronic documentation system (K. Huang and S. Jin):Complete the web and mobile APP development of DeepC system, and digitally empower CEPC-EDR report and document data management with DeepC.
34)CEPC Injection/extraction system (Jinhui Chen): Complete the trapezoidal-wave kicker system prototype R&D.
Further R&D work to be carried out in the EDR period
24)Beam driven plasma injector for CEPC (D.Z. Li): Experiments at SXFEL: HTR e- acceleration experiment and stable mode in hollow channel for e+ acceleration. Demonstrate the prototype of 5m plasma channel based on laser ionized noble gas. Finish the dedicated plasma acceleration TF based on BEPC-II linac.
25)CEPC polarization design (Z. Duan): Carry out preliminary experiments of resonant depolarization technique at BEPCII.
27)SppC high field magnet (Q.J. Xu): Fabrication and test of the 16-T model dipole magnet: complete the fabrication of the outer Nb3Sn coils and inner HTS coils, assembling of the magnet and the preliminary performance test. Engineering design of the 20-T model dipole magnet.

## Slide 14
Feedbacks (Nov. 16, 2022) from IAC chair, Prof. B. Foster on “CEPC Accelerator EDR Phase Working Plan (preliminary) 2023 – 2025 (draft):
-a few very initial comments. The design goal for the linac at 45 GV/m seems very ambitious - I would feel a lot
more comfortable if it were 40. It might not even be more expensive since there are sure to be a lot of cavity rejects if
they have to be rated at 45 GV/m. If in the end 45 GV can be reached, then planning for 40 will provide a useful set of spares!
For the collider magnets: I struggle to think what a “Preliminary Engineering Design Report” in 2023 might be. This will be
directly after the TDR - surely it is better to get the TDR design as final as possible and then go straight to a final engineering design a couple of years later.
Similarly for SC quads and the EM separator - what is down for 2023 surely ought to be part of the TDR - otherwise it is difficult to see how this can be evaluated.

## Slide 15
Feedbacks (Nov. 16, 2022) from IAC chair, Prof. B. Foster on “CEPC Accelerator EDR Phase Working Plan (preliminary) 2023 – 2025 (draft):
The activities for the vacuum system and the control system seem much too vague for an EDR - they need to be sharpened up considerably,
EHS - there should be an item here related to ground-water and how to avoid contamination, also sources and treatment for cooling water -
of course this is highly site dependent - I think the penalty of carrying more than one site along with us is that this sort of work will have
to be duplicated for each site. This is to some extent covered in point 29), but it is important to consider these aspects here too - so at least
a pointer towards 29) should be included.
Is the synchrotron-radiation option going to be in the TDR? We have heard very little about it so far but if things are being done about it in the EDR, it better have been properly reviewed in the TDR.

## Slide 16
Feedbacks (Nov. 16, 2022) from IAC chair, Prof. B. Foster on “CEPC Accelerator EDR Phase Working Plan (preliminary) 2023 – 2025 (draft):
Alignment - the 2023 work again seems to be more suitable for a TDR - I am unclear how the reviewers will react in the TDR review
if, as this implies, there are major unsolved in-principle problems such as error accumulation. Of course, life is what it is and if this
won’t be ready for the TDR, we will have to cope somehow.
The plasma injector activity is building towards a CDR, not an EDR - I assume this will again go into an Appendix. Similarly for
the SppC high-field magnet work - although not the compatibility work, item 26, which has to be in the EDR.

## Slide 17
Feedbacks (Nov. 16, 2022) from IAC chair, Prof. B. Foster on “CEPC Accelerator EDR Phase Working Plan (preliminary) 2023 – 2025 (draft):
Although clearly much less speculative, the description of the polarisation work is more appropriate for a TDR than an EDR.
Perhaps these topics should be placed at the end of the document under a title “Further R&D work to be carried out in the EDR period.”
Documentation - I assume this DeepC system will be detailed in the TDR - I don’t recall ever hearing anything about it before.
Thanks for this, which I think is a very useful initial start. Of course the above are only initial thoughts and others may
react differently - in any case as Marica says, we will have to discuss carefully.

## Slide 18
Summary
We have to work continously on CEPC Accelerator EDR Phase Working Plan (preliminary) 2023 – 2025 (draft) with several interations
A dedicated meeting or workshop on CEPC Accelerator EDR Phase Working Plan
should be held
A finely worked out CEPC Accelerator EDR Phase Working Plan will be prepsented
in the next IARC and IAC meetings

## Slide 19
Acknowledgements
Thanks go to all CEPC accelerator colleageus and collaboration CIPC companies,
CEPC SC, CEPC Direction Board, IAC and IARC for their guidance and suggestions.