## Slide 1: SRF system and beam operation of RAON in IBS
ASSCA 2025
2025. 03. 24
Office of High Energy Linac Development
Institute for Rare Isotope Science, IBS
Youngkwon Kim

## Slide 2
OUTLINE
01
Introduction
02
Mass production of SCL3 cryomdoule
03
Installation and commissioning

## Slide 3: Overview
Providing high intensity RI beams by ISOL and IF
ISOL: direct fission of 238U by 70 MeV proton
IF: 200 MeV/u 238U (intensity: 8.3 pμA)
Providing high quality neutron-rich beams
e.g., 132Sn with up to 250 MeV/u,
up to 109 particles per second
Providing More exotic RI beam
production by combination of ISOL and IF
Budget: KRW 1,432 billion (US$ 1.26 billion, 1$=1,135krw)
- accelerators and experimental apparatus : 460.2 billion won
- civil engineering & conventional facilities : 972 billion won (incl. site 357 billion won)
Period: 2011.12 ~ 2021.12 (1st phase, SCL3 + experimental system)
Goal: To build a heavy ion accelerator complex RAON,
for rare isotope science research in Korea.
* RAON - Rare isotope Accelerator complex for ON-line experiments
Construction of research and support facility to ensure the stable operation of the heavy-ion accelerator, experiment systems, and to establish a comfortable research environment
※ Accelerator and experiment buildings, support facility, administrative buildings, and guest house, etc.
Development, installation, and commissioning of the accelerator systems that provides high-energy (200MeV/u) and high-power (400kW) heavy-ion beam
System Installation Project
Facility Construction Project

## Slide 4: RAON layout
IF System
BIS
μSR
HPMMS/
CLS
SCL2
ISOL System
LAMPS
Cyclotron
SCL3
SCL1
ECR IS
KOBRA
NDPS
Control
Center
Utility
HRS
SCL1 is postponed. (cancelled?)
SCL3 was installed and is under operation.
SCL2 is in prototyping. (2nd phase)

## Slide 5: ISOL and IF
ISOL (Isotope Separator On-Line)
proton  thick target (ex. Uranium )  target spallation or fission (low energy)
RI Ions
Reacceleration
RI Beam
Cyclotron
Proton 70 MeV, 70 kW
IF (In-flight Fragmentation)
Heavy ion beam  thin target (ex. Carbon)  projectile fragmentation (high energy)
RI ion beam
Fast Beam
Experiment
Driver LINAC
Heavy ion
e.g. U : 200MeV/u, 400 kW
Ref.: D. Jeon, Initial Commissioning of the RAON Superconducting Linac and its Future Perspective, IFPC2023

## Slide 6: RIBs at RAON
ISOL  IF
  ISOL  SCL3  SCL2  IF
  ISOL  SCL3  KOBRA
Broad energy range, Variety, High intensity of RIBs will be available at RAON
 | KOBRA (low-E IF) | ISOL | IF (high E)
Driver | SCL3 | Cyclotron | SCL3  SCL2
Post accelerator | SCL3 or SCL3  SCL2 |  | 
Production mechanism | Direct reactions Multi Nucleon Transfer | p induced U fission | PF, U fission
Available RIB energy | < a tens of MeV/u | > A few of keV/u | < a hundreds of MeV/u

## Slide 7: Expected rare isotope from RAON
RAON will provide access to unexplored regions of nuclear chart
KoBRA
IF
ISOL
ISOL+IF

## Slide 8: Introduction on SCL
RF Parameters
 | Cavity | # of cav. per CM | # of CM | Cav. Op. T (K)
SCL3 | QWR | 1 | 22 | 4.5
 | HWR | 2 | 13+2 | 2.05
 |  | 4 | 19 | 2.05
SCL2 | SSR1 | 3 | 23 | 2.05
 | SSR2 | 6 | 23+2 | 2.05
 | QWR | HWR | SSR1 | SSR2
Optimum | 0.047 | 0.12 | 0.32 | 0.51
 | 81.25 | 162.5 | 325 | 325
 | 173.5 | 221.5 | 276.9 | 470.8
 | 469 | 295 | 233 | 290
 | 5.7 | 5.2 | 4.1 | 3.7
 | 10.4 | 9.0 | 6.9 | 7.7
 | 6.1 | 6.6 | 8.5 | 8.7
 | 1.06 | 1.46 | 2.35 | 4.1
 | QWR | HWR | SSR1 | SSR2
 | 0.047 | 0.12 | 0.32 | 0.51
 | 81.25 | 162.5 | 325 | 325
 | 173.5 | 221.5 | 276.9 | 470.8
 | 469 | 295 | 233 | 290
 | 5.7 | 5.2 | 4.1 | 3.7
 | 10.4 | 9.0 | 6.9 | 7.7
 | 6.1 | 6.6 | 8.5 | 8.7
 | 1.06 | 1.46 | 2.35 | 4.1

## Slide 9: Mass production of SCL3 cryomdoule
Contracts
 | SCL31 |  | SCL32 | 
 | Products | Quantity | Products | Quantity
Final deliverables | QWR cryomodule | 22 | HWR cryomodule A | 15
 |  |  | HWR cryomodule B | 19
Subcomponents to be fabricated | Superconducting cavities | 18 | Superconducting cavities | 104
 | Power couplers | 20 | Power couplers | 104
 | Tuners | 22 | Tuners | 104
 | Cryostat | 21 | Cryostat A | 14
 |  |  | Cryostat B | 18
Contract amount | $ 9,065,128 |  | $ 25,457,148 | 
Period | 2017. 12 ~ 2020. 07 |  | 2018. 05 ~ 2022. 01 | 
Domestic vendor: VitzroTech (cavity: RI as subcontractor)

## Slide 10: Schedule for mass production
 | 2017 | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  | 
QWR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HWR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Contract(‘17.12)
cavity fabrication (’18.03 ~ ‘20.06)
module & tuner fabrication (‘18.03~’19.03)
coupler fabrication (‘18.03 ~ ‘20.01)
vertical test (‘20.02 ~ ‘21. 07)
horizontal test (‘19.08 ~ ‘20. 09)
cavity fabrication (‘18.09~’21.06)
Contract(‘18.05)
module fabrication (‘18.12 ~ ‘20. 06)
tuner fabrication (‘19.01 ~ ‘20. 04)
coupler fabrication (‘19.03 ~ 21.04)
module assembly (‘19.07 ~ ‘20. 08)
module assembly (‘20.09 ~ ‘21.10)
horizontal test (‘20.10 ~ ‘21. 11)
vertical test (‘18.08 ~ ‘20.07)
Helium jacket issue based on the KGS (Korea Gas Safety)
Fabrication delay due to COVID-19 in subcontractor (RI, Germany)
Design change of beam sphere and beam port

## Slide 11: Vertical Test
Vertical test
Cryostat
4K Reservoir
Vacuum Line
2K Reservoir
Vacuum Chamber
Ion Pump
Top flange
ID=1,200 mm
Height=3,000 mm
2 stats for dressed cavity and 1 stat for bare & dressed cavity

## Slide 12
Top flange assembly
Variable coupler
Motor
Inner conductor
Outer conductor and bellows

## Slide 13: Performance Test
Ion pump
Cryogenic valve
Vacuum pumping lines
& vacuum gauges
Feedthroughs
Assembly area(clean room) for vertical test
Top flange in the vertical test pit
Vacuum pump
for cavity
GHe supply & return
VLP return
LN2 supply & return

## Slide 14
QWR VT results
Eacc: 6.1 MV/m, Q0=2.4e+8@4.2K, Number of cavity: 22 ea

## Slide 15
HWR VT results
Eacc: 6.6 MV/m, Q0=2.3e+9@2.05K, Number of cavity: 106 ea
VT yield ~75 %
Main cause of failure: field emission

## Slide 16: Horizontal Test
Test procedure
Installation in the bunker
Cavity frequency check & tuner operation test
Leak test and vacuum pumping for cavity
Leak test and Purging cryogenic pipes
Connecting cryogenic lines, signal cables, DC bias, RF transmission lines, etc
Cool-down
Thermal shield cool-down by LN2
Cavity cool-down through cool-down line
4K Test
Cable calibration
MP conditioning
Static and total thermal load measurement
Field emission conditioning with pulsed RF power, if necessary
2K Test
2 K pump-down: df/dp measurement (~3MV/m)
Qext measurement with VNA
Static and total thermal load measurement
LFD & tuner operation test
Alignment measurement
Tuner test at room temp.
(~0.2 Hz/pulse, ~30 kHz span)

## Slide 17: Horizontal Test
Horizontal test facility
Valve box for HT
SSPA
RF transmission line
Helium distribution lines
Horizontal test bunkers

## Slide 18: Horizontal Test
Test setup
Horizontal Test

## Slide 19: Horizontal Test
P&ID for cryomdules and cryogenics system in SRF TF
Horizontal Test
Thermal shield cooled by LN2
Thermal intercepts
- 4 K intercepts: loop thermosiphon connected with 4 K reservoir
- 40 K intercepts: copper braid wire connected with thermal shield
3 cryogenic valves: 1 for cool-down and 2 for JT expansion
Heat exchanger to precool the LHe before 2 K expansion
Vacuum pumping system to maintain 35 mbar
Liquefier (280 L/h) and dewar (3,000 L)
Recovery compressor and gas bag
Pump-down system(vacuum pumps): 1.5g/s each

## Slide 20: Horizontal Test
Thermal load measurement results
Dynamic thermal load of each cryomodule is the sum of the dynamic thermal load of cavities in the cryomdoules

## Slide 21: Horizontal Test
Static thermal load
Main reason: Large mass (~40 Kg) of tuner
Static thermal load that we had measured were 5.6 W and 8.3 W for HWR CMA and HWR CMB, respectively while the average static thermal load measured during the experiments were 8.0 W and 10.7 W, respectively.
Static thermal load change w.r.t. time during HT
Static thermal load of HT vs. tunnel
Wrong measurement
Heat load | QWR |  | HWR CMA |  |  | HWR CMB |  | 
 | 4.5 K | 40 K | 2.05 K | 4.5 K | 40 K | 2.05 K | 4.5 K | 40 K
Estimated (50% margin) | 7.5 | 83.3 | 4.5 | 4.5 | 117.9 | 6.8 | 7.5 | 181.5
Measured in tunnel (avg.) | 4.5 | - | 4.3 | 5.1 | - | 6.1 | 6.8 | -

## Slide 22: Horizontal Test
Dynamic thermal load of each cavity

## Slide 23
Phase and amplitude locking test of cryomdoule
Amplitude and phase lock worked find @ operating Eacc (6.6 MV/m)
Stability: amplitude = ±0.13%, phase=±0.63°
Phase was well controlled by the integration of LLRF-tuner control system

## Slide 24: Installation

## Slide 25
Cryomodule and warm section is clean assembled in the portable clean booth in tunnel

## Slide 26: Cryogenic plant
SCL3 plant: 4.2 KW at 4.5 K, SCL2 plant: 13.5 kW at 4.5 K
Welding VBx to CM
VBx connection
QWR CMs, VBx in rear side
Warm compressors
LHe distribution box
Cold box

## Slide 27: Cool down of SCL3
4 K cool-down of cryogenic system, CDS(cryogenic distribution system) and thermal shield in CM
Temperature (K)
Time (month-date)
10 days

## Slide 28: Cool down of SCL3
4 K cool-down of cavities (fast cool-down for QWR)
Temperature (K)
Time (month-date)
10 days

## Slide 29: Cool down of SCL3
2 K cool-down of HWRs
Temperature (K)
Time (hh:mm)
Pressure (mbara)
Time (hh:mm)
1 days

## Slide 30: SCL3 Beam commissioning (April ~ Sep., 2024)
Beam Energy 18.5 MeV/u
  40Ar8+ beam accelerated by the entire SCL3(QWR/HWR) on May 17, 2024
[ Beam current measured by ACCT in MEBT and P2DT ]
[ Beam transmission through SCL3 ]
[ Energy in SCL cavities ]

## Slide 31: SCL3 Beam commissioning (April ~ Sep., 2024)
8 cavities (out of 124) were not used due to lack of spare SSPA (Q3, Q12, Q21), control issue(HA6, HA8, HB24, HB28, HB61).
Accelerating fields: QWR < 5 MV/m, HWR < 5 MV/m
Beam commissioning with 40Ar8+ and experiment with KoBRA and NDPS for external users (3 teams).
RI beam (25Na5+) from ISOL was successfully accelerated by SCL3 and measured in KoBRA.
Beam time was limited upto 40 minutes due to malfunction of FPC and tuner.
  Improvement of FPC and tuner is in progress.
3rd cool-down and beam operation in 2025 is in preparation.
  Cool-down will be started in April 2025.

## Slide 32
THANK YOU
대전광역시 유성구 국제과학로 1
1, Gukjegwahak-ro, Yuseong-gu, Daejeon, Korea
T 042 878 8842
F 042 878 8866