## Slide 1
Project Methodology of Large-Scale Cryogenic System:
ESS ACCP as A Case Study
Xilong Wang
Dalian Institute of Chemical Physics, CAS, China
March 29 2025

## Slide 2
Contents
Introduction
01
ESS Cryogenic System
02
Project Management
03
ESS ACCP as a project
04

## Slide 3
About Myself
Xilong Wang
2007-2012 DESY, Germany
2012-2020 ESS, Sweden
Scientist
2020- Dalian Institute of Chemical Physics (DICP), CAS, Dalian
2020- Institute of Advanced Science Facilities (IASF), Shenzhen
DESY/European XFEL Accelerator Module Test Facility (AMTF)
DESY/European XFEL Cryomodules
DESY/European XFEL Accelerator Cryogenic System
ESS Accelerator Cryoplant
2004-2006 IHEP/BEPCII, ALHZ, IP/CSNS, China
Senior Scientist
Group leader
SCT Division Head
From Sketch to the End
Prototype and Series Production
CDS and safety system Design
From Sketch to the End
Process Engineer
2002-2005- Institute of Technical Physics and Chemistry (TIPC)
Ph. D

## Slide 4
Dalian Institute of Chemical Physics (DICP)
Beijing
Dalian

## Slide 5
DICP Research Areas
Fundamental Research: Catalytic chemistry, Molecular reaction dynamics
Clean fossil energy utilization, Clean energy technology, Renewable energy
Applied Research: Chemical engineering, Analytical chemistry, Biotechnology
Dalian National laboratory for clean energy (DNL)
Facilities: Dalian Coherent Light Source (DCLS)

## Slide 6
Dalian Coherent Light Source (DCLS)
Undulator
LINAC
Driving Laser
Seed Laser
Experimental Hall
Warm accelerator:0.3 GeV
Tunable Wavelength: 50-150 nm
Pulse Energy: > 100 µJ
Pulse length: 100 fs
Repetition Rate: 50 Hz
Operation since Aug. 2018
More than 6000 hours per year
ASSCA 2023, KEK, 03/Feb/2024

## Slide 7
Electromagnetic Spectrum
DALS
S3FEL

## Slide 8
Important tools for physical and material sciences
High brightness, ultrafast pulse duration and full coherence
Advanced FEL features
A transformative tool for basic science research and cutting-edge technology R&D
Quantum materials, Atmospheric Chemistry, Catalysis, Interstellar chemistry, Biomolecules, Atomic and molecular physics
Meeting national great strategic demands and helping to maintain sustainable development of China
Energy, environment, health and new material

## Slide 9
XFELs Worldwide
Facility | Wavelength | Country | LINAC | Beam energy/GeV | Photon energy | Rep. rate/Hz | Status
European XFEL | Hard X-ray | EU | SRF | 17.5 | 8.4-30 keV | 27,000 | Operation
LCLS-II | Hard X-ray | US | CW SRF | 4 to 8 | 0.2-5 keV | 1,000,000 | Operation
SHINE | Hard X-ray | CN | CW SRF | 8 | 0.4-25 keV | 1,000,000 | Under construction
FLASH | Soft X-ray | DE | SRF | 1.25 | 14-300 eV | 5000 | Operation
DALS | EUV X-ray (6.5-180 nm) | CN | CW SRF | 1.0 | 8-600 eV | 1,000,000 | Proposed
S3FEL | Soft X-ray (1-30 nm) | CN | CW SRF | 2.5 | 0.04-1 keV | 1,000,000 | Approved
There is no EUV & Soft X-ray FEL facilities operating at MHz repetition rate in the world!

## Slide 10
Dalian Advanced Light Source (DALS)
EUV Free Electron laser machine
https://cryo.dicp.ac.cn/
Proposed by Dalian Institute of Chemical Physics (DICP)
1.0 GeV CW SRF accelerator
Ten 1.3 GHz Cryomodules & two 3.9 GHz Cryomodules
One dedicated cryoplant (~3 kW @ 2 K)
~100 SRF Cavities
http://www.dcls.dicp.ac.cn/
Located at Dalian, Northeast of China

## Slide 11
Cryomodule Structures & Components
Eight 9-cell dressed TELSA SRF cavities
Eight fundamental power couplers (FPC)
Eight Tuners & Piezo
One BPM + one SCQ magnet + two GVs
Cryomodule length: ~12.3 m & 38” vacuum vessel
Three supports for cold mass
Two adjustable stands
300 mm –ID, 12 m long tube, as backbone for cavity string piping system and safety release
Cryogenic Piping system
50 K aluminum shielding
JT and CD cryogenic valves
Instrumentations
Based on TTF Type I-V

## Slide 12
Dressed cavity
(8-12 per week)
Cavity vertical test
(4 per week)
Cavity string assembly
(1 per 2 weeks)
Horizontal tests
(1 per 4 weeks)
Tunnel installation
(1 per 2 weeks)
Transportation
(1 per 2 weeks)
Cold mass assembly
(1 per 2 weeks)
1
2
3
4
5
6
7
2
3
4
5
6
7
4
1
Cryomodule Series Production Chain

## Slide 13
DALS Module Test Facility (DMTF)
One Vertical Test Cryostat
One CM Test Bench
CMAI infrastructures
Cryogenic System (370 W @ 2 K)
Clean Room (ISO4/Class 10, 250 m2)
In operation since 2025
Funded by Dalian local government and real project (2019-2024)

## Slide 14
Test Facility CryoPlant (TFCP)
370 W @ 2 K, 400 W @ 5-8 K, 2500 W @ 40-80 K
Key design choices: PVPS for 2 K, LN2 pre-cooling
LKT refrigerator, all the rest
in house design & domestic manufactured
FCD: More than 50 g/s @ 4.5 K, 3 bara
CD/WU of each test bench independent
In operation since 2025

## Slide 15
Test Facility CryoPlant (TFCP)
In operation since 2025

## Slide 16
Shenzhen Superconducting Soft X-ray Free Electron Laser (S3FEL)
Institute of Advanced Science Facilities, Shenzhen (IASF) established in Sept 2020
Approved and fully funded by Shenzhen local government
Two large-scale science facilities’ whole life cycle planning, construction, operation & maintenance
Primary schedule:2026-2031

## Slide 17
2.5 GeV CW SRF accelerator
Charge/pC: 100
Emittance/mm-mrad: 0.5
Repetition rate/MHz: 1
FEL wavelength/nm: 1-30
Injectors
SRF LINAC
Beam lines
Shenzhen Superconducting Soft X-Ray FEL (S3FEL)
~300 SRF cavities, 28 CMs

## Slide 18
S3FEL Cryogenic System

## Slide 19
SRF Accelerator
Energy: 2 GeV
Rep. Rate: 14 Hz
Current: 62.5 mA
16 Instruments in Construction budget
Committed to deliver 22 instruments by 2028
Target Station
5MW average power
42 beam ports
Ion Source
Total cost: 1843 MEuros 2013
European Spallation Source (ESS)
http://europeanspallationsource.se/

## Slide 20
ESS Cryogenic System Overview

## Slide 21
ESS Accelerator Cryoplant (ACCP)
20
Three warm compressors, six turbines, three cold compressors and several bunches of plate fin heat exchangers
Mixed compression cycle at 2 K plus helium guard system for SP compressor
Capacity control
  Floating pressure cycle for HP compressor
  VFD for SP, LP compressors and CCs
  Exchange of CCs flow parts
All built-in acceptance test equipment
Energy recovery
Performance & Process

## Slide 22
ESS Accelerator Cryoplant (ACCP)
System Parameters

## Slide 23
ESS Accelerator Cryoplant (ACCP)
Exergy Efficiencies at various operation modes of two stages
Chart: Operation modes
| Norminal design | Turndown | 4.5 K Standby | TS Standby
Stage 1 | 0.24457 | 0.18342 | 0.15554 | 0.045101
Stage 2 | 0.25934 | 0.21023 | 0.1806 | 0.051058
Flow parts exchange
Warm compressor control
Floating pressure cycle
VFDs for SP&LP and CCs
VFDs for SP&LP
Only HP and T3 in operation

## Slide 24
Stay Organised. The biggest benefit…
Learn to Solve Problems and deal with Challenges
Project Management
Stay Disciplined. ...
Learn to Coordinate and Plan. ...
Learn to Work with Different People. ...
Project management is the practice of using knowledge, skills, tools, and techniques to complete a series of tasks to deliver value and achieve a desired outcome
Plan a vacation or Party, Starting a hobby, buy a new car, search for a new career…
Life is a project!

## Slide 25
Project Lifecycle
Decrease uncertainties
Document requirements
Define the scope
Select a solution
Select a method
Draw up a plan
Define the activities
Organize the resource
Calculate the cost
Handle the risk
Create and hand over the results
Follow up the activities and costs
Deliveries
Evaluate the project
Take advantage of lessons learned
Pre-Study
Planning
Execution
Closure

## Slide 26
Typical projects in a large-scale cryogenic system
Helium Refrigerator (WCS, Cold box & LHe Storage Tank)
Cryogenic Distribution System (Valve Boxes and Cryogenic Transfer Lines)
Recovery and Purification System (External purifier, Recovery Compressor, Gas Bag, etc.)
Pure Helium tank (PHS)
Interconnection piping
Control System
Instruments (Temperature Sensors, Flow Meters, Level Meters, etc.)
Cryomodules

## Slide 27
ACCP as a project
From a project management point of view
Pre-Study
Planning
Execution
Closure
Visiting
Demand Investigation
Performance
Staging & operation modes
Industry study
Schedule & Timing
Staffing
Budget
Others
Technical specification
Call for tender
Meeting & Reviews
Intermediate inspection
Delivery
Installation
Commissioning
Documentation
Lessons learnt
Scope

## Slide 28
Pre-study-Visiting
Name | Machine Type | Lab | Capacity | Comments
LHC | Accelerator | CERN | 2.4 kW @ 1.8 K 0.3 kW @ 4.5 K 33 kW @ 50-75 K | 8 plants 18 kW @ 4.5 K Eqiv. 3CC+SP compressor (ALAT) 4CC+SP compressor (LKT/IHI)
XFEL | Accelerator | DESY | 2.4 kW @ 2 K 4.0 kW @ 5-8 K 30 kW @ 40-80 K | Two HERA plants: 12 kW @ 4.5 K Eqiv. Upgrade to: 8 kW @ 4.5 K Eqiv. Each 4CC to LP
AMTF | Accelerator | DESY | 0.8 kW @ 2 K 0.5 kW @ 5-8 K 3 kW @ 40-80 K | Vacuum pump
CMTF | Accelerator | FERMI | 0.5 kW @ 2 K 0.6 kW @ 5-8 K 5 kW @ 40-80 K | 3CC + SP compressor/Pumps
SNS | Accelerator | ORNL | 2.4 kW @ 2.1 K 15 g/s @ 4.5 K liq. 8.3 kW @ 35 K | 4CCs to LP
CEBAF II | Accelerator | JLAB | 4.6 kW @ 2.1 K 10 g/s @ 4.5 K liq. 12 kW @ 35 K | Two plants 5CC to LP
W-7X | Stellarator | IPP | 3 kW @ 3.4 K 25 g/s @ 4.5 K liq. 14 kW @ 80 K | Two cold circulators
FAIR | Accelerator | GSI | 35 kW @ 4.5 K 33 g/s @ 4.5 K liq. 24 kW @ 50 K | 40 kW @ 4.5 K Eqiv. Magnets
KSTAR | Tokamak | NFRI | 5.3 kW @ 4.3 K 17 g/s @ 4.5 K liq. 270 g/s @ 50-70 K | 9 kW @ 4.5 K Eqiv. Two cold circulators Magnets
Take any possible chances to visit similar projects/Labs and Vendors: Lab visiting, Conferences, Workshop, etc.
Pay particular attention to:
History/Background (CERN, DESY)
Specific application (PVPS)
Discuss overview, design consideration, technical issues, challenges, experiences and lesson learned with a short meeting in person and a site visit
Big science facility community encourages free and open exchange of scientific knowledge & expertise
Machine type (LN2 pro-cooling)
Make summary and make friends
You can never get your experience only from paper and reading!

## Slide 29
CERN: The Sector 3-4 incident (just before the 1st ramp)
19th September 2008 at 11:18.36 last test of the last sector: 7kA (4TeV) towards 9.3 kA (5TeV)
Electrical arc at 8.7 kA in the interconnection
Rupture of bellows, expansion of liquid Helium with MLI debris
Pre-study-Visiting

## Slide 30
2009 - overall repair and consolidation
Pre-study-Visiting

## Slide 31
Pre-study-Visiting
The Higgs particle was discovered on 4th July 2012
Peter W. Higgs & Francois Englert: 2013 Noble price

## Slide 32
Pre-study- Demand investigation
ESS LINAC Layout
ESS ACCP Block-Diagram

## Slide 33
Pre-study- Demand investigation
CM temperature levels: cavities@2 K, thermal Shield@ 40-50 K, couplers @ 4.5-300 K
CNRS-IN2P3, SLHIP4, 2014
Customer/user first: Cryomodules + Cryogenic Distribution System (CDS)
Optimus design:13 Spoke CMs + 9 MBCMs + 21 HBCMs, Contingency: additional 14 HBCMs
CDS: Cryogenic transfer line, one valve box for each CM with a jumper connection
Collect CM&CDS information as much & accuracy as possible (mass, volume, helium inventory)

## Slide 34
Pre-study- Performances
  Heat loads
    3 kW @ 2 K
    9 g/s @ 4.5 K
    11380 W @ 40-50 K
  Continuous Operation
    24 h per day / 7 days per week
    2 years without scheduled shut-down
  Availability
    > 99 % not count utilities & process control
Safety factors
ESS LINAC Layout

## Slide 35
Pre-study- Staging & Operation Modes
Report on ESS operation (Dec 2012)
  Stage 1 (2019-2023) and Stage 2 (2023-…)
  Operation Modes：
    Nominal Design (Beam on)
    Turn Down (Beam off)
    4.5 K Standby (Maintenance)
    40 K standby (Summer break)
    Max. Liq. Mode (Don’t forget)
    Transition modes (CD/WU, Purge, etc.)

## Slide 36
Pre-study- Performances
Maximum design capacity
Turndown: ~60 % within one stage
Max. turndown: ~45 % , even lower
Current state of the art

## Slide 37
Pre-study- Scope

## Slide 38
Pre-study- Industry Study
  Design Choices
    Process, Machine, LN2 cooling, heat recovery, control, Efficiency, etc.
  Layout and footprint
  Utility requirements: Electricals, CW, IA and HVAC
  Schedule:
    Proposal, Design, Manufacture, Delivery, Installation & Commissioning
Laydown and staging area for installation
Preventive maintenance plan
Spare parts and redundancy (hot spare)
Interfaces
Budget
…

## Slide 39
Planning – Schedule & Timing
  One year specification (Draft, External review, Internal procurement procedure)
  Half year procurement (Proposal preparation, Evaluation, complain of tenderers)
  Four years execution (Design, manufacture, installation and commissioning)
ESS ACCP project real schedule
  Delayed in total of 14 months
  LKT takes ~10 months
  ESS takes ~4 months

## Slide 40
Planning – Staffing
ESS Project manager
CDS
Utilities (CW, IA, Electricals, HVAC)
Control
LKT Project manager
Safety
QA/QC
RAMI
CMs
Piping
CF
PPS/ODH
Alignment
External
Internal
  Process
  Mechanics/Designer
  Control & Instruments
  Vacuum
  Conventional Facilities

## Slide 41
Planning – Budget
Start of contract: 5%
Preliminary Design Review 1 (order WCS, PFHX): 20%
Preliminary Design Review 2 (order Vessel, Turbines, CC, CV): 15%
Detail Design Review 1 (Start CBX fabrication): 25%
LDR & Detail Design Review 2: 5%
Delivery of WCS: 10%
Delivery of CBX: 10%
Provisional Acceptance Certificate: 10%

## Slide 42
Planning – Others
  Control strategy and architecture/infrastructure
  PED and Work environment authority
    ASME, EN13445, AD2000, Safety valve inspection
  Quality assurance and control
    Notify body (third party), Vendor internal QA/QC and Lab QA/QC
  Naming convention
  Date management system (CHESS, confluence, JIRA)
  Documentation
  …

## Slide 43
Planning – Technical Specification
Codes and Norms
Site condition / Utility interfaces
Performance
Key component (WCS and Cold box)
Spare parts
Control
Instrumentation, interlocks and electrical design
Requirements on mechanical design, manufacture and mounting
Test
Quality management
Documentation

## Slide 44
Planning – Call for tenders
ACCP – A03 Instruction to Bidders (7 pages)
ACCP – A06 Evaluation Criteria (5 pages)
ACCP – A07 Draft Supply Agreement (27 pages)
ACCP – A02 Company Qualification (7 pages)
ACCP – A08 General Conditions of Tender (4 pages)
ACCP – A05 Technical Specification (117 pages)
ACCP – A01 Tender Management (2 pages)
ACCP – A04 Statement of Work (23 pages)
Tender Evaluation
Award recommendation
CAPEX: Price, 30%
OPEX: Power Consumption, 30%
Qualitative: Almost equal, 40%
Contract signed in March 2015
Tender documents (2014-06-16)

## Slide 45
May 2015
  KOM
Aug 2015
  PDR-1
Oct 2015
  HAZOP
Nov 2015
  PDR-2
Jan 2016
  FMEA
Mar 2016
  CDR-1
June 2016
  IDR
Aug 2016
  LDR
Sept 2016
  CDR-2
Mar 2015
  Contract signed
Apr 2017
  IRR
Apr 2018
  WCS/CB start-up
July 2019
  SAT
Execution – Meeting & Reviews

## Slide 46
Apr 2016
  PFHE
Jun 2016
  Motors
Jul 2016
  Compressor
Feb 2017
  Cold box internal
Mar 2017
  Compressor skid functional
May 2017
  Control loop check
May 2017
  GMP & ORS & Dryer
Mar 2017
  Compressor skid leak test
Jun 2017
  Dewar
Mar 2018
  CB software tests
Execution – Intermediate Inspection
Inspection and Test Plan (ITP)
Factory Acceptance Test (FAT)
Hold and Witness points
External experts or consultants

## Slide 47
Execution – Delivery
Buildings: May 2017
Utilities: Last minute
Warm Tanks: Oct 2017
Warm piping: Dec 2017
Crane
HVAC
Cable
Warm piping

## Slide 48
Execution – Delivery
Key components have been delivered starting from July 2017
Delivery Schedule, Lifting plan (Risk Analysis), Professional on-site team

## Slide 49
Execution – Installation
Interconnecting piping installation (CB-WCS)
Equipment placement and installation
Grouting compressor skids
Platform installation
Final documentation
WCS/CB hall piping installation
Mechanics verification tests (NDT, PT, LT)
Electrical installation (Cabling, wiring, earthing)
Electrical verification tests (loop check, test protocols)
Scope and Sequence

## Slide 50
Execution – Installation
Ready at May 2018 – at least half year behind the schedule

## Slide 51
Execution – Installation
How we work
Area Supervisor
WSCP/Work Order
Certificate and training
  Hot work
  Fall protection
  Forklift
  Crane
  First aid
Work Safety

## Slide 52
Execution – Installation
Parallel work & conflictions
  Framework with one company will help a lot and P&DP request
Under-estimation of civil engineering
  Foundation, grouting, holes, etc.
Two months delay
Key equipment failure, damage, repair & replacement
  See an example next slides
On site quality control and inspection
  Well experienced staff and sound engineering sense
Design drawbacks or mistakes
Missing pressure and T sensors, isolating valves
Reserve enough margin in your schedule
Leak searching and fixation
Lessons learned

## Slide 53
Execution – Installation
Lessons learned-Key equipment failure and replacement
Two oil coolers corrosions / replacement (At least six months delay)

## Slide 54
Execution – Installation
Lessons learned-On site inspection
Fixed
Fixed
Flexible
Flexible

## Slide 55
Execution – Installation
Lessons learned-Leak searching and fixation
Leak here!

## Slide 56
Execution – Installation
At least but not limited to…
Escape way for fire safety
  900 mm in Sweden regulation
Noise protection (Sound hoods)
Double safety valves
Safety valve re-calibration
WCS and CB platforms
Wiring tagging in cabinets
Piping interfaces
  In-house design will be a good solution

## Slide 57
Execution – Commissioning
Chart: HP
| 5.214105793450881 | 5.2261306532663321 | 5.2285714285714286 | 5.2413793103448274 | 5.364779874213836
Isothermal Efficiencies | 0.5913 | 0.58267 | 0.58054 | 0.56967 | 0.57048
Volumetric Efficiencies | 0.76906 | 0.7549 | 0.75854 | 0.7402 | 0.75132
 | 0.56061
 | 0.74703
Chart: LP
| 2.9523809523809526 | 3.2307692307692304 | 3.5769230769230771 | 4.0192307692307692 | 4.0192307692307692
Isothermal Efficiencies | 0.5762 | 0.57839 | 0.58598 | 0.58358 | 0.58403
Volumetric Efficiencies | 0.91225 | 0.92156 | 0.92319 | 0.92474 | 0.91883
 | 0.49107
 | 0.89392
Chart: SP
| 3.9809523809523806 | 6.3265306122448983 | 6.95 | 10.53125 | 11.071428571428571
Isothermal Efficiencies | 0.58837 | 0.54579 | 0.53873 | 0.42942 | 0.42052
Volumetric Efficiencies | 0.90479 | 0.92511 | 0.93134 | 0.91265 | 0.90574
 | 0.48197
 | 0.85347
Design
Design
Mass flow and power consumption is fulfilled
Both isothermal and volumetric efficiencies much better than the design
Impurities keep constant during tests (N2: 15 vpm, H2O: 5 vpm)
Vibration less than 3 mm/s (Design: 10 mm/s)
Integrated noise level: 90 dB (A) (unofficial value, Design: 110 dB (A) each compressor)

## Slide 58
Execution – Commissioning

## Slide 59
Closure
Start the commissioning as early as possible
Reserve enough margin in your schedule
Make your utilities available as early as possible
Prepare your staff as early as possible
Make the interfaces as simply as possible
Framework with one installation company
Piping in-house design
Bring Helium recovery system on line early

## Slide 60
  Stay foolish
  No details too small
  Stay hungry
  Team spirit

## Slide 61
Project management, Bo Tonnquist, third edition, www.sanomautbildning.se/project
The European Spallation Source Design, Roland Garoby et al 2018 Phys. Scr. 93 014001
ESS Technical Design Report, April 23, 2013, ESS-doc-274, http://eval.esss.lu.se/cgibin/public/DocDB/ShowDocument?docid=274 , ISBN 978-91-980173-2-8
Accelerator Cryoplant (ACCP) Status at European Spallation Source ERIC, Xilong Wang, Philipp Arnold, John Weisend II, Cryo-Ops 2018, Beijing, China
Commissioning of the Warm Compressor System for the ESS Accelerator Cryoplant , X L Wang, R Wischhoefer, P Selva, P Nilsson, J Råström, R Goncalves, M Olsson and P Arnold, IOP Conf. Series: Materials Science and Engineering 755 (2020) 012087 doi:10.1088/1757-899X/755/1/012087
Xilong Wang, Philipp Arnold, Wolfgang Hees, J Hildenbeutel, JG Weisend II, ESS accelerator cryoplant process design, IOP Conference Series: Materials Science and Engineering 101 (2015) 012012
Xilong Wang, Philipp Arnold, JaroslawFydrych, Wolfgang Hees, John M Jurns, Daniel Piso, John Weisend, Specification of the ESS accelerator cryoplant, Physics Procedia 67 (2015), 89-94
Xilong Wang, J.G. Weisend II, T. Koettig, W. Hees, C. Darve, ESS accelerator cryoplant, HVAC&R Reseach (2014) 20, 1-6
X. L. Wang, S. Barbanotti, J. Esche, K. Jensch, R. Klos, W. Maschmann, B. Petersen, O. Sawlanski, Thermal performance analysis and measurements of the prototype cryomodule of European XFEL accelerator – Part I, Nuclear Instruments and Methods in Physics Research A 763 (2014) 701-710
X. L. Wang, S. Barbanotti, J. Esche, K. Jensch, R. Klos, W. Maschmann, B. Petersen, O. Sawlanski, Thermal performance analysis and measurements of the prototype cryomodule of European XFEL accelerator – Part II, Nuclear Instruments and Methods in Physics Research A 763 (2014) 688-700
Wolfgang Hees, P Arnold, J Fydrych, H Spoelstra, XL Wang, JG Weisend II, The ESS cryomodule test stand, Physics Procedia 67 (2015), 791-795
J Fydrych, P Arnold, W Hees, P Tereszkowski, XL Wang, JG Weisend II, Cryogenic distribution system for the ESS superconducting proton linac, Physics Procedia 67 (2015) 828-833
Commissioning of the Large-Scale 2 K Helium Refrigeration System at ESS, J. Zhang, P. Arnold, N. Kolev & A. Rueegge, CEC28-ICMC 2022: Proceedings of the 28th International Cryogenic Engineering Conference and International Cryogenic Materials Conference 2022 pp 101–108
The real “life” of operation, Vacuum for Particle Accelerators, Glumslov, Sweden, V. Baglin, 6 - 16 June, 2017
References

## Slide 62
References