## Slide 1
Ji Quan
Oct. 22th, 2024, CEPC Detector Ref-TDR Review
CEPC Detector Mechanical integration

## Slide 2: Content
Introduction
Requirements
Technical challenges
Overall installation plan
Detail installation design
Research team
Summary and working plan

## Slide 3: Introduction
CEPC Detector Mechanical integration : (Ref-TDR)
1. Detectors overall mechanical layout drawing
Based on the design requirements of the sub-detectors and its electronics
2. Connection structure design between the sub-detectors
and installation design for each sub-detector
Provide design direction for the interface design of each sub detector
3. Configuration design of the underground experimental room
Vertical shaft hoist and lifting equipment , etc.
4. Others (Underground ancillary room , Ground room)

## Slide 4: Introduction
1. Detectors overall mechanical layout drawing :
From outside to inside
Yoke
(Muon)
Magnet
HCAL
ECAL
TPC
(OTK)
ITK
Beampipe
(VTX LumiCal)
Barrel(7)
End(3)
Yoke
(Muon)
HCAL
ECAL
(OTK)
MDI(1)
ACC component

## Slide 5: Introduction
2. Initial size distribution :
Further optimization and improvement are needed
Dimension :
length : 11950 mm
Height : 10370 mm

## Slide 6: Introduction
Total weight :
≈ 5150 t
Yoke : ≈ 2960 t
(Barrel: 1560 t End: 700 X 2 t)
Magnet : ≈ 290 t
HCAL : ≈ 1660 t
(Barrel: 960 t End: 350 X 2 t)
……

## Slide 7: Introduction
3. Layout of installation scheme for “Pre-assembly point“ :
Installation location :
Pre-assembly point
This is a very compact design
Main width : 31500 mm
Length : 55500 mm

## Slide 8: Requirements
1. Installation Clearance and accuracy : (See the following table)
Profile Tolerance(mm) |  | installation accuracy(mm) |  | positioning accuracy Coaxiality(mm)
 |  | Collimation accuracy (mm) | GAP (mm) | 
Yoke | ± 1 | < 1 |  | ±0.5
Magnet | Outer: 0 to -5, inner: 0 to +5 | < 2 | 10 | ± 1
HCAL | Outer: 0 to -5, inner: 0 t0 +5 | ± 2 | 10 | ± 0.5
ECAL | Outer: 0 to -5, Inner: 0 t0 +5 | ± 2 | 10 | ± 0.5
TPC | Outer: 0 to -2, Inner: 0 t0 +2 | ± 1 | 5 | ± 0.1
ITK | Outer: 0 to -2, Inner: 0 t0 +2 | ± 1 | 5 | ± 0.1
Beampipe | Outer: 0 to -0.3, Inner: 0 t0 +0.3 | ± 0.5 | 2 | ± 0.1
Minimum gap principle :
As small as possible
Note :
1. The deformation during the installation process of the sub detector must meet the gap requirements
2. The data in the table will continue to be optimized as the design progresses

## Slide 9: Requirements
Connection design :
Barrel Yoke : Fixed on the Base
Magnet : Fixed on the Barrel Yoke
Barrel HCAL : Fixed on the Barrel Yoke
Barrel ECAL : Fixed on the Barrel HCAL
TPC+OTK : Fixed on the Barrel ECAL
ITK : Fixed on the TPC
Beampipe(Vertex and LumiCal) : Fixed on the ITK
End-cap ECAL+OTK : Fixed on the Barrel HCAL
End-cap HCAL : Fixed on the Barrel HCAL
(Auxiliary cylinder or Flange)
End Yoke : Fixed on the Base
1. The connection structure should follow
the principle of proximity connection
2. The connection structure should be adjustable (Remote automatic)
Base

## Slide 10: Requirements
Consists of 4 sections :
Detection angle : 8.1 ° (arccos0.99)
(Before ECAL)
(After ECAL)
ECAL : 700 X 700 mm
HCAL : Ø800 mm
Yoke : Ø1100 mm
MDI boundary
Conical hole and stepped holes are
reserved spaces for accelerators

## Slide 11: Technical challenges
1. The contradiction between self weight deformation and installation clearance
Requirements :
GAP between HCAL and Magnet : 10 mm
GAP between HCAL and ECAL : 10 mm
Self weight deformation :
18.8 mm (> 10mm)
In the current mechanical design process, we encounter many technical challenges:
Key :
Deformation must be controlled
through mechanical optimization
design
How to
Control Deformation?

## Slide 12: Technical challenges
In the current mechanical design process, we encounter many technical challenges:
Pillow seal maybe used for remote vacuum automatic connection
2. Vacuum sealed Connection between the Acc MDI component and the Be beampipe
This is a connection design that
cannot be operated
using conventional methods
Technical difficulties :
leak rate : 2.66 X 10 -11 Pa *m3 /s
Need to improve and develop current technology
Acc MDI component
Beampipe

## Slide 13: Overall installation plan
1. Installation location :
Pre-assembly point
Advantage : Beam-tuning experiments and detectors installation can be carried out
2. Installation design :
● Installation and disassembly processes are reversible
● Retention of installation benchmarks (Mounting rail)
Purpose: To facilitate the maintenance and replacement of the detectors
Follow three principles ：

## Slide 14: Overall installation plan
Collision point
robotic arm
Overhead travelling crane
3. Modern installation :
Installation operation design must be suitable for completion through a robotic arm
If Possible
Future detector installations will be easily installed through
a combination of robotic arms and two overhead cranes
Design requirement :
1. The auxiliary tools is as fewer as possible
2. Operation is as sample as possible

## Slide 15: Detail installation design
Detail installation design:
1. Reliability and safety assessment of integral detectors and their connecting structures
(FEA --- stress and deformation)
2. Overall installation steps
3. Installation process of the detectors
4. Modular lifting and integral lifting of components

## Slide 16: Detail installation design
1. Overall reliability and safety assessment
Deformation : ≈ 0.9 mm
Stress : ≈ 76 MPa
Barrel supports
End Support
Drawing of the End and Barrel support
Conclusion :
Meet requirement
(< 1 mm)
Yoke : 1560 t
Assembly deformation of yoke
without detector
two end flange
and
barrel supports
can reduce the deformation

## Slide 17: Detail installation design
1. Overall reliability and safety assessment
Yoke : 1560 t
Magnet : ≈ 290 t
HCAL : ≈ 1660 t
(Barrel: 960 t End: 350 X 2 t)
Deformation of the yoke
in the presence of a sub-detectors
Load
1950 t
Other lighter components
are ignored
Focus on the deformation of the Yoke
Deformation : 1.07 mm
It’s safety
Deformation within reasonable limits
Deformation : ≈ 0.9 mm

## Slide 18: Detail installation design
2. Overall installation steps
Note :
Mounting rail is the installation reference,
and must be pre-collimation with yoke
Barrel Yoke
General installation drawing
The steps are as follows :
1. In the ground room
Complete the assembly work of each sub-detector, including electronics, etc.
2. In the shaft
Each sub-detector is lifted into the underground experimental room through vertical shaft in sequence
3. In the underground experimental room ---
Assemble each sub detector on the mounting rail and push them into the yoke in sequence
most important part of the installation
Mounting rail

## Slide 19: Detail installation design
Yoke
Magnet
HCAL
ECAL
TPC(OTK)
End ECAL(OTK)
ITK
End HCAL
ACC Component
Step 1 Install the barrel sub-detector first, in the following order :
Yoke, Magnet, HCAL, ECAL, TPC(OTK), ITK, Beampipe(Vertex)
Step 2 Install the end sub-detectors, in the following order :
End ECAL(OTK), End HCAL, End Yoke
Beampipe
(Vertex)
Installation sequence of detectors(As shown in the exploded view) :
2. Overall installation steps

## Slide 20: Detail installation design
3. Installation process of detectors --- Different detectors use different installation methods
Step 1 Alternating installation : Yoke and Magnet (2) --- Barrel Detectors
Step 2 Core shaft installation : Barrel HCAL and Barrel ECAL (2) --- Barrel Detectors
Step 3 Cantilever installation : TPC(OTK) ITK Beampipe(Vertex + LumiCal) (3) --- Barrel Detectors
End HCAL and End ECAL --- End Detectors
Step 4 Installation : Yoke --- End Detectors
Step 5 Move the detectors from the Pre-assembly point to Collision point
Push the accelerator vacuum component into the center of the detector and connect it with the beam tube vacuum

## Slide 21: Detail installation design
Step 1 Alternating installation : Yoke and Magnet (2)
Method :
Design of mutually supportive ‘zero-tool’ assemblies
Advantage :
No redundant tooling, which reduces installation time
Install Yoke and Magnet
Step 1 : Place the both end Yoke flanges on the Base
Step 2 : Install the lower half module first
Step 3 : install the Magnet
Step 4 : Install the Upper half module
This is an efficient installation design
(‘zero-tool’ achieves the installation of two detectors)
Preparation : All components are lifted from the shaft
3. Installation process of detectors --- Different detectors use different installation methods

## Slide 22: Detail installation design
Step 2 Core shaft method installation : HCAL and Barrel ECAL (2) --- Barrel
Core shaft method installation of HCAL
Clearance requirement : 10 mm
Installation Method Instructions :
1. Place HCAL on the core shaft
2. Moving the HCAL using external guide rails
3. Installation process of detectors --- Different detectors use different installation methods

## Slide 23: Detail installation design
Step 2 Core shaft method installation : HCAL and Barrel ECAL (2) --- Barrel
Load :
1. Self-weight
2. 1000 tons HCAL
(ECAL 150 tons)
Result :
Max Deformation : ≈ 3.9 mm
< 10 mm (Gap)
Hight : 2000 mm
Width : 2000 mm
Length : 27300 mm
Design of Combination core shaft
Short core shaft
Middle core shaft
Long core shaft
Adjustable base
Conclusion :
Meet installation requirement
For HCAL and ECAL
Constraints :
Fixed at both ends
3. Installation process of detectors --- Different detectors use different installation methods

## Slide 24: Detail installation design
Step 2 Core shaft method installation : HCAL and Barrel ECAL (2) --- Barrel
Install Barrel HCAL
Preparation : Assembly axis of HCAL is 10mm lower
than the magnet axis
Step 1 : Place the both end HCAL(Barrel) rings on the guide rail
Step 2 : Install the lower half module first
Step 3 : Place the long core shaft on the guide rail
Step 4 : Place the counterweight short core shaft onto the guide rail
at the other end
Step 5 : Install the middle core shaft
Step 6 : Install the upper half module
Step 7 : Lift 10 mm
Step 8 : Move HCAL(Barrel) into the Magnet
Step 9 : Install connection rings at both end
3. Installation process of detectors --- Different detectors use different installation methods

## Slide 25: Detail installation design
Step 2 Core shaft method installation : HCAL and Barrel ECAL (2) --- Barrel
Install Barrel ECAL
Step 1 : Place the long and short core shafts on the guide rail (Omitted)
Step 2 : Lifting ECAL from the shaft into the hall
(Middle core shaft and ECAL are assembled)
Step 3 : Connect the ECAL(middle core shaft) to the long and short shafts
Step 4 : Move ECAL(Barrel) into the HCAL(Barrel)
3. Installation process of detectors --- Different detectors use different installation methods

## Slide 26: Overall installation design
Step 2 Core shaft method installation : HCAL and Barrel ECAL (2) --- Barrel
L-shaped
End Ring
How to
Control Deformation?
Deformation : 3.3 mm
If necessary, further optimization can be done to achieve smaller deformation
3. Installation process of detectors --- Different detectors use different installation methods

## Slide 27: Detail installation design
Step 3 Cantilever method installation : TPC(OTK) ITK Beampipe(Vertex + LumiCal) (3) --- Barrel
Install TPC(OTK)
Step 1 : Place the long core shafts on the guide rail (Omitted)
Step 2 : Lifting TPC from the shaft into the hall
(Middle core shaft and TPC are assembled)
Step 3 : Connect the TPC(middle core shaft) to the long shafts
Step 4 : Move TPC into the ECAL(Barrel)
Deformation : 0.08 mm
(< 5 mm Gap)
Load : 250 kg (OTK)
Constraint : Fixe both end
Calculation conditions
Installation :
1. Cantilever installation
2. Supported at both ends on the cantilever shaft
3. Installation process of detectors --- Different detectors use different installation methods

## Slide 28: Detail installation design
Step 3 Cantilever method installation : TPC(OTK) ITK Beampipe(Vertex + LumiCal) (3) --- Barrel
Install ITK
Step 1 : Place the long core shafts on the guide rail (Omitted)
Step 2 : Lifting ITK from the shaft into the hall
(Middle core shaft and ITK are assembled)
Step 3 : Connect the ITK(middle core shaft) to the long shafts
Step 4 : Move ITK into the TPC
Load : Self weight
Constraint : Fix one end
Calculation conditions
Deformation : 1.4 mm
(< 5 mm Gap)
3. Installation process of detectors --- Different detectors use different installation methods

## Slide 29: Detail installation design
Step 3 Cantilever method installation : TPC(OTK) ITK Beampipe(Vertex + LumiCal) (3) --- Barrel
Install Beampipe(Vertex + LumiCal)
Step 1 : Place the long core shafts on the guide rail (Omitted)
Step 2 : Connect the Beampipe installation axis to the long shafts
Step 3 : Lifting Beampipe from the shaft into the hall
(Installation flange and beampipe are assembled)
Step 4 : Move Beampipe into the ITK
3. Installation process of detectors --- Different detectors use different installation methods

## Slide 30: Detail installation design
Step 4 Cantilever method installation : ECAL(OTK) HCAL Yoke --- End (3) --- End
Install END ECAL(OTK)
Step 1 : Place the long core shafts on the guide rail (Omitted)
Step 2 : Connect the ECAL(End) Flange to the long shafts
Step 3 : Lifting ECAL from the shaft into the hall
Step 4 : Move ECAL(End) into the HCAL(Barrel)
3. Installation process of detectors --- Different detectors use different installation methods

## Slide 31: Detail installation design
Step 4 Cantilever method installation : ECAL(OTK) HCAL Yoke --- End (3) --- End
Install End HCAL and End Yoke
Step 1 ：Install the End HCAL
(The same as install ECAL)
Step 2 : Install the End Yoke
3. Installation process of detectors --- Different detectors use different installation methods

## Slide 32: Detail installation design
Step 5 Move the Detectors from Pre-assembly point to Collision point
Push the accelerator vacuum component into the center of the detector and connect it with the beam tube vacuum
This is a basically viable installation design
Better installation routes may be found in future optimized designs
Step 1 : Move the detectors from the Pre-assembly point
to collision point
Move distance : 16500 mm
Hydraulic cylinder movement distance : ≈ 2.1 m
Hydraulic cylinder thrust : 50 t (> 30 t)
(6000*0.005=30 t hydrostatic guideway)
Step 2 : Install the ACC vacuum component
3. Installation process of detectors --- Different detectors use different installation methods

## Slide 33: Detail installation design
4. Modular lifting and integral lifting for components : (relates to the design of the shaft and the hoists)
Magnet
ECAL
TPC+OTK
ITK
Beampipe
End - ECAL
End - HCAL
Yoke
End Yoke
HCAL
heaviest single module
≈ 350 t
Largest single size
9050 L X Ф 8470
Modular lifting (3)
Integral lifting (7)

## Slide 34: Research team
IHEP (5)
Design units
Zhejiang University
Manufacturing units
CITIC Heavy Industry
University
Hunan University
University of South China
Southwest Jiaotong University
Students
Xia Shang Doctor
He LongYan Master
Calculation team
Design team
Future planning and visioning :
1. Allocate more mechanical engineers to join CEPC R&D as needed
2. Seeking cooperation units in special fields
3. Seek international cooperation
Team characteristics:
1. Optimize and configure the engineering design team with the mechanical engineers from the High Energy Institute as the core
2. Resource allocation is comprehensive and reasonable, can complement each other's shortcomings
Such a team is able to
undertake CEPC design tasks

## Slide 35: Summary and working plan
1. The overall installation scheme for the detector has been basically completed
Summary
Question :
The design of the connection structure only meets basic function,
far from achieving automatic adjustment and convenient operation

## Slide 36: Summary and working plan
Working plan
1. Optimization and refinement of existing installation programmes
2. Refine the connection design of sub detectors
3. Optimize the layout of the underground experimental hall and its auxiliary hall
4. Start planning the layout design of the ground hall

## Slide 37
Thank you for your attention!
Aug. 7th, 2024, CEPC Detector Ref-TDR Review