## Slide 1: Schedule of the MDI installation
Mingyi Dong
2024.10.28

## Slide 2
After discussion with accelerator systems, we have the preliminary schedule of the MDI installation
Minor adjustments may be made based on actual execution

## Slide 3: Schedule (east side)
 | Detailed tasks | Time (day) | date
1 | Deal with CGEM cables to ensure they do not interfere with the installation of the EEMC and beam pipe | 1 | Before Nov.13
2 | (1) Remove current operation platform on east side (2) Push the east EEMC back to its original position | 2 | Nov.14-15
3 | Install the support tools for beam pipe installation | 1 | Nov.16
4 | Install beam pipe | 1-2 | Nov.17-18
5 | Remove the support tools for beam pipe installation | 1 | Nov.19
6 | Deal with CGEM cables to ensure they do not interfere with the installation of SCQ | 1 | Nov.20
7 | Installation of SCQ and related work (some jobs ar not in the IP region) |  | Nov.11-Dec.3
8 | Power on CGEM and MDC to check the connection | 1 | Dec.4
9 | Laser measurement of SCQ | 1 | Dec.5
9 | Install ZDD detector | 2 | Dec 6-7
10 | Check CGEM cables to ensure that they do not interfere with the extraction of EEMC | 1 | Dec.8

## Slide 4: Schedule (east side)
 | Detailed tasks | Time (day) | date
11 | (1) Pull out EEMC (2) Set up the operation platform on east side | 1 | Dec.9
12 | Install CGEM shielding plate on both sides （The west side can be delayed by one day） | 1 | Dec.10
13 | Fix cables of beam pipe and CGEM on the support structure of SCQ and other magnets | 2 | Dec.11-12
14 | (1) Remove the operation platform (2) Push the east EEMC back to its original position and remove the mechanical tools | 2 | Dec.13-14
15 | Installation of the cover of SCQ and Q2, BH02,HV02, shielding blocks | 2 | Dec.15-16
16 | Laser measurement of the magnets | 2 | Dec.17-18
17 | Recover the connection of vacuum, water pipes, cables |  | Dec.19-24
18 | Recover the cables of EEMC and ETOF, close the east door | 2 | Dec.25-26

## Slide 5: Schedule (west side)
 | Detailed tasks | Time (day) | date
1 | Deal with CGEM cables to ensure they do not interfere with the installation of the beam pipe | 1 | Nov.16
2 | Install beam pipe | 1-2 | Nov.17-18
3 | Deal with CGEM cables to ensure they do not interfere with the installation of the SCQ | 1 | Nov. 19
4 | Installation of SCQ and related work |  | Nov.25-Dec.4
5 | Power on CGEM and MDC to check the connection | 1 | Dec.5
6 | Laser measurement of SCQ | 1 | Dec.6
7 | Install small angle lum. detector | 1 | Dec.7
8 | Change the operation platform |  | Dec. 8
9 | Install CGEM shielding plate on the west side | 1 | Dec..9
10 | Fix cables of beam pipe and CGEM on the support structure of SCQ and other magnets | 2 | Dec.14-15

## Slide 6: Schedule (west side)
 | Detailed tasks | Time (day) | date
11 | Remove the operation platform Push the east EEMC back to its original position and remove the mechanical tools | 2 | Dec.16-17
12 | Installation of the cover of SCQ and Q2, BH02,HV02, shielding blocks | 3 | Dec.18-20
13 | Laser measurement of the magnets | 2 | Dec.21-23
14 | Recover the connection of vacuum, water pipes, cables |  | Dec.24-29
15 | Recover the cables of EEMC and ETOF, close the east door | 2 | Dec.30-31

## Slide 7: Backup

## Slide 8: Schedule (may be updated each week)
No. | tasks | Duration（day） | Start time and stop time | Sub-system involved | Status
1 | Removal of equipment of machine |  | July 1- Aug. 6 | Utility, Small angle lum. Detector and ZDD, Beam pipe, slow control | done
2 | Pull-out of EEMC |  |  | Utility, EMC, TOF, MDC | done
3 | Removal of inner chamber（Operate simultaneously on both sides ） | 51 | Aug. 7- Sep.7 Sep.8- Sep. 28 | MDC, MDC electronics, Gas, Mechanics, Laser measurement group, Trigger, DAQ, Slow control | done
4 | Installation of CGEM | 44 | Sep.29- Nov. 11 | CGEM group, MDC, MDC electronics, Gas, Mechanics, Laser measurement group, Trigger, DAQ, Slow control | On Schedule
5 | Recover EEMC |  | Nov. 12-Dec.30 | Utility, EMC, TOF, MDC | 
6 | Recover equipment of machine |  |  | Utility, Small angle lum. Detector, ZDD, Beam pipe, slow control | 
total |  | 180 days | July 1- Dec.30 |  |