## Slide 1
Ji Quan Xia Shang
(On behalf of the CEPC Mechanics Working Group)
Oct. 22th, 2024, CEPC Detector Ref-TDR Review
CEPC Detector Mechanical Integration

## Slide 2: Content
Introduction
Requirements
Technical challenges
Overall installation plan
Detail installation design
Our Team
Summary and working plan

## Slide 3: Introduction
CEPC Detector Mechanical Integration : (Ref-TDR)
1. Overall mechanical layout
Based on design requirements of sub-detectors and their electronics
2. Connection structure between sub-detectors and the installation of sub-detectors
Provide design guidance for the interface of each sub-detector
3. Configuration of the underground experimental Hall
Space for the detector and installation
Vertical shaft hoist, lifting equipment, and other essential infrastructure
4. Others
Underground auxiliary hall, Ground Halls

## Slide 4: Introduction
1. Overall mechanical layout:
From outmost to innermost
Yoke
(Muon)
Magnet
HCAL
ECAL
TPC
(OTK)
ITK
Beam pipe
(VTX LumiCal)
Barrel(7)
Endcap(3)
Yoke
(Muon)
HCAL
ECAL
(OTK)
MDI(1)
ACC component
Paraffin

## Slide 5: Introduction
2. Detector layers and dimensions:
Further optimization and improvement are needed
Overall dimension :
length : 11,950 mm
Height : 10,370 mm

## Slide 6: Introduction
Total weight :
≈ 5,150 t
Yoke ≈ 2,960 t
(Barrel: 1560 t Endcap: 700 X 2 t)
Magnet ≈ 290 t
HCAL ≈ 1,660 t
(Barrel: 960 t Endcap: 350 X 2 t)
……

## Slide 7: Introduction
3. Layout of the installation scheme with a “Pre-assembly point“ :
Installation starts at the
Pre-assembly point
Main width : 31,500 mm
Length : 55,500 mm
Beam-tuning experiments and detector installation
can be carried out in parallel

## Slide 8: Requirements
1. Installation clearance and accuracy :
Profile Tolerance(mm) |  | installation accuracy(mm) |  | positioning accuracy Coaxiality(mm)
 |  | Collimation accuracy (mm) | GAP (mm) | 
Yoke | ± 1 | < 1 |  | ±0.5
Magnet | Outer: 0 to -5, inner: 0 to +5 | < 2 | 10 | ± 1
HCAL | Outer: 0 to -5, inner: 0 t0 +5 | ± 2 | 10 | ± 0.5
ECAL | Outer: 0 to -5, Inner: 0 t0 +5 | ± 2 | 10 | ± 0.5
TPC | Outer: 0 to -2, Inner: 0 t0 +2 | ± 1 | 5 | ± 0.1
ITK | Outer: 0 to -2, Inner: 0 t0 +2 | ± 1 | 5 | ± 0.1
Beampipe | Outer: 0 to -0.3, Inner: 0 t0 +0.3 | ± 0.5 | 2 | ± 0.1
Minimum gap principle :
As small as possible
Note :
1. The deformation during the installation procedures of the sub-detector must meet the gap requirements.
2. The data in the table will be continuously to be optimized as the design evolves.

## Slide 9: Requirements
Connection design :
Barrel Yoke : Fixed on the ground Base
Magnet : Fixed on the Barrel Yoke
Barrel HCAL : Fixed on the Barrel Yoke
Barrel ECAL : Fixed on the Barrel HCAL
TPC+OTK : Fixed on the Barrel ECAL
ITK : Fixed on the TPC
Beampipe(Vertex and LumiCal) : Fixed on the ITK
End-cap ECAL+OTK : Fixed on the Barrel HCAL
End-cap HCAL : Fixed on the Barrel HCAL
(Auxiliary ring or Flange)
End Yoke : Fixed on the ground Base
1. The connection structure should be proximity
2. The connection structure should be adjustable (Remote automatic)
Base

## Slide 10: Requirements
Consists of 4 sections :
Detection coverage: 8.1 ° (cosq=0.99)
(Before ECAL)
(After ECAL)
ECAL : 700 X 700 mm
HCAL : Ø800 mm
Yoke : Ø1100 mm
MDI boundary
Conical hole and stepped holes are
reserved for accelerators

## Slide 11: Technical Challenges
1. Self-weight deformation VS installation clearance
Requirements :
GAP between HCAL and Magnet : 10 mm
GAP between HCAL and ECAL : 10 mm
Self-weight deformation :
18.8 mm (> 10 mm)
In the mechanical design process, we are facing several technical challenges:
Key :
Deformation must be controlled
by the mechanical structure design
How to
Handle Deformation ?
for HCAL
HCAL deformation calculation results
HCAL Structure

## Slide 12: Technical Challenges
In the mechanical design process, we are facing several technical challenges:
Pillow seals may be used for remote vacuum connections automatically.
2. Vacuum sealed Connection between Accelerator component and the Be beampipe
This connection
cannot be operated
using conventional methods
Technical challenge :
leak rate : 2.66 X 10 -11 Pa *m3 /s
Further improvement is needed in pillow seals technology
Accelerator
MDI component
Beampipe

## Slide 13: Overall Installation Plan
1. Installation location :
Pre-assembly point
Advantage : Beam-tuning experiments and detector installation can be carried out in parallel
with the accelerator installation and commissionning
2. Installation design :
● Installation and disassembly processes are reversible
● Installation rails will be kept permanently
Purpose: To facilitate the maintenance and replacement of the detectors
Follow three principles ：

## Slide 14: Overall Installation Plan
Collision point
robotic arm
Overhead travelling crane
3. Installation procedures:
Installation should be designed to allow the use of robotic arms
If Possible
Installations will be easily through a combination of
robotic arms and two overhead cranes.
Design principles :
1. Minimal Tooling
2. Simplified Operation

## Slide 15: Detailed Installation Design
Detailed installation design:
1. Reliability and safety assessment of the detector integration and their connection structures
(FEA --- stress and deformation)
2. Overall installation procedures
3. Detailed Installation procedures
4. Modular lifting and lifting of integral components

## Slide 16: Detailed installation Design
1. Overall reliability and safety assessment
Deformation : ≈ 0.9 mm
Stress : ≈ 76 MPa
Barrel supports
End Support
Drawing of the Endcap and Barrel support
Conclusion :
Meet requirement
(< 1 mm)
Yoke : 1560 t
Deformation of yoke
without detectors
Two end flanges
and
barrel supports
can reduce the deformation

## Slide 17: Detailed installation Design
1. Overall reliability and safety assessment
Yoke : 1560 t
Magnet : ≈ 290 t
HCAL : ≈ 1660 t
(Barrel: 960 t End: 350 X 2 t)
Deformation of the yoke
in the presence of sub-detectors
Load
1950 t
Other lighter components
are ignored
deformation of the Yoke
Deformation : 1.07 mm
It’s safe
Deformation within requirement
Deformation ≈ 0.9 mm

## Slide 18: Detailed Installation Design
2. Overall installation procedures
Note :
Installation guide rails is the benchmark,
and must be pre-aligned with the yoke
Barrel Yoke
General installation drawing
The main procedures are as follows :
1. In the ground hall
Complete the assembly work of each sub-detector, including electronics, etc.
2. Transport through the shaft
Each sub-detector is lifted into the underground experimental hall through the vertical shaft one by one
3. In the underground experimental hall ---
Assemble each sub detector on the guide rails and push them into the yoke in sequence
most important part of the installation
Installation guide rails

## Slide 19: Detailed Installation Design
Yoke
Magnet
HCAL
ECAL
TPC(OTK)
End ECAL(OTK)
ITK
End HCAL
ACC Component
Step 1 Install the barrel sub-detector first, in the following order :
Yoke, Magnet, HCAL, ECAL, TPC(OTK), ITK, Beampipe(Vertex)
Step 2 Install the endcap sub-detectors, in the following order :
End ECAL(OTK), End HCAL, End Yoke
Beampipe
(Vertex)
Installation sequence of detectors(As shown in the following exploded view) :
2. Overall installation procedures

## Slide 20: Detailed Installation Design
3. Detailed Installation procedures
Step 1 Alternating installation : Yoke and Magnet (2) --- Barrel Detectors
Step 2 Core shaft installation : Barrel HCAL and Barrel ECAL (2) --- Barrel Detectors
Step 3 Cantilever installation : TPC(OTK) ITK Beampipe(Vertex + LumiCal) (3) --- Barrel Detectors
End HCAL and End ECAL (2) --- End Detectors
Step 4 Lifting Installation : Yoke --- End Detectors
Step 5 Move the detectors from the Pre-assembly point to the Collision point
Push the accelerator vacuum component into the center of the detector and connect it with the Be beampipe

## Slide 21: Detailed Installation Design
Step 1 Alternating installation : Yoke and Magnet (2) --- Barrel Detectors
Method :
‘zero-tool’ assembly
Advantage :
No redundant tooling, reduces installation time
Install Yoke and Magnet (2)
This is an efficient installation design
(‘zero-tool’ achieves the installation of two detectors)
3. Detailed Installation procedures
Yoke and Magnet
Yoke
Magnet

## Slide 22: Detailed Installation Design
Step 2 Core shaft method installation : HCAL and ECAL (2) --- Barrel Detectors
Core shaft method installation of HCAL
Clearance requirement : 10 mm
Installation Method :
1. Place HCAL (or ECAL) on the core shaft
2. Move the HCAL(or ECAL) using external guide rails
3. detailed Installation procedures
There is no space for guide rails
External Guide rails

## Slide 23: Detailed Installation Design
Step 2 Core shaft method installation : HCAL and ECAL (2) --- Barrel Detectors
Load :
1. Self-weight
2. 1,000 tons HCAL
(ECAL 150 tons)
Result :
Max Deformation ≈ 3.9 mm
< 10 mm (Gap)
Hight : 2,000 mm
Width : 2,000 mm
Length : 27,300 mm
Design of the core shaft:
Short core shaft
Middle core shaft
Long core shaft
Adjustable base
Conclusion :
Meet installation requirement
For HCAL and ECAL
Constraints :
Fixed at both ends
3. detailed Installation procedures

## Slide 24: Detailed Installation Design
Install Barrel HCAL
3. Detailed Installation procedures
Method :
Assembled in the same way as the yoke
Step 2 Core shaft method installation : HCAL and ECAL (2) --- Barrel Detectors
Barrel HCAL
adjust
Adjustable base
Barrel HCAL
Connection structure
HCAL rings
Coaxial adjustment

## Slide 25: Overall Installation Design
Step 2 Core shaft method installation : HCAL and Barrel ECAL (2) --- Barrel Detectors
L-shaped
End Ring
How to
Handle Deformation ?
For HCAL
Deformation : 3.3 mm
Further optimization can be implemented to achieve smaller deformation
3. Detailed Installation procedures
Deformation : 18.8 mm
The animation has given
the solution!
Just two auxiliary rings

## Slide 26: Detailed Installation Design
Install Barrel ECAL
3. Detailed Installation procedures
Assembly of Core shaft :
Assembled in the same way as the HCAL
Step 2 Core shaft method installation : HCAL and ECAL (2) --- Barrel Detectors
Installation Steps :
1. Lift into the hall from the vertical shaft
2. Connected to the core shaft
3. Move ……

## Slide 27: Detailed Installation Design
Step 3 Cantilever method installation : TPC(OTK) ITK Beampipe(Vertex + LumiCal) (3) --- Barrel Detectors
Install TPC(OTK) and ITK (2)
3. detailed Installation procedures
Installation Steps :
1. Lift into the hall from the vertical shaft
2. Connected to the core shaft
3. Move ……
Deformations meet GAP requirements (< 5 mm)
TPC Deformation : 1.6 mm
ITK Deformation : 1.4 mm
ITK
TPC
Installing deformation simulation

## Slide 28: Detailed Installation Design
Install Beampipe(Vertex + LumiCal)
3. detailed Installation procedures
Step 3 Cantilever method installation : TPC(OTK) ITK Beampipe(Vertex + LumiCal) (3) --- Barrel Detectors
Deformation meet GAP requirement (< 2 mm)
Deformation : 0.9 mm
Installation Steps :
1. Lift into the hall from the vertical shaft
2. Connected to the core shaft
3. Move ……
Beampipe
Installing deformation simulation

## Slide 29: Detailed Installation Design
Step 4 Cantilever method installation : ECAL(OTK) HCAL --- End (2) --- End Detectors
Install ECAL(OTK) HCAL YOKE (3)
3. Detailed Installation procedures
Lifting Installation : Yoke --- End Detectors
Installation Steps :
1. Lift into the hall from the vertical shaft
2. Connected to the core shaft
3. Move ……

## Slide 30: Detailed Installation Design
Step 4 Installation : ECAL(OTK) HCAL Yoke --- End (3) --- End Detectors
3. Detailed Installation procedures
Connection and adjustment of HCAL
End HCAL
Connection Structure
In the Axial direction :
Two Adjustable Pad Irons
Circumferential direction :
Eight pairs
Connection :
Fixed to the HCAL rings
End HCAL
adjust
Hydraulic adjustment

## Slide 31: Detailed Installation Design
Step 5 Move the Detectors from the Pre-assembly point to the Collision point
Push the accelerator vacuum component into the center of the detector and connect it to the Be beampipe
1. This is a conceptual installation design
2. We will continue to optimize and improve the design in the future
Design parameters of hydraulic cylinder :
Move distance : 16,500 mm
Hydraulic cylinder movement span: ≈ 2.1 m
Hydraulic cylinder thrust : 50 t (> 30 t)
(hydrostatic guide rail 6000*0.005 = 30 t)
3. Detailed Installation procedures
Installation Summary :

## Slide 32: Detailed Installation Design
4. Modular lifting and lifting of integral components : (relate to the design of the vertical shaft and the hoists)
Magnet
ECAL
TPC+OTK
ITK
Beampipe
End - ECAL
End - HCAL
Yoke
End Yoke
HCAL
heaviest single module
≈ 350 t
Largest single size
9050 L X Ф 8470
Modular lifting (3)
lifting of integral (7)

## Slide 33: Our Team
IHEP (5)
Design companies
Zhejiang University Affiliated Company
Manufacturing companies
CITIC Heavy Industry
Universities
Hunan University
University of South China
Southwest Jiaotong University
Students (3)
Calculation team
Design team
Future plan:
1. Allocate more mechanical engineers, including those at JUNO now
2. Seeking cooperation partners in special fields
3. Seek international cooperation
1. IHEP mechanical engineers as the core for the design and optimization
2. Use as much possible outside resources

## Slide 34: Summary and Working Plan
1. The overall concept of the installation scheme has been completed
2. The connection structure of the Barrel HCAL and END HCAL are designed,
and they can be remotely and automatically adjusted
3. The connection structure for the other sub-detectors has been designed,
but is difficult to operate and needs to be optimized
Summary

## Slide 35: Summary and Working Plan
Working plan
1. Optimization and refinement of existing installation programmes
2. Refine the connection design of sub detectors
3. Optimize the layout of the underground experimental hall and its auxiliary hall
4. Start planning the layout design of the ground hall

## Slide 36
Thank you for your attention!
Aug. 7th, 2024, CEPC Detector Ref-TDR Review