## Slide 1: IDRC review report – electronics system related
Comments from IDRC
  Moving to a triggered readout scheme is listed as a backup plan, however it is unlikely that this would be viable once the project is well underway due to the impact on the FEE-ASIC designs as the backend is radically different. (related to R.2)
  By far the highest risk in the electronics is designing and delivering the 6 FEE-ASICs needed. For the 6 FEE-ASICs needed to readout the detector subsystems, there is significant effort needed. (related to R.1)
  There are design teams already working on 2 of the chips (for VTX and TPC detectors) and another has been identified for the ITK.
    Not exactly. Design teams are also assigned to OTK and SiPM (for ECAL+HCAL+Muon). Principle ASIC schemes & readout schemes were prepared. Due to the short of time in the review, not much details were discussed. Supplement materials can be prepared further.
  It is planned that most chips would share the same technology node (55 nm) and possibly share some blocks, which is very efficient but not so easy in practice.
    Agreed, but not exactly. Technology will be chosen based on the most suitable case. Some are unified, for OTK, SiPM, TaoTie, Chitu, KinWoo. Others are different, for VTK, BaSha.

## Slide 2: IDRC review report – electronics system related
Comments from IDRC
  The FE-ASIC progress should be closely monitored by the electronics coordinators. …. The timeline and development path should be clearly specified (number of intermediate prototypes, variants…) (related to R.1)
  The development of these common chips by a strong central group is a good choice. However, it’s a heavy load and the manpower needed for full verification and testing should not be underestimated. The manpower absorbed by this common task may deprive other developments, in particular for the FE ASICs. If all the chips need to be developed in China (to be discussed with management), the resources are probably insufficient, especially if they are distributed over several labs. In any case a strong central facility (like CERN-MIC does for LHC) is essential. Otherwise look at existing chips and whether they could be adapted to CEPC.
    Agreed, and it is the idea. On the one hand, IHEP will be THE central facility to develop the ASIC, on the other hand, actually design power has been allocated to each FE ASIC (will be listed in the supplement file).
    We have also looked at existing chips. One candidate is the SiPM ASIC for CAL. However it is developed by a company (the leader formerly has the background of HEP), the cost is not possible for such a large facility of CEPC. Thus it also has to be design by ourselves.
    We also warmly welcome international collaborators for the joint effort of ASIC development

## Slide 3: IDRC review report – electronics system related
Comments from IDRC
  The DC-DC converter is at an early stage. The GaN transistor has been selected, though needs testing for radiation tolerance. The switching frequency of the design is currently 5MHz, but the group is investigating moving to a higher frequency to improve the conversion efficiency. The converter circuitry itself is an established design. The parallel power scheme baseline plan is low risk, but serial powering has benefits if it can be used. The team should monitor developments elsewhere in case progress makes a serial scheme viable.
    Fully agreed. We will keep pace on R&D of the serial powering scheme.
  The wireless data transmission option is a backup plan, however it is not a low-risk backup. Significant R&D remains in miniaturizing and shielding, which is envisioned being driven by an industrial partner. … . Use inside the detector for readout of, eg, the silicon system would also require development of shielding and significant testing of the level of noise pickup the transmitters might induce in the detector elements. However, the wireless readout development should not take resources from the baseline electronics effort.
    Agreed. The R&D resources will be independent from the baseline effort.

## Slide 4: IDRC review report – electronics system related
Recommendations from IDRC
  R.1：Establish the timeline for all the FE ASICs development for all the sub-detectors and their state of maturity.
  R.2：Establish early enough the readout scheme (triggerless) so that no efforts are wasted on developments that will not be retained, chips unlikely to accommodate both R/O schemes.
    Agreed and it is almost established. We are waiting for the final report from the MDI background rate to finalized the electronics schemes.
  R.3：For the triggerless readout, show the maximum rates that can be handled, the safety margin that is included and what happens if the occupancy gets higher. What throttle scheme can be used?
    The maximum rate were currently calculated based on MDI effort, and were summarized in the table. In the supplement files, it can be seen that for most sub-detector, data link are at relatively low load of the data rate. At the meanwhile, only one fiber is used for each module while the maximum possibility is 4 fibers. The occupancy variations is already considered in FE-ASIC, as they are all zero-suppressed (or event-driven).
    The most/only risky part is VTX FE. As the current data rate is already 1~2Gbps per RSU. It is not sure if the cooling capability is enough for the current stitching scheme. We will keep eyes on it while the R&D is ongoing. Once it is proved to be problematic, fast trigger will be added to the VTX detector.

## Slide 5: Status of FE & common ASIC
Name | Application | Functional | Maturity | Comment | Similar chips
ChiTu（赤兔） | Common Elec | Data Link | 2~3 | Key blocks ready, protocol TBD | lpGBT
KinWoo（金乌） | Common Elec | Optical | 3~4 | Real module verified | VTRx
TaoTie（饕餮） | Common Elec | Data Aggregation | 2 | Although needs scheme, but a pure digital ASIC, low risk | GBTx、HCC
BaSha（霸下） | Common Elec | DC-DC | 2 | Initial stage, but the scheme are conventional and low risk. GaN has been preliminarily verified. Inductors to be selected and tested for Magnet. | bPolx，FEAST
Taichu（太初） | VTX | VTX-Stitching | 2~3 | Single chip fully verified. Will be focused on stitching issues | ALICE-ITS3
TEPIX-TPC | TPC | Pixel TPC | 3~4 | TPC module to be beam-tested. Further optimization is ongoing | Gridpix（Timepix3）
ITK-B |  |  | ? |  | 
ITK-E |  |  | ? |  | 
OTK-ROC | OTK | LGAD-TOF | 2 | With preliminary scheme, while TDC & similar FE is already tapedout and wait for test. Cd & power to be optimized for a real design. | ALTIROC
SiPM-ROC | SiPM ASIC | ECAL, HCAL, Muon | 2~3 | Schemes verified in previous chips. No show stopper for all key blocks. Waiting for the detector finalization & device selection to start the design | HGCROC、SPIROC
Maturity: 1：from scratch; 2: initial design proposed, R&D needed; 3: with experience or previous design, no show stopper; 4：prototyped, further optimization required; 5：verified for the real detector.

## Slide 6: Timeline for all the FE ASICs - VTX
2025：
  Taichu debugging and finalization
  Stitching design on TJ180, based on Taichu’s previous design, for low cost
  Bending chip electrical test based on Taichu3-most2, at single chip level.
2026：
  Taichu-Stitching-180 chip test
  TJ65 design kit finalization (expected)
  Taichu4 prototype design on TJ65 for process evaluation (MPW or combined-engineering), at single chip level
2027：
  Taichu-Stitching-180 mechanical prototype and test
  TJ65 chip prototype test.
2028~2029：
  TJ65-stitching based on previous experience of TJ180-stitching & TJ65 prototype
Comment:
  Stitching on TJ65 currently is not cost-effective and high risk, given that the design kit is not finalized. Two parallel design to verify the final scheme: Stitching on TJ180; prototype on TJ65

## Slide 7: Timeline for all the FE ASICs - TPC
2025：
  Beamtest with TPC module based on current TEPIX chip.
  Detector optimization for a final pixel size.
2026：
  Chip optimization with the final detector design
  Chip test
2027：
  Prototype with the final detector & final chip
  Beamtest with the final module

## Slide 8: Timeline for all the FE ASICs – SiPM FE for CAL & Muon
2024：
  Detector’s final requirements to FE
  SiPM’s final selection for FE design
2025：
  The first version of SiPM ASIC: with main analog performance and basic digital functionality
  Test & verification of the SiPM ASIC 1st with main performance
If mostly verified
2026：
  Chip debugging & optimization (2nd MPW)
2027：
  1st Engineering
  Prototype for the 7000chn HCAL
Comment:
  Rough price of the existing chip is too high for a mass production prototype
  Self-R&D is necessary for the final CEPC ECAL
If critical issues found
2026：
  Contact for existing chip (minor modification might needed); find for (international) collaboration
2027：
  7000chn HCAL prototype based on xxx chip
2026~2029：
  SiPM ASIC design with 2 MPW + 1~2 engineering run, aiming for real CEPC CAL

## Slide 9: Timeline for all the FE ASICs - OTK
For OTK prototype as the recent plan
  2025：
    First chip prototype test for the FASTPMT ASIC (FPMROC) (from other project with similar requirement); Chip debugging & optimization
  2026：
    FASTPMT ASIC finalization
  2027：
    Co-test by FASTPMT ASIC with AC-LGAD sensor prototype
For real CEPC OTK FE-ASIC
  2025：
    Detector Cd and size optimization & finalization
    Specification and schemes review for OTK FE
  2026~2029
    OTK FE ASIC design with 2 MPW + 1~2 engineering run
Comment:
  OTK detector R&D can be guaranteed by the previous & ongoing FASTPMT ASIC
  Real CEPC OTK needs detector finalization, which needs time
  Design power can be shifted in timeline between OTK & SiPM

## Slide 10: Timeline for all the FE ASICs – common ASIC
Irradiation test
GaN Selection
DC-DC Controller schematic design
DC-DC module performance from simulation
2024.10
2024.11
2025.1
2025.3
Power & DC-DC Module
DC-DC BaSha module prototype
2026.1
Specification finalization
Protocol define
ChiTu Chip prototype
2024.8
2024.10
2027.6
Data Link
Overall Electronics system
Specification & background finalization
2024.8
Sub-Det readout Elec scheme finalization
2024.9
Overall Electronics scheme finalization
2024.10
Elec TDR Draft1
Elec cost Draft1
Ref-TDR release
2025.6
2024.12
2025.3