## Slide 1: Schedule of the MDI installation
Xiaoping Jing, Mingyi Dong
2024.12.17

## Slide 2
Based on discussions with the accelerator systems, a schedule for MDI installation was updated
Due to noise issues, we have postponed the recovery work, and the recovery on the east side will start on December 24th
The schedule may be slightly adjusted according to the actual implementation situation

## Slide 3: Schedule (east side)
 | Detailed tasks | date
1 | Deal with CGEM cables to ensure they do not interfere with the installation of the EEMC | Dec. 23/24
2 | (1) Remove current operation platform on east side (2) Push the east EEMC back to its original position (3) Disconnect the east EEMC from the support structure | Dec. 24-25
3 | Fix CGEM cables on EEMC support structure to ensure they do not interfere with installation of beam pipe | Dec.26
4 | Install the support tools for beam pipe installation | Dec.27
5 | Install beam pipe | Dec.28-29
6 | Remove the support tools for beam pipe installation | Dec.29
7 | Laser measurement and alignment of beam pipe | Dec.30
8 | Install shielding plates for CGEM | Dec.31
9 | Deal with CGEM cables to ensure they do not interfere with pulling out of east EEMC | Jan.2

## Slide 4: Schedule (east side)
 | Detailed tasks | date
10 | Pull out east EEMC again | Jan3-4
11 | Deal with CGEM cables to ensure they do not interfere with installation of SCQ | Jan.4-5
12 | Installation of SCQ and related work (some jobs are not in the IP region) | Jan.6- Jan.9
13 | Power on CGEM and MDC to check the connection | Jan.10
14 | Laser measurement of SCQ | Jan.11-13
15 | Fix cables of beam pipe and CGEM on the support structure of SCQ and other magnets | Jan.13-15
16 | (1) Remove the operation platform (2) Push the east EEMC back to its original position and remove the mechanical tools | Jan.15-16
17 | Other recovery work on east side | Jan.16-Feb.8

## Slide 5: Schedule (west side)
 | Detailed tasks | date
1 | Install CGEM shielding plate on the west side | Jan.3
2 | Deal with CGEM cables to ensure they do not interfere with the installation of SCQ | Jan.4
3 | Installation of SCQ and related work (some jobs are not in the IP region) | Jan.6- Jan.9
4 | Power on CGEM and MDC to check the connection | Jan.10
5 | Laser measurement of SCQ | Jan.11-13
6 | Fix cables of beam pipe and CGEM on the support structure of SCQ and other magnets | Jan.13-15
7 | Remove the operation platform Push the east EEMC back to its original position and remove the mechanical tools | Jan.16-17
8 | Other recovery work on west side | Jan.17-Feb.11