## Slide 1: Progress and Plan
Mingyi Dong
2025.01.07

## Slide 2: progress in last week
 | Tasks | date | person in charge | Status
1 | Install shielding plates for CGEM | Dec.31, move to the beginning of Jan.(before Jan.9) | Italy team | Not yet，move to Jan.7 or 8
2 | Deal with CGEM cables to ensure they do not interfere with removing big leg and pushing back EEMC on west side | Jan.6 | Italy team, IHEP | done
3 | Deal with CGEM cables to ensure they do not interfere with pulling out of EEMC | Jan.3(east side), 6(west side) | Italy team | done
4 | Pull out east EEMC | Jan.3 | IHEP | done
 | Push west EEMC to its original position and pull it out again | Jan.6 | IHEP | done
5 | Deal with CGEM cables to ensure they do not interfere with installation of SCQ | Jan.4 | Italy team | Not yet
6 | CGEM tests , Open the shielding board and solve the problem of several cables being disconnected from the patch cards | Dec.31, Jan.5 (east side) Jan.7 (west side) | Italy team IHEP | ongoing
7 | Preparation of Installation of the SCQs on east and west sides | Jan.2-6 | IHEP | done

## Slide 3: Plan for next week
 | Detailed tasks | date | person in charge
1 | Check connection of CGEM | Jan.7-8 | Italy team
2 | Recover installation of the final shielding plates | Jan.7-8 | IHEP, Italy team
3 | Install the final shielding plates for CGEM | Jan.7-8 | IHEP, Italy team
4 | Deal with CGEM cables to ensure they do not interfere with installation of SCQ | Jan.7-8 | Italy team
5 | SCQs will be installed in place on both sides | West side on Jan.9 East side on Jan.10 | IHEP
6 | Power on CGEM and MDC to check the connection | Jan.10, 11 | IHEP, Italy team