## Slide 1: Progress and Plan
Mingyi Dong
2025.01.21

## Slide 2: Progress
Due to discharge issues on layer3 and huge noise issues on Layer1, gg. asked one week delay in installation start-up of the SCQ (from Jan.9 to Jan.16)
Due to new discharge issues on layer3 found on Jan.16 morning, gg. asked one more day for solving the discharge problem (Jan.16).
The installation of the SCQ started on Jan.17

## Slide 3: progress in last week
 | Tasks | date | person in charge | Status
1 | Testing to resolve the problems of CGEM L1 noise and L3 discharge New discharged was found and solved on Jan 16 | Jan.8-16 | Italy team IHEP | done
2 | Installation of final shielding plates for both CGEM and MDC | Jan.15-16 | IHEP | done
3 | Installation of small shielding plate for CGEM | Jan.16 | IHEP Italy team | done
4 | Cosmic ray checks and tests of MDC and CGEM | Jan.8-16 | IHEP Italy team | done
5 | Installation of SCQ vacuum pipe on east side Installation of SCQ vacuum pipe on west sides and leakage check | Jan.17 Jan.18 | IHEP | done
6 | Rearranged CGEM cables on both sides to ensure they do not interfere with installation of SCQ | Jan.18(east side), Jan19 (west side) | Italy team IHEP | done
7 | Preparation of Installation of the SCQs on east and west sides (cutting small pieces from the SCQ, laser measurement of the step parts to make sure the space is ok for SCQ insertion) | Jan.20 | IHEP | done

## Slide 4: Plan for next week
 | Detailed tasks | date | person in charge
1 | Insertion of SCQ on both sides Power on CGEM and MDC to check the connection after Insertion of SCQ | Jan.21-22 | IHEP, Italy team
2 | Cables and pipes connection of SCQ and vacuum pipes on both sides | Jan.23 | IHEP, Italy team
3 | Water pressure tests and powering on test for SCQ and vacuum pipes on both sides | Jan.24 | IHEP, Italy team
4 | Fix CGEM cables on the support structure of SCQ | Jan.25-28 | Italy team, IHEP,
5 | CGEM DAQ debugging | Jan.25- | IHEP, Italy team

## Slide 5: Dedicated meetings on noise issues
On Jan. 11, the second dedicated meeting on noise issues was organized. 10 experts attended the meeting.
The suggestions are as follow
  Further improve the shielding of the first step, especially the gap between the shielding layer and the flange2 of MDC
  Shield the HV patch cards of CGEM

## Slide 6: Noise tests and results
The following measures and tests have been done to reduce the noise based on the suggestions made at the meeting.
  (1) Added a shielding layer on the HV patch card of CGEM.
  (2) Further improved the shielding of the first step of MDC with copper foils, especially the gap between the shielding layer and MDC flange2
The experimental results are as follows:
  (1)The baseline noise was further reduced. When CGEM is powered off, there is no noise in MDC.
  (2)But there was no significant change in the noise related to CGEM. When CGEM is powered on, there will be big noise in the MDC step section.
  (3)Additional grounding tests were conducted, but the noise remained almost unchanged.
  (4)after all shielding plates were installed, the noise decreased a bit.
Cosmic-ray tests with trigger signals only coming from MDC will be done next week to evaluate the impact of noise on triggering