## Slide 1: Progress and Plan
Mingyi Dong
2025.02.11

## Slide 2: progress in last week
 | Tasks | date | person in charge | Status
1 | Insertion of the SCQ on east side | Jan.21 | IHEP | done
2 | Insertion of the SCQ on west side | Jan.22 | IHEP | done
3 | (1)Electronics connection check of CGEM and MDC after the installation of SCQ (2)Leakage check of beam pipe cooling pipe | Jan.23 | IHEP Italy team | done
4 | Fixed CGEM cables and beam pipe cables on the SCQ support structure (both sides) | Jan.24-31 | IHEP Italy team | done
5 | DAQ debugging | Jan.24-Feb.11 | IHEP Italy team | On going
6 | MDC cosmic-ray test with different T thresholds (80/110 -> 105/135 on Feb.4) | Jan.24-Feb.11 | IHEP | On going
7 | MDC Q noise tests | Feb.4 | IHEP | done

## Slide 3: progress in last week
 | Tasks | date | person in charge | Status
8 | Pushing the east EEMC to its original position Rearranging the cables of the dose sensors | Feb.5 | IHEP Italy team | done
9 | Pushing the west EEMC to its original position Rearranging the cables of the dose sensors Installation of Small angel Lum. detector on west side | Feb.6 | IHEP Italy team | done
10 | Removing the support structure of EEMC on east side Installation of the platform for magnets (Q1A, Q1B) on east side | Feb.7 | IHEP Italy team | done
11 | Installation of magnets (Q1A, Q1B) on east side Installation of the platform for magnets (Q1A, Q1B) on west side | Feb.8 | IHEP Italy team | done
12 | Removing the support structure of EEMC on west side Installation of magnets (Q1A, Q1B) on west side | Feb.10 | IHEP Italy team | On going

## Slide 4: Plan for next week
 | Detailed tasks | date | person in charge
1 | Rearrange the cables of EEMC and ETOF Cosmic-ray test | Feb.11-12 | IHEP
2 | Installation of shielding lead block to reduce the beam background |  | IHEP
3 | Close the door of the BESIII detector |  | IHEP, Italy team
4 | DAQ debugging |  | Italy team, IHEP
5 | Cosmic –ray test |  | Italy team, IHEP

## Slide 5: Issues
CGEM HV cable support structure should be partially cut off (both sides)
DAQ issues
Fast signal test (trigger, clock, check, full )