## Slide 1
Zhijun Liang (IHEP)
Hybrid status
Notes: 1

## Slide 2
Update in hybrid process flow
PI layer deposition for ALTIROC-A wafer is now after ASIC wafer probing
  9 ALTIROC-A wafers in IHEP/NCAP
    1 wafer UBMed and Diced for hybrids
    ASIC probing will be performed for remaining 8 wafers
  9 ALTIROC-A wafers in IJClab
    1 wafer diced for ASIC study (distributed a few chips to other sites)
    1 wafer under ASIC probing (died, take too long )
    1 new wafer for ASIC probing ( )
    6 wafer from recent batch
  2 ALTIROC-A wafer on-hold in TSMC

## Slide 3
Thick Sensor wafers UBM
IHEP-IME sensor UBM is managed by sensor group
  Contract with IME is to provide UBMed diced LGAD
  Status: pre-production Thick wafers (more detailed in sensor report tomorrow)
  2 LGAD wafer picking is done (~60 LGAD)
  10 LGAD wafers UBMed and diced, picking dies (200~300 LGAD, this week)
USTC-IME sensor UBM managed by module group
  6 wafers received in middle of Dec 2024. (150~200 LGAD, this week)
  One wafer reserved for USTC sensor probing
  UBM ready by the end of this week
  Dicing starting from next week, ready in ~10 days
80+ ASIC (unprobed )

## Slide 4: Thick Sensor wafers UBM
2 LGAD thick sensor picking is done