## Slide 1: CSNS & CSNS-II beam instr. Feb. 17, 2025 week Mar. 27, 2025
R. Yang

## Slide 2: Tasks in 2025
CSNS-II:
  2025 installations
  2027 key hardwares
CSNS maintain
  New interface (pyQt)
Isotope
  50 Hz DAQ
Photoinjector
  Dedicated discussion

## Slide 3: Installation & maintenance in 2025 summer(7.15-10.1)
LRBT-Inj. removal & installation (stauts?)
  BPM, CT, BLM, ECOL, SEM-grid, SCREEN
RCS BPM Re-mapping
R2BPM01 (Fabrication?)
Neutron Target MWS (TMWS-n) backup (Wishlist)
Gated IPM (Hurry up!)
LW-H0 (Hurry up!) , LW-2?
A list of the corresponding detectors being refurbished, removed or installed (F. Li, hurry up)

## Slide 4: Recent avitivities
R&D towards intermediate-pulse beam profile (WS, MWS)
TMWS gain uniformity measurement
LINAC DAQ upgrade (50 Hz)
Open discussion & meeting
  RCS BPM Maintainance & Calibration (M. Rehman, R. Qiu, Z. Xu)
  LW-v1 (12/02/2025), LW-H0 (17/03/2025), LW-optics (17/03/2025)
  Photoinjector instr. discussion (18/02/2025)
  Gated IPM design (10/03/2025)
  R2BPM01 (M. Rehman)
  icBLM+CFC (26/02/2025, 27/03/2025)
  CNT wire experiments & remote discussion (14/02/2025)
  LRBT FCT (17/03/2025 week)
  BSM testbench summary (Dr. W. Huang)

## Slide 5: To be checked
Injection
  BCT (Mechanical minor modification by Nie, R. Qiu: preparing electronics)
  MWS (CNT rope heat-test chamber in vacu.; reused signal cables; R. Qiu: to check current electronics 5X max. signal; RuiYang: check 41-ch. cable)
  E-Col (Machining, F. Li/R.Qiu: one coax. cable + amplifier)
  BLM (IC & analog electronics & DC PS & HV PS & connector & ADC module ok, F. Li: DAQ)
  Rectangular BPM (draws ok, ordering components, Rehman: lead time: <6.15)
  Screen (review tomorrow; Z. Xu: check mover control)
RABT
  d290 mm BPM (R2BPM01)

## Slide 6: Key hardware
DCCT
  Prepare kickoff meeting, pls (W. Huang: after mag. measurements of torus)
BSM
  Status
  A tentative schedule towards 2025 installation to beamline (regular discussion?)
RCS BPM electronics
  FEC beam test results (R. Qiu: 2nd version discussion meeting)
  Next version (PXIe, prepare for discussion)
LINAC BLM
  icBLM & electronics (specification, survey of ESS case)
  DAQ system (not very urgent…)
  regular project meeting

## Slide 7: Key hardwares
LW prototype
  beam experiments (2 times,  fine scan)
  Chamber update (done)
  H0 detection (LGAD sensor preparation)
RCS IPM
  MCP test chamber (H2 gas safety review, prepare exp. room near D2)
  Pulsed PS (lead time postponed to April, 2025)
  EMI test in lab/RCS/RTBT (waiting for updates)
  Amplifier v3 modification (Feb. 2025, R. Qiu)
BxB feedback
  Simulation effort
  try signal acquisition on mTCA
  check amplifier (done)

## Slide 8: Meeting and Discussions in April
RCS BPM electronics design (R. Qiu, Z. Xu)
RCS BPM measurement accuracy discussion (28/03/2025)
LRBT FCT re-location (F. Li, Dr. W. Huang)
BSM progress, status and new requirements (Dr. W. Huang)
Injection MWS and CNT wire (Z. Lu)
LINAC 50 Hz summary (Z. Xu, F. Li)
LW experiments and new design (R. Yang)

## Slide 9: Procurements (import) in 2025
Libera Single-pass (CSNS-II, 1)
Cividec C1-HV (OP, x2)
GSPS digitizer (CSNS-II, 1)
CAEN pico4 (CSNS OP, x1)
FCT (CSNS-II, 2-4)

## Slide 10: Misc
AI-associated scientific researches
IBIC2024 opened abstract submission (Feb. 10 – Apr. 30) HB2023 abstract submission (Apr. 2 – Jul 15) Information collection on IHEPdocs https://docs.ihep.ac.cn/link/AA754B89430AD6422DBE8F8BDCA56F3F55
Safety and cleanness of the lab. in A1 & D1
  A1-306: electronics, DAQ
  A1-310: detector, electronics, storage
  D1-ground floor: BPM calib., IPM, BSM, detector assemble/test
  D1-2nd floor: detector/optics
AoB