## Slide 1: CSNS & CSNS-II beam instr. Apr. 28 week
R. Yang

## Slide 2: CSNS instr. (2025)
Injection
  BCT (W. Huang: detector arrived, cal. tool ok; R. Qiu: preparing electronics, X2, processing)
  MWS (CNT wire, detector to be weld, mover, analog electronics)
  E-Col (fabricating, F. Li/R.Qiu: amplifier/filter(BW=100 kHz))
  BLM (ready)
  Rectangular BPM (electrodes CNC machining, lead time: <6.15)
  Screen (welded/check on-site, mover!)
RABT
  d290 mm BPM (R2BPM01): to be machined, lead time: July 2025

## Slide 3: CSNS instr.
RCS BPM
  Re-Mapping; CST simulations (w/ pipe); electronics (algorithm)
  New electronics (PXIe vs. mTCA, hurry!)
LINAC BLM
  icBLM & electronics (specification, survey of ESS case)
  DAQ system (BI+Control, designed)
  Discussion in early May
BSM
  Status: prepare discussion meeting (May 7, 2025)

## Slide 4: CSNS instr.
LW prototype
  Prototype-v1 succeeded, experiments almost finished
  Chamber update (done)
  H0 detection (LGAD sensor preparation) => review meeting
RCS IPM
  Experiments on the e-col. mode ( -> discussion meeting)
  Gated IPM test & commissioning in lab.
BxB feedback
  Simulation effort
  FPGA function programming
  Power amplifier specification & supplier

## Slide 5: Meeting and Discussions in April
RCS BPM electronics design (R. Qiu, Z. Xu, 23-24/04/2025)
RCS BPM measurement accuracy discussion (28/03/2025)
LRBT FCT re-location (F. Li, Dr. W. Huang)
BSM progress, status and new requirements (Dr. W. Huang)
Injection MWS and CNT wire (Z. Lu, 16/04/2025)
LINAC 50 Hz summary (Z. Xu, F. Li)
LW experiments and new design (R. Yang, 14/04/2025)
FPS: Monitor part
BxB Feedback discussion

## Slide 6: Others
CSNS Operation:
  user-friend GUI oriented to CSNS-II;
  necessary upgrade, e.g., WS mover control?
CSNS-II:
  in align with the CPM plan!
  BPM & BPM electronics!!
Others
  be ready for the Isotope project

## Slide 7: One major project one person for May 2025?
Zhihong Xu, LabView Linux (INJ MWS)
Ruiyang Qiu, Analog Front-end design (URGENT)
Lei Zeng, demo of <10 us response time of icBLM electronics
Fang Li, new GUI, Control&DAQ@Ions Source
Zhijun Lu, CNT wire experiments in lab.
M. Rehman, Gated IPM design & report

## Slide 8: IBIC2025