## Slide 1
Plan of the Electronic System
Wei Wei
On behalf of the CEPC Electronics study team
June. 3rd, 2026, CEPC Detector and Physics Plenary Meeting

## Slide 2: Feedback from IDRC
Key Achievements & Recognition
Structural Breakthrough:Successfully adopted a data streaming readout architecture. ASIC design, data rate handling, and safety margin implementation are all well managed.
Technological Maturity:Key ASIC modules have been successfully prototyped, demonstrating the team's strength and efficiency.
Comprehensive System:The electronics system description was recognized by the review committee as comprehensive and complete, laying a solid foundation for the project.
Recommendation Response & Actions
Responsibility & Verification
Clear leaders have been assigned for all key ASICs.
Independent verification is being implemented. More resources for verification will be considered to be find from the university for testing.
Risk & Supply Chain Management
Backup resources for key components (like FPGAs) are in place to mitigate supply chain risks.
System & Parallel Development
A verified common backplane prototype exists and will be optimized for future sub-detector R&D.
Documentation Improvement
The ASIC overview in the Ref-TDR has been restored and improved with a detailed table for better readability.
Core Future Work Directions
Power Optimization: Optimize power consumption at every design stage, ensuring all power usage is justified by performance requirements to improve energy efficiency.
Parallel Testing Strategy: Use "sister chips" to start detector testing in parallel with chip development, accelerating the R&D verification cycle.
Prototype Iteration: Proceed with system development to meet the needs of each sub-detector, creating a flexible and scalable hardware verification platform.

## Slide 3: Plan updates
The“new”chips：
  Tapeout with 2 MPWs（V0, V1), with channel functionality in current ver.
  Following exactly the TDR schedule for the development, no modification
    LATRIC(OTK)
    SIPAC(SiPM)
  Tapeout with 1 MPW, another in manufacture, bugs understood
    PAL (DC-DC convertor)
  Main chip in design, to be tapeout in July, delayed due to complexity
    FEDI (Data Interface)
    FEDA (Data Aggregation) and OAT (Opto- module) prototype version tapeout, to be tested

## Slide 4
GaN Selection
PAL func module prototype
Module on detector test
2024.11
2026.12
2027.12
Power & DC-DC
(PAL)
Rad-tol & Mag proof PAL prototype
2029.12
Protocol define
1st tapeout
Chip set
Rad-tol FEDI DataLink prototype
2024.10
2025.10
2029.12
Data Link
(FEDA, FEDI & OAT)
Overall Electronics system
Elec TDR Draft1
2024.12
2027.12
VTX STCH
(Taichu-Stitching)
Preliminary scheme for Stitching
TJ65 single chip design
TJ65 wafer-level
Stitching detector prototype
2024.12
2026.12
2029.12
Prototype beamtest
Chip Finalization
2025.6
2029.12
Preliminary scheme
AC-LGAD detector co-test
Chip Finalization & detector co-test
2024.12
2027.10
2029.12
Spec finalization & device selection
HCAL module prototype
2025.1
2027.12
2027.12
ECAL/HCAL/Muon
SiPM ASIC
(SIPAC)
OTK
AC-LGAD
(LATRIC)
PIX TPC
(TEPIX)
2029.12
Towards final CEPC detectors
Final Design Review
Production Readiness Review
2025.1
DC-DC Controller schematic design
2028.12
Rad enhancement & Inductor design
2026.12
FEDI & OAT func prototype
2027.12
FEDI & OAT on detector test
Rad enhancement & FEDA development
2028.12
Taichu-stitching-180 development
2025.1
1st design of wafer-level stitch onTJ180
2025.12
TJ65 single chip prototype
2027.12
wafer-level stitching mechanical prototype
Optimized Prototype beamtest
2027.12
2026.12
Chip optim for optimized TPC
2025.12
FPMROC prototype test (for FASTPMT)
OTK detector optimization
2026.6
ASIC-128chn
tapeout
2025.12
1st SiPM ASIC
test
2026.12
Existing chip based modification
SiPM ASIC optimization
Chip Finalization
Y
N
TJ65 design kit finalization
Scheme define
2025.1
1st tapeout
2025.4
1st tapeout
2025.4
1st tapeout
2025.4
FPMROC chip test (for FASTPMT)