## Slide 1: TPC/DC R&D status and planning
Mingyi Dong
On behalf of the working group
June 10， 2026

## Slide 2: Reminder: IDRC recommendations for TPC
Reassess the choice of 500 × 500 μm² pad size in combination with the T2K gas mixture, as this configuration appears suboptimal for dE/dx-based particle identification.
Extend the beam-induced background studies, incorporating recent improvements in simulation and mitigation methods to refine background estimates and design margins.
Conduct more detailed investigations of space-charge distortions, ensuring that correction strategies are validated for all expected running conditions.
Prototype ion backflow suppression techniques, independently of the selected solution (e.g., double mesh or graphene filter), to verify feasibility and performance.
Demonstrate experimentally the effectiveness of spark-protection measures for the readout electronics.
Evaluate CO₂ cooling as a potential alternative to water, taking advantage of its dielectric properties and ability to maintain constant-temperature heat removal without electrical risk.

## Slide 3: TPC R&D Planning and Status
Item | execution time | Status and planning
1. Test and validation of readout modules (double mesh Micromegas + high granularity pads) | 2026 | (1) Finished prototyping and testing of single-mesh Micromegas (2) The integration of readout module is almost finished (1) Finish readout module assembly and preliminary tests (2) Perform beam test of readout modules
2. Readout ASIC optimization (including spark-protection measures ) | 2026-2029 | (1)Discussed with Zhi Deng, we will firstly focus on the testing of current ASIC version (2)Recovered the readout testing system (1) Joint test of the readout ASIC and detector module (2) New version design of readout ASIC based on the test results (3) Investigation of other readout schemes
3. Prototype ion backflow suppression techniques, independently of the selected solution (e.g., double mesh or graphene filter), to verify feasibility and performance | double mesh : 2026-2027 Graphene: 2026-2029 | (1)Performed simulation of IBF suppression with double mesh. Further simulation study is needed. (1)Testing of IBF suppression with double mesh (2)Preparing for graphene testing in corporation with Shandong university

## Slide 4: TPC R&D planning and Status
Item | execution time | Status and planning
4. Pad size optimization in combination with the optimized gas mixture | 2026-2029 | (1)Simulation studies has been done to optimize the pad size. Truncated mean shows the optimal pad size is likely in the rage of 200-400 μm, deep learning gives much higher SP with smaller pad size Performance tests of the modules with different pad sizes based on the simulation results Gas mixture test and optimization
5. Further studies of beam-induced background (together with Haoyu) | 2026-2030 | (1) Minor updates (1) Continue to study beam-induced background and impact on the TPC (both Higgs and high lumi. Z)
6. More detailed investigations of space-charge distortions. Calibration and correction strategy studies | 2026-2030 | (1) Started investigation of calibration and correction strategy (1) Continue to study space-charge distortions (2) Investigate calibration and correction strategy
7. Evaluate CO₂ cooling as a potential alternative to water, preliminary design and FEA | 2026-2027 | (1)Discussed with mechanics experts, the study of CO₂ will performed together with tracker system. (1) Perform thermodynamic FEA (2) Propose a detailed design based on FEA

## Slide 5: DC R&D planning and Status
2026:
  Join the test beam at CERN (Just completed)
  Cluster counting analysis combined with tracking
  Study of reconstruction with Deep Learning
  Optimization of the readout electronics parameters based on the test results
2027:
  Beam test at BSRF or HEPS