## Slide 1: Preparing the SPS complex alignment for future LHC runs
Patrick Bestmann
IWAA 2014 IHEP, Beijing, China 13-17.10.2014

## Slide 2: Outline
  Introduction
  Long Shutdown 1
  Measurement and alignment strategy
  Planning
  Vertical alignment SPS ring
  Horizontal alignment of the SPS ring
  TI2 & TI8 Transfer lines
  TT10 Transfer line

## Slide 3: Introduction

## Slide 4: CERN LS1
Initially intended for the LHC consolidation
Start of LHC Injector Upgrade Project
  Working towards Higher Luminosity
  LHC injectors need to push their boundaries to deliver the needed beam quality
15 Month of SPS shutdown is the unique opportunity to improve the alignment in the whole complex

## Slide 5: Strategy
SPS ring Levelling + alignment 6 w
SPS Sextant 6 Realignment H+V 8 w
SPS Quads horizontal survey 6 w
SPS Quads horizontal alignment 4 w
SPS Dipole + intem. Alignement H+V 20 w
TI2 Transfer line survey and alignment 6 w
TI8 Transfer line survey and alignment 20 w
TT10 Transfer line survey and alignment 12 w
Change of Magnets / Upgrades and installation

## Slide 6: Planning
OBSOLETE

## Slide 7: SPS vertical profile
Measured and corrected every year
6.9km, DNA03 double run with1800 observations
LHC
Notes: LHC 40 m underneath
One single LGC adjustment for the whole ring
Datum fixed on the two deep references

## Slide 8: Sextant 6
Cumulated ground movements have build a sharp excursion in the vertical profile
Limiting aperture and performance of the machine

## Slide 9: Sextant 6 constraints
Jacks were at the end of the range
Exchange of PU Jacks and additional shimming
TI2 extraction in the center of excursion
Interconnects were kept closed
Restricts roll angle and transversal offsets
Delicate load transfer to jacks
Double actuator hydraulic
Independent adjustment of volume and pressure
Notes: 3,5mm smooting +10mm shimms
200m of Ti2 also fully realigned

## Slide 10: New handling equipment

## Slide 11: Strategy
3 Step approach to keep track
  Relative vertical displacements for focussing Quadrupoles
    Reference measurement
    Lifting with exchange of jacks and shims
    Realignment to new vertical, but initial horizontal position
  Alignment of defocussing quadrupoles using the focussing as reference
  Alignment of all intermediate components

## Slide 12: Strategy
SPS FoDo Lattice
MB
QF
QD
QF
QD
QD
MB
QD
QF
QF
MB
MB
MB
MB
MB
MB
MB
MB
MB
MB
MB
MB
MB
MB
MB
MB
MB
MB
MB
MB
MB
MB
Notes: SPS lattice is making things very straight forward
From a practical point of view very handy

## Slide 13: Calculation & Alignment
One single LGC adjustment for the whole ring
Datum fixed on the two deep references
Smooth curve approximation
Two batches of corrections for QF and QD magnets
Relative displacements with two control measurements

## Slide 14: Results
92 Quadrupole Magnets aligned

## Slide 15: SPS Horizontal profile
Wire offset measurements
Datum fixed on one Point with radial corridors for some straight sections

## Slide 16: Beam Based Alignment
Very final adjustments to Orbit
Corrector Magnets not strong enough at 450GeV
Measurements done by the operation team during each startup
Cumulated 40 volontary displacements
Change from Q26 to Q20 Optics
All displacements deleted during LS1
Two iterations done with 10 Magnets in V and 10 in Horizontal direction
Notes: Starting from 100GeV the correctors are not strong enough anymore.
The only way to correct the orbit is a physical displacement of the magnets.
Displacement of a quadrupole to introduce dipole component.

## Slide 17: Q20 Orbit
finished

## Slide 18: Transfer Lines TI2 & TI8
Geologically unstable
Full realignment of TI8 in both planes
Only Quadrupoles of TI2 in both planes
Strategy is basically the same as the one for the SPS or LHC
Notes: Quiete recent constructions

## Slide 19: TI2 Vertical Profile

## Slide 20: TI8 Vertical Profile

## Slide 21: TT10 Transfer line
Delivering beam from PS to SPS complex
Showed invert heave plus compression racks in the crown and tension/shear cracks at the level of the shoulder

## Slide 22: Measurements
Notes: Is it still moving?
Installation of monitoring profiles
It is stable since april 2013
All stress was released by the cracks

## Slide 23: Work Zone

## Slide 24: Reinforcements

## Slide 25: Future Monitoring
Regular monitoring of Profiles
Installation of new Network points all along TT10
Installation of a fiber optic permanent monitoring system

## Slide 26
With contributions of
Philippe Dewitte, James Ridewood, Richard Francis Morton, Stephan Cettour Cave