## Slide 1
The development of 650MHz/800kW klystron for CEPC in GLVAC
Wang Shaozhe Li Yongming

## Slide 2
Development of 650MHz/800kW klystron
Gantt chart of the work in GLVAC
Facilities establishment in GLVAC
Components manufacture in GLVAC
Final assembly & baking
Future plan
Outline

## Slide 3
Development of 650MHz/800kW klystron
Gantt chart of the work in GLVAC
Facilities establishment in GLVAC
Components manufacture in GLVAC
Final assembly & baking
Future plan
Outline

## Slide 4
Gantt chart of the work in GLVAC
Development of 650MHz/800kW klystron
To develop the 650MHz/800kW CW klystron for CEPC and push its efficiency up to 80%, IHEP, IECAS and GLVAC established the collaboration group for the klystron development in 12th 2017, and its group meeting was held every 3 months.
Collaboration group meeting held in GLVAC (6th 2018)

## Slide 5
Gantt chart of the work in GLVAC
Development of 650MHz/800kW klystron
Design
E-gun
Cavities
Collector
Coils
Oil cylinder
Operation support
Cooperation of IHEP, IECAS and GLVAC

## Slide 6
Gantt chart of the work in GLVAC
Development of 650MHz/800kW klystron
Gantt chart of the work in GLVAC
The work in GLVAC includes baking-workshop building construction, baking oven customization, clean room construction, final assembly support, collector, coils, oil cylinder, operation support and so on.

## Slide 7
Gantt chart of the work in GLVAC
Development of 650MHz/800kW klystron
Gantt chart of the work in GLVAC
The work in GLVAC also includes mold design, final assembly, baking, post processing, packaging and so on. Its time schedule starts from 12th 2017 to 12th 2019.
The Invest capital of all in GLVAC is about RMB 20,000,000

## Slide 8
Development of 650MHz/800kW klystron
Gantt chart of the work in GLVAC
Facilities establishment in GLVAC
Components manufacture in GLVAC
Final assembly & baking
Future plan
Outline

## Slide 9
Facilities establishment in GLVAC
1. Baking-workshop building construction
4th 2019
1st 2019
2nd 2019
3th 2019
Development of 650MHz/800kW klystron

## Slide 10
Facilities establishment in GLVAC
1. Baking-workshop building construction
Collaboration group meeting held in GLVAC (3th 2019)
Development of 650MHz/800kW klystron

## Slide 11
Facilities establishment in GLVAC
2. Baking oven customization
Assembling
4th 2019
End of debugging
8th 2019
Unloading
Development of 650MHz/800kW klystron
Acceptance check
3th 2019

## Slide 12
Facilities establishment in GLVAC
3. Overhead travelling crane (5T) & cooling-water machine
4th 2019
4th 2019
Development of 650MHz/800kW klystron

## Slide 13
Facilities establishment in GLVAC
Electricity expansion in GLVAC, 17-19 5th 2019
4. 400kW Electricity expansion only for baking oven
Development of 650MHz/800kW klystron

## Slide 14
Facilities establishment in GLVAC
7 meters high and air cleanliness CL-100K clean room, 6th 2019
5. Clean room
Development of 650MHz/800kW klystron

## Slide 15
Facilities establishment in GLVAC
Final assembly support, 6th 2019
6. Final assembly support
Development of 650MHz/800kW klystron

## Slide 16
Development of 650MHz/800kW klystron
Gantt chart of the work in GLVAC
Facilities establishment in GLVAC
Components manufacture in GLVAC
Final assembly & baking
Future plan
Outline

## Slide 17
Components manufacture in GLVAC
1.8 meters high and 300 kg weight, it is the largest copper collector brazed in the world, and its whole perpendicularity is less than 0.2mm
1. Copper parts of the collector
Development of 650MHz/800kW klystron

## Slide 18
Components manufacture in GLVAC
Leak hunting for the copper part of the collector in the leak rate less than -10 Pa· m3 /s after brazed
1. Copper parts of the collector
Development of 650MHz/800kW klystron

## Slide 19
Components manufacture in GLVAC
Trial assembly of the inter part of the water jacket (Only 0.2mm gap was left on one side)
2. Water jacket of the collector
Development of 650MHz/800kW klystron

## Slide 20
Components manufacture in GLVAC
Trial assembly and argon arc welding of the outer part of the water jacket
2. Water jacket of the collector
Development of 650MHz/800kW klystron

## Slide 21
Components manufacture in GLVAC
Trial assembly measurement of coils
3. Coils
Development of 650MHz/800kW klystron

## Slide 22
Components manufacture in GLVAC
Shell of oil cylinder and the high-pressure components (passed 200kV test)
4. Oil cylinder
Development of 650MHz/800kW klystron

## Slide 23
Components manufacture in GLVAC
5th 2019
5. Operation support
Development of 650MHz/800kW klystron

## Slide 24
Components manufacture in GLVAC
Drawing
Assembly
leak hunting
Baking test
Pinch off
6. Insulating part for klystron baking
Development of 650MHz/800kW klystron

## Slide 25
Drawing
Assembly
Pinch off test
leak hunting 1
Components manufacture in GLVAC
7. Pinch off tool
leak hunting 2
Development of 650MHz/800kW klystron

## Slide 26
Development of 650MHz/800kW klystron
Gantt chart of the work in GLVAC
Facilities establishment in GLVAC
Components manufacture in GLVAC
Final assembly & baking
Future plan
Outline

## Slide 27
Final assembly & baking
Assembly and leak hunting of the 2nd , 3th and 4th cavity
Development of 650MHz/800kW klystron

## Slide 28
Final assembly & baking
Assembly and leak hunting of the 2nd , 3th and 4th cavity
Development of 650MHz/800kW klystron
Collimation using laser tracker

## Slide 29
Final assembly & baking
Assembly and leak hunting of the 2nd , 3th and 4th cavities
Development of 650MHz/800kW klystron
After adjusting, the concentricity of the cavities is ±0.11mm

## Slide 30
Final assembly & baking
2. Assembly and leak hunting of the 4-5th and e-gun cavities
Development of 650MHz/800kW klystron
After adjusting, the concentricity of the cavities is ±0.18mm

## Slide 31
Final assembly & baking
3. Assembly and leak hunting of collector
Development of 650MHz/800kW klystron

## Slide 32
Final assembly & baking
4. End of final assembly
Development of 650MHz/800kW klystron

## Slide 33
Final assembly & baking
5. Move the klystron to the baking oven
Development of 650MHz/800kW klystron

## Slide 34
Final assembly & baking
6. Cover the oven
Development of 650MHz/800kW klystron

## Slide 35
Final assembly & baking
7. Start baking
Development of 650MHz/800kW klystron

## Slide 36
Development of 650MHz/800kW klystron
Gantt chart of the work in GLVAC
Facilities establishment in GLVAC
Components manufacture in GLVAC
Final assembly & baking
Future plan
Outline

## Slide 37
Future plan
Development of 650MHz/800kW klystron
Finish baking (10.25-11.28)
Klystron post processing (11.28-12.31)
Another one …

## Slide 38
Acknowledgement
Thanks !
Development of 650MHz/800kW klystron